## Project Summary
Client | ProjectConsultant | Contractor | ProjectType | ProjectName | StartDate | EndDate | ForecastDate | Delayed by (Days) | Project Completion Period (months) | Planned Progress | Actual Progress | Overall Duration | Time Elapsed | Time Remaining | TimeElapsed% | TimeRemaining%
Line Investments & Property L.L.C | NEB Engineering Consultancy Office | Shapoorji Pallonji Mideast L.L.C | Construction | Khalifa City Mall | 43282 | 44074 | 44104 | 0 | 26.04 |  |  | 792 | 792 | 0 | 100 | 0

## Health&Safety
HealthSafetyType | StartDate | EndDate | ManHours | Accidents/First Aid cases | FAT | LTI | SafetyInduction | In House Training Hrs | Training (3rdParty)Hrs
Period | 44123 | 44131 | 345 | 3 | 0 | 0 | 7 | 4 | 0
Upto Date | 43282 | 44074 | 20607321 | 87 | 1 | 2 | 32675 | 286524 | 8674

## SubmittalOverview
SubmittalStatus | SubmittalCount
A | 9156
B | 1160
C | 152
D | 306
E | 5
P | 0
UR | 0

## SubmittalConstruction
ActivityType | SubmittalCount
WIR | 6947
SD | 895
TS | 629
MS | 1910
MIR | 2064

## QAQCSubmittal
TechnicalSubmittalType | SubmittalCount
PQ | 164
MSS | 8

## Closeout
TechnicalSubmittalType | SubmittalCount
OMM | 91
Training Manuals | 29