## Sheet1
Order | Activitytype | InternalRefNumber | System | Subsystem | Building | level | trade | room | createdcompanyname | SubmittalStatus | SubmittalDate
1 | SD | 5PML-KCM-5TR-AB-022 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43325
1 | SD | 5PML-KCM-AR-AB-0087 | Finishes | Car Park | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43411
1 | SD | 5PML-KCM-RCP-AR-AB-03 | Finishes | Ceiling | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43471
1 | SD | PML-KCM-AR-AB-0063 | Finishes | Floor | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-AAES-ME-13231-AR-AB-001 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-AAES-ME-13231-AR-AB-002 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-AAES-ME-13231-AR-AB-007 | Doors & Windows | Overhead Sectional doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-AAES-ME-13231-AR-AB-008 | Doors & Windows | Overhead Sectional doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-AAES-ME-13231-AR-AB-009 | Doors & Windows | Overhead Sectional doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-AR-A8-0251-1.0 | Finishes | Ceiling | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-AR-AB-0001 | Walls | Block Work | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43751
1 | SD | SPML-KCM-AR-AB-0005 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0005b | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-AR-AB-0005c | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-0005d | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-0005e | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-0006 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-AR-AB-0006 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-AR-AB-0006 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-AR-AB-0007 | Finishes | Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-AR-AB-0007a | Finishes | Wall | Al Forsan Central Mall | Attic Level | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0008 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-AR-AB-0008 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-AR-AB-0009 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-0009a | Finishes | Floor | Al Forsan Central Mall | Attic Level | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-000Sa | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0010 | Finishes | Ceiling | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-AR-AB-0013 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0017 | Finishes | Floor | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-AR-AB-0018 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-AR-AB-0019 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0020 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-AR-AB-0021 | Finishes | Ceiling | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-AR-AB-0022 | Finishes | Ceiling | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-AR-AB-0025 | Finishes | Ceiling | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-AR-AB-0026 | Finishes | Wall | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-0027 | Finishes | Floor | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-AR-AB-0029 | Walls | Block Work | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43104
1 | SD | SPML-KCM-AR-AB-0032 | Finishes | Car Park | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0032 | Finishes | Car Park | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-AR-AB-0032 | Finishes | Car Park | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-0032 | Finishes | Car Park | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-AR-AB-0032 | Finishes | Car Park | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM-AR-AB-0032 | Finishes | Car Park | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-AR-AB-0034 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-AR-AB-0034 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-AR-AB-0034 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-AR-AB-0035 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-AR-AB-0036 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-AR-AB-0036 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-AR-AB-0036 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-AR-AB-0037 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0037 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-AR-AB-0038 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-AR-AB-0038 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-AR-AB-0039 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0039 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-AR-AB-0043 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-AR-AB-0043 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-0044 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-0044 | Finishes | Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-0045 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-AR-AB-0046 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-AR-AB-0047 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-AR-AB-0048 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-AR-AB-0049 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43411
1 | SD | SPML-KCM-AR-AB-0050 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-AR-AB-0050 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-AR-AB-0051 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-AR-AB-0052 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-AR-AB-0053 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43471
1 | SD | SPML-KCM-AR-AB-0053 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-AR-AB-0054 | Finishes | Floor | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-AR-AB-0055 | Finishes | Floor | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-AR-AB-0062 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-AR-AB-0062 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-AR-AB-0062 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-AR-AB-0062 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43411
1 | SD | SPML-KCM-AR-AB-0062 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-AR-AB-0062 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-AR-AB-0062 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-AR-AB-0063 | Finishes | Floor | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-AR-AB-0063 | Finishes | Floor | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-AR-AB-0063 | Finishes | Floor | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-AR-AB-0063 | Finishes | Floor | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-AR-AB-0063 | Finishes | Floor | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-AR-AB-0063 | Finishes | Floor | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-AR-AB-0064 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-AR-AB-0066 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-AR-AB-0066 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-AR-AB-0066 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43471
1 | SD | SPML-KCM-AR-AB-0066 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-AR-AB-0066 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-AR-AB-0066 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-AR-AB-0066 | Finishes | Floor | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-AR-AB-0068 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-AR-AB-0068 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-AR-AB-0069 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-AR-AB-0069 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-AR-AB-0069 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-AR-AB-0070 | Finishes | Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-AR-AB-0070 | Finishes | Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-AR-AB-0071 | Finishes | Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-AR-AB-0071 | Finishes | Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-AR-AB-0072 | Finishes | Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-AR-AB-0072 | Finishes | Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-AR-AB-0073 | Finishes | Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-AR-AB-0074 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-AR-AB-0075 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-AR-AB-0076 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-AR-AB-0076 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-AR-AB-0076 | Finishes | Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-AR-AB-0085 | Finishes | Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-AR-AB-0086 | Finishes | Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-AR-AB-0087 | Finishes | Car Park | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-AR-AB-0087 | Finishes | Car Park | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-AR-AB-0087 | Finishes | Car Park | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-AR-AB-0087 | Finishes | Car Park | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-AR-AB-0087 | Finishes | Car Park | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-AR-AB-0087 | Finishes | Car Park | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-AR-AB-0087 | Finishes | Car Park | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43471
1 | SD | SPML-KCM-AR-AB-0087 | Finishes | Car Park | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-AR-AB-0087 | Finishes | Car Park | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-AR-AB-0087 | Finishes | Car Park | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-AR-AB-009a | Finishes | Ceiling | Al Forsan Central Mall | Attic Level | Architectural | NULL | Global Admin | B | 43411
1 | SD | SPML-KCM-AR-AB-0100 | Finishes | Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0101 | Finishes | Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-0102 | Finishes | Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM-AR-AB-0103 | Finishes | Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0111 | Finishes | Floor | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-AR-AB-0112 | Finishes | Ceiling | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-AR-AB-0114 | Finishes | Ceiling | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-AR-AB-0118 | Finishes | Ceiling | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-AR-AB-0118A | Finishes | Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-AR-AB-0119 | Finishes | Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-AR-AB-0120 | Finishes | Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-AR-AB-0121 | Finishes | Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-AR-AB-0122 | Finishes | Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-AR-AB-0123 | Finishes | Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-AR-AB-0124 | Finishes | Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-AR-AB-0242-1.0 | Finishes | Ceiling | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-AR-AB-0242-2.0 | Finishes | Ceiling | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-AR-AB-0242-3.0 | Finishes | Ceiling | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-AR-AB-0242-4.0 | Finishes | Ceiling | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-AR-AB-0242-5.0 | Finishes | Ceiling | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-AR-AB-0242-6.0 | Finishes | Ceiling | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-AR-AB-0242-7.0 | Finishes | Ceiling | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-AR-AB-0242-8.0 | Finishes | Ceiling | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-AR-AB-0242-9.0 | Finishes | Ceiling | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-AR-AB-0251-2.0 | Finishes | Ceiling | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-AR-AB-0251-3.0 | Finishes | Ceiling | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-AR-AB-0251-4.0 | Finishes | Ceiling | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-AR-AB-0251-5.0 | Finishes | Ceiling | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0251-6.0 | Finishes | Ceiling | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-AR-AB-0251-7.0 | Finishes | Ceiling | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-0251-8.0 | Finishes | Ceiling | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-0251-9.0 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM-AR-AB-040 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-040 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-AR-AB-040 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-AR-AB-041 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-AR-AB-041 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM-AR-AB-041 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-AR-AB-042 | Finishes | Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-ASC-AR-AB-001 | Floor | Floor Screed | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43661
1 | SD | SPML-KCM-ASC-AR-AB-002 | Floor | Floor Screed | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43662
1 | SD | SPML-KCM-ASC-AR-AB-004 | Floor | Floor Screed | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43662
1 | SD | SPML-KCM-ASC-AR-AB-005 | Floor | Floor Screed | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43662
1 | SD | SPML-KCM-ASC-AR-AB-006 | Floor | Floor Screed | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43664
1 | SD | SPML-KCM-ASC-AR-AB-007 | Floor | Floor Screed | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43720
1 | SD | SPML-KCM-ASC-AR-AB-008 | Floor | Floor Screed | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43737
1 | SD | SPML-KCM-ASC-AR-AB-009 | Floor | Floor Screed | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43760
1 | SD | SPML-KCM-ASC-AR-AB-010 | Concrete Works | Water Proofing | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43669
1 | SD | SPML-KCM-ASC-AR-AB-011 | Concrete Works | Water Proofing | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43729
1 | SD | SPML-KCM-ASC-AR-AB-013 | Concrete Works | Water Proofing | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43104
1 | SD | SPML-KCM-ASC-AR-AB-014 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43673
1 | SD | SPML-KCM-ASC-AR-AB-015 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43698
1 | SD | SPML-KCM-ASC-AR-AB—012 | Concrete Works | Water Proofing | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43673
1 | SD | SPML-KCM-ASCCO-WP-AR-AB-001 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-ASCCO-WP-AR-AB-002 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43656
1 | SD | SPML-KCM-ASCCO-WP-AR-AB-003 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43717
1 | SD | SPML-KCM-ASCCO-WP-AR-AB-004 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43656
1 | SD | SPML-KCM-ASCCO-WP-AR-AB-005 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43746
1 | SD | SPML-KCM-ASCCO-WP-AR-AB-006 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-ASCCO-WP-AR-AB-007 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43656
1 | SD | SPML-KCM-ASCCO-WP-AR-AB-008 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43659
1 | SD | SPML-KCM-ASCCO-WP-AR-AB-009 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43657
1 | SD | SPML-KCM-ASCCO-WP-AR-AB-010 | Concrete Works | Water Proofing | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43659
1 | SD | SPML-KCM-BCS-AR-AB-01 | Finishes | Ceiling | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-BCS-AR-AB-02 | Finishes | Ceiling | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-BO-AR-AB-001 | Space Protection System | Bollards | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-CBB-AR-AB-001 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-CBB-AR-AB-002 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-CBB-AR-AB-003 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-CBB-AR-AB-004 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-CBB-AR-AB-005 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-CBB-AR-AB-006 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-CBB-AR-AB-007 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-CBB-AR-AB-008 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-CBB-AR-AB-009 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-CBB-AR-AB-010 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-CBB-AR-AB-011 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-CBB-AR-AB-012 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-CBB-AR-AB-013 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43411
1 | SD | SPML-KCM-CBB-AR-AB-014 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-CBB-AR-AB-015 | Doors & Windows | Steel Doors | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-CBB-AR-AB-016 | Doors & Windows | Steel Doors | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-CBB-AR-AB-017 | Doors & Windows | Steel Doors | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-CBB-AR-AB-018 | Doors & Windows | Steel Doors | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-CBB-AR-AB-019 | Doors & Windows | Steel Doors | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-CHB-AR-AB-01 | Waste Management | Garbage Compactor | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-DMI-AB-0001 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43680
1 | SD | SPML-KCM-DMI-AB-0002 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43694
1 | SD | SPML-KCM-DMI-AB-0003 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43704
1 | SD | SPML-KCM-DMI-AB-0004 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 44137
1 | SD | SPML-KCM-DMI-AB-0005 | Cladding | ACP Cladding | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 44144
1 | SD | SPML-KCM-DMI-AB-0006 | Cladding | ACP Cladding | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43605
1 | SD | SPML-KCM-DMI-AB-0007_1 | Cladding | ACP Cladding | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43605
1 | SD | SPML-KCM-DMI-AB-0007_2 | Cladding | ACP Cladding | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43605
1 | SD | SPML-KCM-DMI-AB-0010 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43702
1 | SD | SPML-KCM-DMI-AB-0011 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43629
1 | SD | SPML-KCM-DMI-AB-0012 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43669
1 | SD | SPML-KCM-DMI-AB-0013 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43710
1 | SD | SPML-KCM-DMI-AB-0014 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43629
1 | SD | SPML-KCM-DMI-AB-0015 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43624
1 | SD | SPML-KCM-DMI-AB-0016 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43624
1 | SD | SPML-KCM-DMI-AB-0017 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43748
1 | SD | SPML-KCM-DMI-AB-0053 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43626
1 | SD | SPML-KCM-DMI-AB-0054 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Mezzanine | Architectural | NULL | Global Admin | B | 44174
1 | SD | SPML-KCM-DMI-AB-0055 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43104
1 | SD | SPML-KCM-DMI-AB-0056 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43627
1 | SD | SPML-KCM-DMI-AB-0057 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43660
1 | SD | SPML-KCM-DMI-AB-0058 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43633
1 | SD | SPML-KCM-DMI-AB-0059 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43730
1 | SD | SPML-KCM-DMI-AB-0060 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-DMI-AB-0061 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43633
1 | SD | SPML-KCM-DMI-AB-0062 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43640
1 | SD | SPML-KCM-DMI-AB-0063 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43641
1 | SD | SPML-KCM-DMI-AB-0064 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43872
1 | SD | SPML-KCM-DMI-AB-0065 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43641
1 | SD | SPML-KCM-DMI-AB-0066 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43641
1 | SD | SPML-KCM-DMI-AB-0067 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43697
1 | SD | SPML-KCM-DMI-AB-0068 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43653
1 | SD | SPML-KCM-DMI-AB-0069 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43717
1 | SD | SPML-KCM-DMI-AB-0070 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43649
1 | SD | SPML-KCM-DMI-AB-0071 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43642
1 | SD | SPML-KCM-DMI-AB-0072 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43645
1 | SD | SPML-KCM-DMI-AB-0073 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43768
1 | SD | SPML-KCM-DMI-AB-0074 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43645
1 | SD | SPML-KCM-DMI-AB-0075 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43768
1 | SD | SPML-KCM-DMI-AB-0076 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43652
1 | SD | SPML-KCM-DMI-AB-0077 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43652
1 | SD | SPML-KCM-DMI-AB-0078 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Mezzanine | Architectural | NULL | Global Admin | B | 43652
1 | SD | SPML-KCM-DMI-AB-0079 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Mezzanine | Architectural | NULL | Global Admin | B | 43695
1 | SD | SPML-KCM-DMI-AB-0080 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43653
1 | SD | SPML-KCM-DMI-AB-0083 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43720
1 | SD | SPML-KCM-DMI-AB-0084 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43653
1 | SD | SPML-KCM-DMI-AB-0085 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43702
1 | SD | SPML-KCM-DMI-AB-0086 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43654
1 | SD | SPML-KCM-DMI-AB-0087 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43736
1 | SD | SPML-KCM-DMI-AB-0088 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 44157
1 | SD | SPML-KCM-DMI-AB-0109 | Doors & Windows | Aluminum Door | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43655
1 | SD | SPML-KCM-DMI-AB-0110 | Doors & Windows | Aluminum Door | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43655
1 | SD | SPML-KCM-DMI-AB-0111 | Doors & Windows | Aluminum Door | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43696
1 | SD | SPML-KCM-DMI-AB-0112 | Doors & Windows | Aluminum Door | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43768
1 | SD | SPML-KCM-ENE-AR-AB-0001 | FF&E | Wooden Benches | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-ENE-AR-AB-0002 | FF&E | Wooden Benches | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-ENE-AR-AB-0003 | FF&E | Wooden Benches | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-ENE-AR-AB-0004 | FF&E | Wooden Benches | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-ENE-AR-AB-0005 | FF&E | Wooden Benches | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43411
1 | SD | SPML-KCM-ENE-AR-AB-0006 | FF&E | Wooden Benches | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-ENE-AR-AB-0007 | FF&E | Wooden Benches | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-ENE-AR-AB-0008 | FF&E | Wooden Benches | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-ENE-AR-AB-0009 | FF&E | Wooden Benches | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-FIO-AR-AB-001 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-FIO-AR-AB-002 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-FIO-AR-AB-003 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-FIO-AR-AB-004 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-FIO-AR-AB-005 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-FIO-AR-AB-006 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-FIO-AR-AB-007 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-FN-AR-AB-001 | Finishes | Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-FN-AR-AB-002 | Finishes | Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-FRZ-STR-AB-1102 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Attic Level | Structural | NULL | Global Admin | B | 43523
1 | SD | SPML-KCM-FRZ-STR-AB-1103 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Attic Level | Structural | NULL | Global Admin | B | 43534
1 | SD | SPML-KCM-FRZ-STR-AB-112 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43545
1 | SD | SPML-KCM-FRZ-STR-AB-113 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43517
1 | SD | SPML-KCM-FRZ-STR-AB-1212 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43536
1 | SD | SPML-KCM-FRZ-STR-AB-1213 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-FRZ-STR-AB-122 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43517
1 | SD | SPML-KCM-FRZ-STR-AB-1222 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43587
1 | SD | SPML-KCM-FRZ-STR-AB-1223 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43614
1 | SD | SPML-KCM-FRZ-STR-AB-123 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43767
1 | SD | SPML-KCM-FRZ-STR-AB-1233 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-FRZ-STR-AB-1242 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43842
1 | SD | SPML-KCM-FRZ-STR-AB-1243 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43844
1 | SD | SPML-KCM-FRZ-STR-AB-1252 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43523
1 | SD | SPML-KCM-FRZ-STR-AB-1253 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43526
1 | SD | SPML-KCM-FRZ-STR-AB-1262 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43557
1 | SD | SPML-KCM-FRZ-STR-AB-1272 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-FRZ-STR-AB-1312 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43638
1 | SD | SPML-KCM-FRZ-STR-AB-1313 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43748
1 | SD | SPML-KCM-FRZ-STR-AB-132 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43517
1 | SD | SPML-KCM-FRZ-STR-AB-1322 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43768
1 | SD | SPML-KCM-FRZ-STR-AB-1323 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-FRZ-STR-AB-133 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43519
1 | SD | SPML-KCM-FRZ-STR-AB-1332 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43529
1 | SD | SPML-KCM-FRZ-STR-AB-1333 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43551
1 | SD | SPML-KCM-FRZ-STR-AB-1342 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43572
1 | SD | SPML-KCM-FRZ-STR-AB-1343 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-FRZ-STR-AB-1353 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-FRZ-STR-AB-1362 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43529
1 | SD | SPML-KCM-FRZ-STR-AB-1363 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43538
1 | SD | SPML-KCM-FRZ-STR-AB-142 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43533
1 | SD | SPML-KCM-FRZ-STR-AB-143 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43551
1 | SD | SPML-KCM-FRZ-STR-AB-152 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43519
1 | SD | SPML-KCM-FRZ-STR-AB-153 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43544
1 | SD | SPML-KCM-FRZ-STR-AB-162 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43521
1 | SD | SPML-KCM-FRZ-STR-AB-163 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43522
1 | SD | SPML-KCM-FRZ-STR-AB-172 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43545
1 | SD | SPML-KCM-FRZ-STR-AB-173 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43558
1 | SD | SPML-KCM-FRZ-STR-AB-183 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43522
1 | SD | SPML-KCM-FRZ-STR-AB-192 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43522
1 | SD | SPML-KCM-FRZ-STR-AB-193 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43523
1 | SD | SPML-KCM-FRZ-STR-AB—1263 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43529
1 | SD | SPML-KCM-FRZ-STR—AB-182 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43572
1 | SD | SPML-KCM-FRZ—STR-AB-1352 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43529
1 | SD | SPML-KCM-GFI-AR-AB-001 | Finishes | Toilet Cubicles | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-GFI-AR-AB-002 | Finishes | Toilet Cubicles | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-GFI-AR-AB-003 | Finishes | Toilet Cubicles | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-GFI-AR-AB-004 | Finishes | Toilet Cubicles | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-GFI-AR-AB-006 | Finishes | Toilet Cubicles | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-GFI-AR-AB-007 | Finishes | Toilet Cubicles | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-GFI-AR-AB-008 | Finishes | Toilet Cubicles | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-GFI-AR-AB-009 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-GFI-AR-AB-00S | Finishes | Toilet Cubicles | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-IBN-AR-AB-0022 | Finishes | Demised Wall | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-IBN-AR-AB-0023 | Finishes | Demised Wall | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-IBN-AR-AB-0024 | Finishes | Demised Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-IBN-AR-AB-0027 | Finishes | Demised Wall | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-IBN-AR-AB-0052 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43744
1 | SD | SPML-KCM-IBN-AR-AB-0053 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43781
1 | SD | SPML-KCM-IBN-AR-AB-0054 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43744
1 | SD | SPML-KCM-IBN-AR-AB-0055 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43781
1 | SD | SPML-KCM-IBN-AR-AB-0064a | Cladding | Wall Cladding | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-IBN-AR-AB-0068a | Cladding | Wall Cladding | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-IBN-AR-AB-0069a | Cladding | Wall Cladding | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-IBN-AR-AB-0074a | Cladding | Wall Cladding | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-IBN-AR-AB-0076a | Cladding | Wall Cladding | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-IBN-AR-AB-015 | Cladding | Column Cladding | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-IBN-AR-AB-017 | Cladding | Column Cladding | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43471
1 | SD | SPML-KCM-IBN-AR-AB-018 | Cladding | Column Cladding | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-IBN-AR-AB-019 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-IBN-AR-AB-020 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-IBN-AR-AB-021 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-IKK-AR-AB-001 | Expansion | Expansion Joint | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-IKK-AR-AB-002 | Expansion | Expansion Joint | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-IKK-AR-AB-003 | Expansion | Expansion Joint | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-IKK-AR-AB-004 | Expansion | Expansion Joint | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-IKK-AR-AB-005 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-IKK-AR-AB-006 | Expansion | Expansion Joint | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-JA-AR-AB-011 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-JA-AR-AB-012 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-JA-AR-AB-013 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-JA-AR-AB-014 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-JA-AR-AB-015 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-JA-AR-AB-026 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-JA-AR-AB-027 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM-JA-AR-AB-032 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-JA-AR-AB-033 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-lBN-AR-AB-0075a | Cladding | Wall Cladding | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-LYK-AR-AB-016 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-LYK-AR-AB-019 | Cladding | Column Cladding | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-MEP-AB -1 | Plumbing | Drainage | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-MEP-AB -10 | Plumbing | Drainage | Al Forsan Central Mall | First Floor | Mechanical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -100 | ELV | Public Address | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-MEP-AB -101 | ELV | CCTV | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-MEP-AB -102 | ELV | Access Control | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-MEP-AB -103 | Power Distribution | Containment | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43471
1 | SD | SPML-KCM-MEP-AB -104 | ELV | Structured Cabling | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-MEP-AB -105 | Power Distribution | Small Power | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-MEP-AB -106 | ELV | Fire Alarm | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-MEP-AB -107 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-MEP-AB -108 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -109 | ELV | Public Address | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -11 | Plumbing | Storm Water | Al Forsan Central Mall | First Floor | Mechanical | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-MEP-AB -110 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-MEP-AB -111 | ELV | Structured Cabling | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -112 | ELV | Disabled Toilet Alarm | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-MEP-AB -113 | ELV | Structured Cabling | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-MEP-AB -114 | Power Distribution | Small Power | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -115 | Lighting | Lighting Fixture | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-MEP-AB -116 | Power Distribution | Small Power | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-MEP-AB -117 | ELV | Fire Alarm | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-MEP-AB -118 | Lighting | Lighting Fixture | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-MEP-AB -119 | ELV | CCTV | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-MEP-AB -12 | Plumbing | Water supply | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-MEP-AB -120 | ELV | Public Address | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-MEP-AB -121 | ELV | Access Control | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-MEP-AB -122 | ELV | Structured Cabling | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-MEP-AB -123 | Earthing & Lightning Protection | Lightning Protection | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -124 | ELV | Disabled Toilet Alarm | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -125 | ELV | CCTV | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -126 | ELV | Structured Cabling | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-MEP-AB -127 | Earthing & Lightning Protection | Lightning Protection | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-MEP-AB -128 | Power Distribution | Small Power | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-MEP-AB -129 | Power Distribution | Small Power | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-MEP-AB -13 | Plumbing | Drainage | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-MEP-AB -130 | Power Distribution | Small Power | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -131 | Power Distribution | Small Power | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-MEP-AB -132 | ELV | Fire Alarm | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -133 | Lighting | Lighting Fixture | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -134 | ELV | CCTV | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM-MEP-AB -135 | ELV | Public Address | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -136 | ELV | Access Control | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-MEP-AB -137 | ELV | Structured Cabling | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -138 | ELV | Disabled Toilet Alarm | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -139 | ELV | Structured Cabling | Al Forsan Central Mall | First Floor | Electrical | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-MEP-AB -14 | Plumbing | Storm Water | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-MEP-AB -140 | Earthing & Lightning Protection | Lightning Protection | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -141 | Lighting | Lighting Fixture | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -142 | Power Distribution | Small Power | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -143 | Power Distribution | Small Power | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-MEP-AB -144 | Power Distribution | Small Power | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-MEP-AB -145 | ELV | Fire Alarm | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-MEP-AB -146 | ELV | CCTV | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-MEP-AB -147 | ELV | Public Address | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43411
1 | SD | SPML-KCM-MEP-AB -148 | ELV | Structured Cabling | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-MEP-AB -149 | Lighting | Lighting Fixture | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-MEP-AB -15 | Plumbing | Storm Water | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-MEP-AB -150 | Earthing & Lightning Protection | Lightning Protection | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-MEP-AB -151 | Power Distribution | Small Power | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-MEP-AB -152 | Lighting | Lighting Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-MEP-AB -153 | Power Distribution | LV Cable | Al Forsan Central Mall | LV Room | Electrical | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-MEP-AB -154 | Power Distribution | LV Cable | Al Forsan Central Mall | LV Room | Electrical | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-MEP-AB -155 | Power Distribution | LV Cable | Al Forsan Central Mall | MCC Room | Electrical | NULL | Global Admin | B | 43471
1 | SD | SPML-KCM-MEP-AB -156 | HV System | Transformer | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-MEP-AB -157 | Power Distribution | Generator | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-MEP-AB -158 | Lighting | Lighting Fixture | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-MEP-AB -159 | Lighting | Lighting Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-MEP-AB -16 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-MEP-AB -160 | Lighting | Lighting Fixture | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -161 | Lighting | Lighting Fixture | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -162 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-MEP-AB -163 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -164 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-MEP-AB -165 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-MEP-AB -166 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -167 | HV System | Transformer | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-MEP-AB -168 | Power Distribution | UPS | Al Forsan Central Mall | UPS Room | Electrical | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-MEP-AB -169 | Lighting | Lighting Fixture | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-MEP-AB -17 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-MEP-AB -170 | HV System | Transformer | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-MEP-AB -171 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-MEP-AB -172 | Lighting | Lighting Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-MEP-AB -173 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-MEP-AB -174 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-MEP-AB -175 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -176 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -177 | ELV | Disabled Toilet Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -178 | ELV | Access Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-MEP-AB -179 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-MEP-AB -18 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-MEP-AB -19 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -2 | Plumbing | Water supply | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-MEP-AB -20 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -21 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -22 | Plumbing | Water supply | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-MEP-AB -23 | Plumbing | Water supply | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-MEP-AB -24 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | First Floor | Mechanical | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-MEP-AB -25 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | First Floor | Mechanical | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-MEP-AB -26 | Plumbing | Water supply | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -27 | Plumbing | Water supply | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-MEP-AB -28 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | First Floor | Mechanical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -29 | Plumbing | Water supply | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -3 | Plumbing | Drainage | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-MEP-AB -30 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM-MEP-AB -31 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -32 | Earthing & Lightning Protection | Earthing | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-MEP-AB -33 | Earthing & Lightning Protection | Lightning Protection | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -34 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -35 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-MEP-AB -36 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -37 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -38 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -39 | Power Distribution | Small Power | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-MEP-AB -4 | Plumbing | Storm Water | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -40 | Power Distribution | Small Power | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-MEP-AB -41 | ELV | Fire Alarm | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-MEP-AB -42 | ELV | Public Address | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-MEP-AB -43 | ELV | CCTV | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43411
1 | SD | SPML-KCM-MEP-AB -44 | ELV | Access Control | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-MEP-AB -45 | Power Distribution | Containment | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-MEP-AB -46 | ELV | Structured Cabling | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-MEP-AB -47 | Power Distribution | Small Power | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-MEP-AB -48 | ELV | Fire Alarm | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-MEP-AB -49 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-MEP-AB -5 | Plumbing | Water supply | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -50 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-MEP-AB -51 | ELV | Public Address | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43471
1 | SD | SPML-KCM-MEP-AB -52 | Lighting | Lighting Fixture | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-MEP-AB -53 | ELV | Structured Cabling | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-MEP-AB -54 | ELV | Disabled Toilet Alarm | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-MEP-AB -55 | ELV | Structured Cabling | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-MEP-AB -56 | Power Distribution | Containment | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -57 | Lighting | Lighting Fixture | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -58 | Power Distribution | Small Power | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-MEP-AB -59 | Power Distribution | Small Power | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -6 | Plumbing | Drainage | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-MEP-AB -60 | Plumbing | Drainage | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-MEP-AB -61 | Plumbing | Water supply | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-MEP-AB -62 | Plumbing | Drainage | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -63 | Plumbing | Storm Water | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-MEP-AB -64 | Plumbing | Water supply | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-MEP-AB -65 | Plumbing | Water supply | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-MEP-AB -66 | Plumbing | Drainage | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-MEP-AB -67 | Plumbing | Storm Water | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-MEP-AB -68 | Plumbing | Water supply | Al Forsan Central Mall | First Floor | Mechanical | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-MEP-AB -69 | Plumbing | Drainage | Al Forsan Central Mall | First Floor | Mechanical | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-MEP-AB -7 | Plumbing | Drainage | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-MEP-AB -70 | Plumbing | Storm Water | Al Forsan Central Mall | First Floor | Mechanical | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-MEP-AB -71 | Plumbing | Water supply | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -72 | Plumbing | Drainage | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -73 | Plumbing | Water supply | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-MEP-AB -74 | Plumbing | Storm Water | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-MEP-AB -75 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-MEP-AB -76 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-MEP-AB -77 | Plumbing | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-MEP-AB -78 | Plumbing | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -79 | Plumbing | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-MEP-AB -8 | Plumbing | Storm Water | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-MEP-AB -80 | Plumbing | Sprinkler system | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -81 | Plumbing | Water supply | Al Forsan Central Mall | Ground Floor | Mechanical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -82 | Plumbing | Sprinkler system | Al Forsan Central Mall | First Floor | Mechanical | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM-MEP-AB -83 | Plumbing | Sprinkler system | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -84 | Plumbing | Water supply | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-MEP-AB -85 | Plumbing | Water supply | Al Forsan Central Mall | First Floor | Mechanical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -86 | Plumbing | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-AB -87 | Plumbing | Water supply | Al Forsan Central Mall | Roof Floor | Mechanical | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-MEP-AB -88 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -89 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -9 | Plumbing | Water supply | Al Forsan Central Mall | First Floor | Mechanical | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-MEP-AB -90 | Earthing & Lightning Protection | Earthing | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-AB -91 | Earthing & Lightning Protection | Lightning Protection | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-MEP-AB -92 | Lighting | Lighting Fixture | Al Forsan Central Mall | Roof Floor | Electrical | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-MEP-AB -93 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-MEP-AB -94 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-MEP-AB -95 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43411
1 | SD | SPML-KCM-MEP-AB -96 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-MEP-AB -97 | Power Distribution | Small Power | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-MEP-AB -98 | Power Distribution | Small Power | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-MEP-AB -99 | ELV | Fire Alarm | Al Forsan Central Mall | Basement Floor | Electrical | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-MEP-AB-BSM-FFG-001 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-MEP-AB-BSM-FFG-001.1 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-MEP-AB-IR-0001 | LandScaping | Irrigation System | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-MEP-AB-L00-001 | LandScaping | Irrigation System | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-MEP-AB-L01-IR-001 | LandScaping | Irrigation System | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43471
1 | SD | SPML-KCM-MEP-AB-LOO-IR-010 | LandScaping | Irrigation System | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-MEP-BSM-PGS-AB-001 | ELV | Parking Guidnce | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-MEP-BSM-PGS-AB-002 | ELV | Parking Guidnce | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM-MEP-L00-PGS-AB-001 | ELV | Parking Guidnce | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-MEP-L00-PGS-AB-002 | ELV | Parking Guidnce | Al Forsan Central Mall | Ground Floor | Electrical | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-OSS-AR-AB-001 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-OTIS-STR-AB-001 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43712
1 | SD | SPML-KCM-OTIS-STR-AB-003 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43874
1 | SD | SPML-KCM-OTIS-STR-AB-004 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43104
1 | SD | SPML-KCM-OTIS-STR-AB-005 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43680
1 | SD | SPML-KCM-OTIS-STR-AB-006 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43720
1 | SD | SPML-KCM-OTIS-STR-AB-007 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43754
1 | SD | SPML-KCM-OTIS-STR-AB-008 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43699
1 | SD | SPML-KCM-OTIS-STR-AB-009 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43706
1 | SD | SPML-KCM-OTIS-STR-AB-010 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 44128
1 | SD | SPML-KCM-OTIS-STR-AB-011 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43704
1 | SD | SPML-KCM-OTIS-STR-AB-012 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 44171
1 | SD | SPML-KCM-OTIS-STR-AB-013 | Lift System | Escalator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43719
1 | SD | SPML-KCM-OTIS-STR-AB-014 | Lift System | Escalator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43704
1 | SD | SPML-KCM-OTIS-STR-AB-015 | Lift System | Escalator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43709
1 | SD | SPML-KCM-OTIS-STR-AB-018 | Lift System | Travalator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43715
1 | SD | SPML-KCM-OTIS-STR-AB-020 | Lift System | Elevator | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43722
1 | SD | SPML-KCM-OTIS-STR-AB-021 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43726
1 | SD | SPML-KCM-OTIS-STR-AB-022 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43764
1 | SD | SPML-KCM-OTIS-STR-AB-024 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43739
1 | SD | SPML-KCM-OTIS-STR-AB-025 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43740
1 | SD | SPML-KCM-OTIS-STR-AB-026 | Lift System | Escalator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43744
1 | SD | SPML-KCM-OTIS—STR-AB-017 | Lift System | Travalator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43712
1 | SD | SPML-KCM-PLS-LS-AB-001 | LandScaping | Urban Garden | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-PLS-LS-AB-001 | LandScaping | Urban Garden | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-PLS-LS-AB-002 | LandScaping | Urban Garden | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-PLS-LS-AB-002 | LandScaping | Urban Garden | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-PLS-LS-AB-003 | LandScaping | Urban Garden | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-PLS-LS-AB-003 | LandScaping | Urban Garden | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-PLS-LS-AB-004 | LandScaping | Urban Garden | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-PLS-LS-AB-005 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-PLS-LS-AB-006 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-PLS-LS-AB-007 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-PLS-LS-AB-008 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-PLS-LS-AB-009 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-PLS-LS-AB-010 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-PLS-LS-AB-011 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-PLS-LS-AB-011 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-PLS-LS-AB-012 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-PLS-LS-AB-012 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-PLS-LS-AB-013 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-PLS-LS-AB-014 | LandScaping | Urban Garden | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-PLS-LS-AB-015 | LandScaping | Urban Garden | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-PLS-LS-AB-018 | LandScaping | Urban Garden | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-PLS-LS-AB-023 | LandScaping | Urban Garden | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM-PLS-LS-AB-024 | LandScaping | Urban Garden | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-PMTE-AR-AB-008 | Structural System | Steel Structure | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-PMTE-AR-AB-009 | Structural System | Steel Structure | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-PMTE-AR-AB-011 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-PMTE-AR-AB-012 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-PMTE-AR-AB-014 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-PMTE-AR-AB-015 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-PMTE-AR-AB-016 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-PMTE-AR-AB-017 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-PMTE-AR-AB-024 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43411
1 | SD | SPML-KCM-PMTE-AR-AB-026 | Structural System | Steel Structure | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-RCP-AR-AB-01 | Finishes | Ceiling | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-RCP-AR-AB-02 | Finishes | Ceiling | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-RCP-AR-AB-04 | Finishes | Ceiling | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-RCP-AR-AB-05 | Finishes | Ceiling | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-RCP-AR-AB-06 | Finishes | Ceiling | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-RSL-VE'i-AR—AB-1039-D | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-RSL-VES-4R-AB-1057 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-RSL-VES-AR-AB-1001 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-RSL-VES-AR-AB-1001A | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-RSL-VES-AR-AB-1001B | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-RSL-VES-AR-AB-1001C | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-RSL-VES-AR-AB-1001D | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-RSL-VES-AR-AB-1002 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-RSL-VES-AR-AB-1002A | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43471
1 | SD | SPML-KCM-RSL-VES-AR-AB-1002B | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-RSL-VES-AR-AB-1002C | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-RSL-VES-AR-AB-1002D | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-RSL-VES-AR-AB-1003 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-RSL-VES-AR-AB-1004 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-RSL-VES-AR-AB-1005 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-RSL-VES-AR-AB-1006 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-RSL-VES-AR-AB-1007 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-RSL-VES-AR-AB-1008 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-RSL-VES-AR-AB-1017 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-RSL-VES-AR-AB-1018 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-RSL-VES-AR-AB-1019 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-RSL-VES-AR-AB-1020 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-RSL-VES-AR-AB-1021 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-RSL-VES-AR-AB-1022 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-RSL-VES-AR-AB-1023 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-RSL-VES-AR-AB-1024 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-RSL-VES-AR-AB-1025 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-RSL-VES-AR-AB-1026 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-RSL-VES-AR-AB-1039 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-RSL-VES-AR-AB-1039-A | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-RSL-VES-AR-AB-1039-B | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-RSL-VES-AR-AB-1039-C | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-RSL-VES-AR-AB-1039-E | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-RSL-VES-AR-AB-1039-F | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-RSL-VES-AR-AB-1039-G | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-RSL-VES-AR-AB-1039-H | Roofing and Glazing System | Skylight | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-RSL-VES-AR-AB-1041 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43582
1 | SD | SPML-KCM-RSL-VES-AR-AB-1041A | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43530
1 | SD | SPML-KCM-RSL-VES-AR-AB-1042 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43531
1 | SD | SPML-KCM-RSL-VES-AR-AB-1043 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43615
1 | SD | SPML-KCM-RSL-VES-AR-AB-1044 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44128
1 | SD | SPML-KCM-RSL-VES-AR-AB-1045 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43534
1 | SD | SPML-KCM-RSL-VES-AR-AB-1046 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43557
1 | SD | SPML-KCM-RSL-VES-AR-AB-1047 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-RSL-VES-AR-AB-1048 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43536
1 | SD | SPML-KCM-RSL-VES-AR-AB-1049 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43537
1 | SD | SPML-KCM-RSL-VES-AR-AB-1050 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43538
1 | SD | SPML-KCM-RSL-VES-AR-AB-1051 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43593
1 | SD | SPML-KCM-RSL-VES-AR-AB-1052 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43561
1 | SD | SPML-KCM-RSL-VES-AR-AB-1054 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-RSL-VES-AR-AB-1061 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43556
1 | SD | SPML-KCM-RSL-VES-AR-AB-1062 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43613
1 | SD | SPML-KCM-RSL-VES-AR-AB-1063 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43633
1 | SD | SPML-KCM-RSL-VES-AR-AB-1064 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-RSL-VES-AR-AB-1065 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-RSL—VES-AR-AB-1053 | Cladding | Wall Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-SSENT-AR-AB-001 | Space Protection System | Bollards | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-SSENT-AR-AB-001 | Space Protection System | Bollards | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-SSENT-AR-AB-002 | Space Protection System | Bollards | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43471
1 | SD | SPML-KCM-SSENT-AR-AB-002 | Space Protection System | Bollards | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-SSENT-AR-AB-003 | Space Protection System | Bollards | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-SSENT-AR-AB-003 | Space Protection System | Bollards | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-SSS-AR-AB-017 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-SSS-AR-AB-029 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-SSS-AR-AB-030 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43411
1 | SD | SPML-KCM-SSS-AR-AB-031 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-SSS-AR-AB-032 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-SSS-AR-AB-033 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-SSS-AR-AB-034 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-STR-AB-0005 | Walls | Block Work | Al Forsan Central Mall | Slab Floor | Architectural | NULL | Global Admin | B | 43758
1 | SD | SPML-KCM-STR-AB-001 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43281
1 | SD | SPML-KCM-STR-AB-001 | Foundation | Piling | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43103
1 | SD | SPML-KCM-STR-AB-002 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43103
1 | SD | SPML-KCM-STR-AB-0023 | Walls | Block Work | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43794
1 | SD | SPML-KCM-STR-AB-003 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43145
1 | SD | SPML-KCM-STR-AB-0031 | Walls | Block Work | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-STR-AB-004 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43150
1 | SD | SPML-KCM-STR-AB-005 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43200
1 | SD | SPML-KCM-STR-AB-006 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43169
1 | SD | SPML-KCM-STR-AB-0061 | Concrete Works | General Arrangement | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-STR-AB-0063 | Concrete Works | General Arrangement | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-STR-AB-0064 | Concrete Works | General Arrangement | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-STR-AB-0064a | Concrete Works | General Arrangement | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-STR-AB-0064a | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-STR-AB-007 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43177
1 | SD | SPML-KCM-STR-AB-008 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43177
1 | SD | SPML-KCM-STR-AB-009 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43188
1 | SD | SPML-KCM-STR-AB-010 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43177
1 | SD | SPML-KCM-STR-AB-011 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43188
1 | SD | SPML-KCM-STR-AB-012 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43177
1 | SD | SPML-KCM-STR-AB-013 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43188
1 | SD | SPML-KCM-STR-AB-014 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43216
1 | SD | SPML-KCM-STR-AB-015 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-STR-AB-016 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43216
1 | SD | SPML-KCM-STR-AB-017 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43232
1 | SD | SPML-KCM-STR-AB-018 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43255
1 | SD | SPML-KCM-STR-AB-019 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-STR-AB-020 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43258
1 | SD | SPML-KCM-STR-AB-021 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43278
1 | SD | SPML-KCM-STR-AB-023 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43258
1 | SD | SPML-KCM-STR-AB-024 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43278
1 | SD | SPML-KCM-STR-AB-025 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43261
1 | SD | SPML-KCM-STR-AB-026 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-STR-AB-027 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43274
1 | SD | SPML-KCM-STR-AB-028 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43288
1 | SD | SPML-KCM-STR-AB-029 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-STR-AB-031 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43288
1 | SD | SPML-KCM-STR-AB-032 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43299
1 | SD | SPML-KCM-STR-AB-033 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43302
1 | SD | SPML-KCM-STR-AB-034 | Foundation | Piling | Al Forsan Central Mall | Foundation | Structural | NULL | Global Admin | B | 43313
1 | SD | SPML-KCM-STR-AB-035 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-STR-AB-035.1 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43316
1 | SD | SPML-KCM-STR-AB-035.2 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43325
1 | SD | SPML-KCM-STR-AB-035.3 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43325
1 | SD | SPML-KCM-STR-AB-035.4 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43331
1 | SD | SPML-KCM-STR-AB-035.5 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43331
1 | SD | SPML-KCM-STR-AB-035.6 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43335
1 | SD | SPML-KCM-STR-AB-035.7 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-STR-AB-035.8 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-STR-AB-035.9 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-STR-AB-036 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-STR-AB-037 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-STR-AB-038 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-STR-AB-039 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM-STR-AB-040 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-STR-AB-041 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 44206
1 | SD | SPML-KCM-STR-AB-042 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-STR-AB-043 | Concrete Works | Column | Al Forsan Central Mall | Basement Floor | Structural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-STR-AB-044 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43374
1 | SD | SPML-KCM-STR-AB-044.1 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-STR-AB-044.2 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-STR-AB-044.3 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-STR-AB-044.4 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43381
1 | SD | SPML-KCM-STR-AB-044.5 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 44205
1 | SD | SPML-KCM-STR-AB-044.6 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43386
1 | SD | SPML-KCM-STR-AB-044.7 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43404
1 | SD | SPML-KCM-STR-AB-044.8 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43411
1 | SD | SPML-KCM-STR-AB-044.9 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-STR-AB-045 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-STR-AB-046 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43412
1 | SD | SPML-KCM-STR-AB-047 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43425
1 | SD | SPML-KCM-STR-AB-048 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43431
1 | SD | SPML-KCM-STR-AB-049 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43465
1 | SD | SPML-KCM-STR-AB-050 | Concrete Works | Column | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-STR-AB-051 | Concrete Works | Column | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43471
1 | SD | SPML-KCM-STR-AB-052 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43487
1 | SD | SPML-KCM-STR-AB-052.1 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-STR-AB-052.2 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-STR-AB-052.3 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-STR-AB-052.4 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-STR-AB-052.5 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-STR-AB-052.6 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-STR-AB-053 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-STR-AB-054 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-STR-AB-056 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-STR-AB-057 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-STR-AB-058 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-STR-AB-059 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-STR-AB-059.1 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-STR-AB-059.2 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-STR-AB-059.3 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-STR-AB-059.4 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-STR-AB-059.5 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-STR-AB-059.6 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-STR-AB-060 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-STR-AB—0062 | Concrete Works | General Arrangement | Al Forsan Central Mall | Ground Floor | Structural | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-VSF-STR-AB-001 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43561
1 | SD | SPML-KCM-VSF-STR-AB-002 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-VSF-STR-AB-003 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-VSF-STR-AB-004 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43561
1 | SD | SPML-KCM-VSF-STR-AB-005 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43586
1 | SD | SPML-KCM-VSF-STR-AB-006 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43604
1 | SD | SPML-KCM-VSF-STR-AB-008 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 44142
1 | SD | SPML-KCM-VSF-STR-AB-009 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-VSF-STR-AB-011 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43597
1 | SD | SPML-KCM-VSF-STR-AB-012 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-VSF-STR-AB-013 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43589
1 | SD | SPML-KCM-VSF-STR-AB-018 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43657
1 | SD | SPML-KCM-VSF-STR-AB-019 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-VSF-STR-AB-031 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43650
1 | SD | SPML-KCM-VSF-STR-AB-033 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43575
1 | SD | SPML-KCM-VSF-STR-AB-034 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43652
1 | SD | SPML-KCM-VSF-STR-AB-035 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43664
1 | SD | SPML-KCM-VSF-STR-AB-036 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43575
1 | SD | SPML-KCM-VSF-STR-AB-037 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43603
1 | SD | SPML-KCM-VSF-STR-AB-041 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43576
1 | SD | SPML-KCM-VSF-STR-AB-042 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43578
1 | SD | SPML-KCM-VSF-STR-AB-043 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43583
1 | SD | SPML-KCM-VSF-STR-AB-045 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43582
1 | SD | SPML-KCM-VSF-STR-AB-046 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43586
1 | SD | SPML-KCM-VSF-STR-AB-047 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43585
1 | SD | SPML-KCM-VSF-STR-AB-048 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43585
1 | SD | SPML-KCM-VSF-STR-AB-051 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43648
1 | SD | SPML-KCM-VSF-STR-AB-052 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43586
1 | SD | SPML-KCM-VSF-STR-AB-053 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43604
1 | SD | SPML-KCM-VSF-STR-AB-054 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 44157
1 | SD | SPML-KCM-VSF-STR-AB-056 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43587
1 | SD | SPML-KCM-VSF-STR-AB-071 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43566
1 | SD | SPML-KCM-VSF-STR-AB-081 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43720
1 | SD | SPML-KCM-VSF-STR-AB-082 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43750
1 | SD | SPML-KCM-VSF-STR-AB-083 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43754
1 | SD | SPML-KCM-VSF-STR-AB-084 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43764
1 | SD | SPML-KCM-VSF-STR-AB-085 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43590
1 | SD | SPML-KCM-VSF-STR-AB-086 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-VSF-STR-AB-087 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43614
1 | SD | SPML-KCM-VSF-STR-AB-088 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43629
1 | SD | SPML-KCM-VSF-STR-AB-088A | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43597
1 | SD | SPML-KCM-VSF-STR-AB-089 | Finishes | Aqua Panel | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43828
1 | SD | SPML-KCM-VSF-STR-AB-090 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43603
1 | SD | SPML-KCM-VSF-STR-AB-091 | Structural System | Steel Structure | Al Forsan Central Mall | Mezzanine | Structural | NULL | Global Admin | B | 43544
1 | SD | SPML-KCM-VSF-STR-AB-092 | Structural System | Steel Structure | Al Forsan Central Mall | Mezzanine | Structural | NULL | Global Admin | B | 43551
1 | SD | SPML-KCM-VSF-STR-AB-093 | Structural System | Steel Structure | Al Forsan Central Mall | Mezzanine | Structural | NULL | Global Admin | B | 43544
1 | SD | SPML-KCM-VSF-STR-AB-094 | Structural System | Steel Structure | Al Forsan Central Mall | Mezzanine | Structural | NULL | Global Admin | B | 43544
1 | SD | SPML-KCM-VSF-STR-AB-095 | Structural System | Steel Structure | Al Forsan Central Mall | Mezzanine | Structural | NULL | Global Admin | B | 43561
1 | SD | SPML-KCM-VSF-STR-AB-096 | Structural System | Steel Structure | Al Forsan Central Mall | Mezzanine | Structural | NULL | Global Admin | B | 43558
1 | SD | SPML-KCM-VSF-STR-AB-097 | Structural System | Steel Structure | Al Forsan Central Mall | Mezzanine | Structural | NULL | Global Admin | B | 43564
1 | SD | SPML-KCM-VSF-STR-AB-098 | Structural System | Steel Structure | Al Forsan Central Mall | Mezzanine | Structural | NULL | Global Admin | B | 43559
1 | SD | SPML-KCM-VSF-STR-AB-099 | Structural System | Steel Structure | Al Forsan Central Mall | Mezzanine | Structural | NULL | Global Admin | B | 43565
1 | SD | SPML-KCM-VSF-STR-AB—072 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43594
1 | SD | SPML-KCM-WD-AR-AB-0001 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43555
1 | SD | SPML-KCM-WD-AR-AB-0002 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-WD-AR-AB-0002A | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44177
1 | SD | SPML-KCM-WD-AR-AB-0003 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-WD-AR-AB-0003a | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-WD-AR-AB-0004 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-WD-AR-AB-0006 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43607
1 | SD | SPML-KCM-WD-AR-AB-0007 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM-WD-AR-AB-0008 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-WD-AR-AB-0009 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-WD-AR-AB-000S | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43481
1 | SD | SPML-KCM-WD-AR-AB-0010 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43491
1 | SD | SPML-KCM-WD-AR-AB-0011 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43492
1 | SD | SPML-KCM-WD-AR-AB-0012 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-WD-AR-AB-0013 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43493
1 | SD | SPML-KCM-WD-AR-AB-0014 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43499
1 | SD | SPML-KCM-WD-AR-AB-0014A | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43500
1 | SD | SPML-KCM-WD-AR-AB-0014B | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43505
1 | SD | SPML-KCM-WD-AR-AB-0014C | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-WD-AR-AB-0015 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-WD-AR-AB-0016 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43516
1 | SD | SPML-KCM-WD-AR-AB-0017 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43571
1 | SD | SPML-KCM-WD-AR-AB-0018 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43579
1 | SD | SPML-KCM-WD-AR-AB-0019 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43599
1 | SD | SPML-KCM-WD-AR-AB-0020 | Doors & Windows | Wooden Door | Al Forsan Central Mall | Basement Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-WD-AR-AB-0021 | Doors & Windows | Wooden Door | Al Forsan Central Mall | Ground Floor | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-WD-AR-AB-0022 | Doors & Windows | Wooden Door | Al Forsan Central Mall | First Floor | Architectural | NULL | Global Admin | B | 43388
1 | SD | SPML-KCM-WD-AR-AB-0023 | Doors & Windows | Wooden Door | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43358
1 | SD | SPML-KCM-WD-AR-AB-0024 | Doors & Windows | Wooden Door | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43377
1 | SD | SPML-KCM-WD-AR-AB-0025 | Doors & Windows | Wooden Door | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44202
1 | SD | SPML-KCM—FRZ-STR-AB-1232 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | First Floor | Structural | NULL | Global Admin | B | 43523
1 | SD | SPML-KCM—OTIS-STR-AB-002 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43675
1 | SD | SPML-KCM—OTIS—STR-AB-016 | Lift System | Escalator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43711
1 | SD | SPML-KCM—STR-AB-055 | Concrete Works | Column | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 44138
1 | SD | SPML-KCM—VSF-STR-AB-032 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43572
1 | SD | SPML-KCM—VSF—STR-AB-010 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43585
1 | SD | SPML—KCM-ASC-AR-AB-003 | Floor | Floor Screed | Al Forsan Central Mall | Roof Floor | Architectural | NULL | Global Admin | B | 43662
1 | SD | SPML—KCM-OTIS-STR-AB-019 | Lift System | Elevator | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43722
1 | SD | SPML—KCM-OTIS-STR-AB-023 | Lift System | Elevator | Al Forsan Central Mall | Basement Floor | Mechanical | NULL | Global Admin | B | 43731
1 | SD | SPML—KCM-VSF-STR-AB-007 | Structural System | Steel Structure | Al Forsan Central Mall | Roof Floor | Structural | NULL | Global Admin | B | 43618
2 | MS | SPML-KCM-CA-MAS-0009 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43103
2 | MS | SPML-KCM-CA-MAS-00310 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43103
2 | MS | SPML-KCM-CA-MAS-0034A | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43200
2 | MS | SPML-KCM-CA-MAS-0044 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43169
2 | MS | SPML-KCM-CA-MAS-0047 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43177
2 | MS | SPML-KCM-CA-MAS-0048 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43188
2 | MS | SPML-KCM-CA-MAS-0049 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43188
2 | MS | SPML-KCM-CA-MAS-0050 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43188
2 | MS | SPML-KCM-CA-MAS-0070 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-CA-MAS-0073 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-CA-MAS-0097 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43325
2 | MS | SPML-KCM-CA-MAS-0098 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43278
2 | MS | SPML-KCM-CA-MAS-0099 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-CA-MAS-0105 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-CA-MAS-0112 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43281
2 | MS | SPML-KCM-CA-MAS-0122 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43288
2 | MS | SPML-KCM-CA-MAS-0136 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-CA-MAS-0149 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43316
2 | MS | SPML-KCM-CA-MAS-0162 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43325
2 | MS | SPML-KCM-CA-MAS-0163 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43325
2 | MS | SPML-KCM-CA-MAS-0166 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43331
2 | MS | SPML-KCM-CA-MAS-0167 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43331
2 | MS | SPML-KCM-CA-MAS-0168 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43335
2 | MS | SPML-KCM-CA-MAS-0198 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43388
2 | MS | SPML-KCM-CA-MAS-0199 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43388
2 | MS | SPML-KCM-CA-MAS-0200 | Concrete Works | Post Tension Slab | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44202
2 | MS | SPML-KCM-CA-MAS-0201 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-CA-MAS-0202 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43358
2 | MS | SPML-KCM-CA-MAS-0204 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43358
2 | MS | SPML-KCM-CA-MAS-0222 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43374
2 | MS | SPML-KCM-CA-MAS-0224 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43377
2 | MS | SPML-KCM-CA-MAS-0225 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43377
2 | MS | SPML-KCM-CA-MAS-0226 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43377
2 | MS | SPML-KCM-CA-MAS-0229 | Expansion | Expansion Joint Sealant | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44205
2 | MS | SPML-KCM-CA-MAS-0239 | Concrete Works | Post Tension Slab | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43386
2 | MS | SPML-KCM-CA-MAS-0271 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43404
2 | MS | SPML-KCM-CA-MAS-0279 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43411
2 | MS | SPML-KCM-CA-MAS-0281 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43412
2 | MS | SPML-KCM-CA-MAS-0282 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43412
2 | MS | SPML-KCM-CA-MAS-0283 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43412
2 | MS | SPML-KCM-CA-MAS-0306 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43425
2 | MS | SPML-KCM-CA-MAS-0312 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43431
2 | MS | SPML-KCM-CA-MAS-0387 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43565
2 | MS | SPML-KCM-CA-MAS-0393 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
2 | MS | SPML-KCM-CA-MAS-0411 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43481
2 | MS | SPML-KCM-CA-MAS-0412 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43500
2 | MS | SPML-KCM-CA-MAS-0413 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
2 | MS | SPML-KCM-CA-MAS-0414 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43481
2 | MS | SPML-KCM-CA-MAS-0423 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43491
2 | MS | SPML-KCM-CA-MAS-0424 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43491
2 | MS | SPML-KCM-CA-MAS-0435 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43492
2 | MS | SPML-KCM-CA-MAS-0437 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43493
2 | MS | SPML-KCM-CA-MAS-0438 | Finishes | Epoxy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43493
2 | MS | SPML-KCM-CA-MAS-0456 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43499
2 | MS | SPML-KCM-CA-MAS-0458 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43500
2 | MS | SPML-KCM-CA-MAS-0466 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43505
2 | MS | SPML-KCM-CA-MAS-0482 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43516
2 | MS | SPML-KCM-CA-MAS-0483 | Finishes | Epoxy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43516
2 | MS | SPML-KCM-CA-MAS-0484 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43599
2 | MS | SPML-KCM-CA-MAS-0485 | Finishes | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43545
2 | MS | SPML-KCM-CA-MAS-0487 | Loading Bay Equipment System | Overhead Door | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43517
2 | MS | SPML-KCM-CA-MAS-0488 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43767
2 | MS | SPML-KCM-CA-MAS-0489 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43517
2 | MS | SPML-KCM-CA-MAS-0491 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43551
2 | MS | SPML-KCM-CA-MAS-0496 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43544
2 | MS | SPML-KCM-CA-MAS-0500 | Waste Management | Garbage Compactor | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43521
2 | MS | SPML-KCM-CA-MAS-0501 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43572
2 | MS | SPML-KCM-CA-MAS-0502 | Finishes | Vanity Countertop | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43522
2 | MS | SPML-KCM-CA-MAS-0503 | Finishes | Toilet Cubicle | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43522
2 | MS | SPML-KCM-CA-MAS-0512 | FF&E | Wooden Benches | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43614
2 | MS | SPML-KCM-CA-MAS-0515 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43844
2 | MS | SPML-KCM-CA-MAS-0516 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43523
2 | MS | SPML-KCM-CA-MAS-0518 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-CA-MAS-0531 | LandScaping | Planting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43571
2 | MS | SPML-KCM-CA-MAS-0535 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43536
2 | MS | SPML-KCM-CA-MAS-0542 | Finishes | Canopy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43537
2 | MS | SPML-KCM-CA-MAS-0545 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
2 | MS | SPML-KCM-CA-MAS-0556 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43544
2 | MS | SPML-KCM-CA-MAS-0589 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43564
2 | MS | SPML-KCM-CA-MAS-0590 | Finishes | Canopy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43559
2 | MS | SPML-KCM-CA-MAS-0591 | Sealant | Expansion Joint Sealant | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43597
2 | MS | SPML-KCM-CA-MAS-0594 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
2 | MS | SPML-KCM-CA-MAS-0595 | Waste Management | Garbage Compactor | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44142
2 | MS | SPML-KCM-CA-MAS-0605 | Walls | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43597
2 | MS | SPML-KCM-CA-MAS-0607 | GRP System | GRP Lining | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43657
2 | MS | SPML-KCM-CA-MAS-0611 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43565
2 | MS | SPML-KCM-CA-MAS-0613 | Finishes | Mirror | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43650
2 | MS | SPML-KCM-CA-MAS-0619 | FF&E | `Shoe Rack | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43572
2 | MS | SPML-KCM-CA-MAS-0623 | Cladding | Facade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43664
2 | MS | SPML-KCM-CA-MAS-0624 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43603
2 | MS | SPML-KCM-CA-MAS-0625 | Cladding | Facade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43575
2 | MS | SPML-KCM-CA-MAS-0633 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43576
2 | MS | SPML-KCM-CA-MAS-0648 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44157
2 | MS | SPML-KCM-CA-MAS-0653 | Finishes | Toilet Cubicle | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43764
2 | MS | SPML-KCM-CA-MAS-0657 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43629
2 | MS | SPML-KCM-CA-MAS-0660 | Structural System | Tranformer Channel | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43828
2 | MS | SPML-KCM-CA-MAS-0670 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43603
2 | MS | SPML-KCM-CA-MAS-0674 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44144
2 | MS | SPML-KCM-CA-MAS-0676 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43605
2 | MS | SPML-KCM-CA-MAS-0677 | Finishes | Epoxy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43605
2 | MS | SPML-KCM-CA-MAS-0682 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43702
2 | MS | SPML-KCM-CA-MAS-0686 | Cladding | Facade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43710
2 | MS | SPML-KCM-CA-MAS-0694 | Doors & Windows | Aluminium Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43629
2 | MS | SPML-KCM-CA-MAS-0702 | Finishes | Curtain Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43624
2 | MS | SPML-KCM-CA-MAS-0703 | Doors & Windows | Glass Door | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43748
2 | MS | SPML-KCM-CA-MAS-0708 | Finishes | Curtain Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44174
2 | MS | SPML-KCM-CA-MAS-0709 | Finishes | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43626
2 | MS | SPML-KCM-CA-MAS-0711 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43660
2 | MS | SPML-KCM-CA-MAS-0717 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-CA-MAS-0719 | Foundation | AHU Foundation | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43633
2 | MS | SPML-KCM-CA-MAS-0728 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43640
2 | MS | SPML-KCM-CA-MAS-0731 | Finishes | Baffle Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43872
2 | MS | SPML-KCM-CA-MAS-0732 | Walls | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43641
2 | MS | SPML-KCM-CA-MAS-0733 | Finishes | Armour Coat | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43697
2 | MS | SPML-KCM-CA-MAS-0735 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43717
2 | MS | SPML-KCM-CA-MAS-0736 | Cladding | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43649
2 | MS | SPML-KCM-CA-MAS-0737 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43642
2 | MS | SPML-KCM-CA-MAS-0738 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43768
2 | MS | SPML-KCM-CA-MAS-0739 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43768
2 | MS | SPML-KCM-CA-MAS-0746 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43652
2 | MS | SPML-KCM-CA-MAS-0747 | Finishes | Toilet Cubicle | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43652
2 | MS | SPML-KCM-CA-MAS-0748 | Cladding | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43695
2 | MS | SPML-KCM-CA-MAS-0750 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43720
2 | MS | SPML-KCM-CA-MAS-0751 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43702
2 | MS | SPML-KCM-CA-MAS-0755 | Loading Bay Equipment System | Overhead Door | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44157
2 | MS | SPML-KCM-CA-MAS-0756 | Finishes | Wheel Stopper | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43655
2 | MS | SPML-KCM-CA-MAS-0757 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44177
2 | MS | SPML-KCM-CA-MAS-0760 | Finishes | Louvre | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
2 | MS | SPML-KCM-CA-MAS-0761 | Foundation | AHU Foundation | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43659
2 | MS | SPML-KCM-CA-MAS-0763 | Cladding | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43657
2 | MS | SPML-KCM-CA-MAS-0764 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43661
2 | MS | SPML-KCM-CA-MAS-0767 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43662
2 | MS | SPML-KCM-CA-MAS-0768 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43662
2 | MS | SPML-KCM-CA-MAS-0769 | Sealant | Fire Sealant | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43662
2 | MS | SPML-KCM-CA-MAS-0771 | Sealant | Fire Sealant | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43662
2 | MS | SPML-KCM-CA-MAS-0773 | Finishes | Raised Floor | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43760
2 | MS | SPML-KCM-CA-MAS-0775 | Finishes | Aluminium Extrusion | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43729
2 | MS | SPML-KCM-CA-MAS-0777 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43704
2 | MS | SPML-KCM-CA-MAS-0779 | Cladding | Facade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43698
2 | MS | SPML-KCM-CA-MAS-0783 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43712
2 | MS | SPML-KCM-CA-MAS-0785 | Cladding | Facade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43874
2 | MS | SPML-KCM-CA-MAS-0789 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43677
2 | MS | SPML-KCM-CA-MAS-0796 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43754
2 | MS | SPML-KCM-CA-MAS-0816 | LandScaping | Irrigation System | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44128
2 | MS | SPML-KCM-CA-MAS-0820 | Doors & Windows | Sliding Door | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44171
2 | MS | SPML-KCM-CA-MAS-0822 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43719
2 | MS | SPML-KCM-CA-MAS-0823 | Cladding | Facade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43704
2 | MS | SPML-KCM-CA-MAS-0827 | FF&E | Wooden Benches | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43709
2 | MS | SPML-KCM-CA-MAS-0830 | Drainage System | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43711
2 | MS | SPML-KCM-CA-MAS-0831 | Finishes | Epoxy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43712
2 | MS | SPML-KCM-CA-MAS-0833 | Finishes | Floor | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43715
2 | MS | SPML-KCM-CA-MAS-0841 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43722
2 | MS | SPML-KCM-CA-MAS-0844 | GRP System | GRP System | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43722
2 | MS | SPML-KCM-CA-MAS-0850 | Finishes | Aqua Panel | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43764
2 | MS | SPML-KCM-CA-MAS-0855 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43731
2 | MS | SPML-KCM-CA-MAS-0860 | Finishes | Mirror | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43739
2 | MS | SPML-KCM-CA-MAS-0864 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43740
2 | MS | SPML-KCM-CA-MAS-0867 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43744
2 | MS | SPML-KCM-CA-MAS-0868 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43781
2 | MS | SPML-KCM-CA-MAS-0869 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43781
2 | MS | SPML-KCM-CA-MAS-0878 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43751
2 | MS | SPML-KCM-CA-MAS-0886 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43755
2 | MS | SPML-KCM-CA-MAS-0891 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43794
2 | MS | SPML-KCM-CA-MAS-0898 | Roofing and Glazing System | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44173
2 | MS | SPML-KCM-CA-MAS-0905 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43768
2 | MS | SPML-KCM-CA-MAS-0917 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44187
2 | MS | SPML-KCM-CA-MAS-0928 | Cladding | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44174
2 | MS | SPML-KCM-CA-MAS-0931 | Finishes | Wheel Stopper | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43793
2 | MS | SPML-KCM-CA-MAS-0934 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43799
2 | MS | SPML-KCM-CA-MAS-0948 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43816
2 | MS | SPML-KCM-CA-MAS-0975 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43853
2 | MS | SPML-KCM-CA-MAS-0982 | Sealant | Fire Sealant | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43872
2 | MS | SPML-KCM-CA-MAS-0988 | Finishes | Canopy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
2 | MS | SPML-KCM-CA-MAS-0998 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43904
2 | MS | SPML-KCM-CA-MAS-1020 | Concrete Works | Shuttering | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43927
2 | MS | SPML-KCM-CA-MAS-1047 | Finishes | Stickers | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44234
2 | MS | SPML-KCM-CA-MAS-1048 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44009
2 | MS | SPML-KCM-CA-MAS-1060 | LandScaping | Planting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44201
2 | MS | SPML-KCM-CA-MAS-1069 | FF&E | Litter bin | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44055
2 | MS | SPML-KCM-CA-MAS-1104 | Finishes | PVC Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44095
2 | MS | SPML-KCM-CA-MAS-1105 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44097
2 | MS | SPML-KCM-CA-MAS-1111 | Pole | Flag Pole | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44105
2 | MS | SPML-KCM-CA-MAS-1121 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44124
2 | MS | SPML-KCM-CA-MAS-1144 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44175
2 | MS | SPML-KCM-CA-MAS-1156 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
2 | MS | SPML-KCM-CA-MAS-1167 | Walls | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44207
2 | MS | SPML-KCM-CA-MAS-1168 | Walls | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44207
2 | MS | SPML-KCM-CA-MAS-1171 | Walls | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44220
2 | MS | SPML-KCM-ID-MAS-0517 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43557
2 | MS | SPML-KCM-ID-MAS-0519 | Finishes | Stone Carpet | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43579
2 | MS | SPML-KCM-ID-MAS-0520 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43555
2 | MS | SPML-KCM-ID-MAS-0521 | Finishes | Urinals | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43582
2 | MS | SPML-KCM-ID-MAS-0522 | LandScaping | Irrigation System | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44128
2 | MS | SPML-KCM-ID-MAS-0553 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
2 | MS | SPML-KCM-ID-MAS-0554 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43551
2 | MS | SPML-KCM-ID-MAS-0561 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43561
2 | MS | SPML-KCM-ID-MAS-0636 | Finishes | Marble | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43578
2 | MS | SPML-KCM-ID-MAS-0637 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43583
2 | MS | SPML-KCM-ID-MAS-0640 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43582
2 | MS | SPML-KCM-ID-MAS-0642 | Paving System | Interlock | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43586
2 | MS | SPML-KCM-ID-MAS-0645 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43585
2 | MS | SPML-KCM-ID-MAS-0646 | Finishes | Armour Coat | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43648
2 | MS | SPML-KCM-ID-MAS-0655 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43590
2 | MS | SPML-KCM-ID-MAS-0759 | Balustrade | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43717
2 | MS | SPML-KCM-MEP-MAS-0283 | ELV | Parking Guidance | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43641
2 | MS | SPML-KCM-MEP-MAS-EL-0007 | Power Distribution | LV System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43633
2 | MS | SPML-KCM-MEP-MAS-EL-0008 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43736
2 | MS | SPML-KCM-MEP-MAS-EL-0009 | Earthing & Lightning Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43571
2 | MS | SPML-KCM-MEP-MAS-EL-0014 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43655
2 | MS | SPML-KCM-MEP-MAS-EL-0015 | Power Distribution | UPS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44202
2 | MS | SPML-KCM-MEP-MAS-EL-0016 | Power Distribution | Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43572
2 | MS | SPML-KCM-MEP-MAS-EL-0019 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43599
2 | MS | SPML-KCM-MEP-MAS-EL-0022 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43103
2 | MS | SPML-KCM-MEP-MAS-EL-0024 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43169
2 | MS | SPML-KCM-MEP-MAS-EL-0025 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43177
2 | MS | SPML-KCM-MEP-MAS-EL-0028 | Power Distribution | Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43652
2 | MS | SPML-KCM-MEP-MAS-EL-0031 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44138
2 | MS | SPML-KCM-MEP-MAS-EL-0037 | HV System | RMU | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43695
2 | MS | SPML-KCM-MEP-MAS-EL-0038 | HV System | RMU | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43720
2 | MS | SPML-KCM-MEP-MAS-EL-0041 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43177
2 | MS | SPML-KCM-MEP-MAS-EL-0043 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43177
2 | MS | SPML-KCM-MEP-MAS-EL-0048 | Power Distribution | LV System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43627
2 | MS | SPML-KCM-MEP-MAS-EL-0052 | HV System | Transformer | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43331
2 | MS | SPML-KCM-MEP-MAS-EL-0067 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43216
2 | MS | SPML-KCM-MEP-MAS-EL-0071 | ELV | SCADA | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43702
2 | MS | SPML-KCM-MEP-MAS-EL-0074 | Emergency Lighting | CBS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43576
2 | MS | SPML-KCM-MEP-MAS-EL-0085 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43652
2 | MS | SPML-KCM-MEP-MAS-EL-0092 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43586
2 | MS | SPML-KCM-MEP-MAS-EL-0096 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44142
2 | MS | SPML-KCM-MEP-MAS-EL-0100 | Power Distribution | LV System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43586
2 | MS | SPML-KCM-MEP-MAS-EL-0118 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-MEP-MAS-EL-0123 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43575
2 | MS | SPML-KCM-MEP-MAS-EL-0124 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43278
2 | MS | SPML-KCM-MEP-MAS-EL-0133 | Lift System | Elevator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43557
2 | MS | SPML-KCM-MEP-MAS-EL-0142 | Power Distribution | LV System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-MEP-MAS-EL-0157 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43325
2 | MS | SPML-KCM-MEP-MAS-EL-0167 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43754
2 | MS | SPML-KCM-MEP-MAS-EL-0173 | ELV | Access Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43103
2 | MS | SPML-KCM-MEP-MAS-EL-0188 | Power Distribution | Capacitor Banks | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43575
2 | MS | SPML-KCM-MEP-MAS-EL-0192 | ELV | Disabled Toilet Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43377
2 | MS | SPML-KCM-MEP-MAS-EL-0194 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43748
2 | MS | SPML-KCM-MEP-MAS-EL-0201 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43278
2 | MS | SPML-KCM-MEP-MAS-EL-0205 | Power Distribution | Busbar | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43566
2 | MS | SPML-KCM-MEP-MAS-EL-0233 | Lighting | Light Fixtures | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43702
2 | MS | SPML-KCM-MEP-MAS-EL-0236 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43589
2 | MS | SPML-KCM-MEP-MAS-EL-0246 | Lift System | Escalator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43537
2 | MS | SPML-KCM-MEP-MAS-EL-0266 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43614
2 | MS | SPML-KCM-MEP-MAS-EL-0279 | Lighting | Light Fixtures | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43680
2 | MS | SPML-KCM-MEP-MAS-EL-0289 | ELV | CPMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44202
2 | MS | SPML-KCM-MEP-MAS-EL-0291 | Lighting | Light Fixtures | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43669
2 | MS | SPML-KCM-MEP-MAS-EL-0321 | HV System | Transformer | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43335
2 | MS | SPML-KCM-MEP-MAS-EL-0331 | Earthing & Lightning Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43768
2 | MS | SPML-KCM-MEP-MAS-EL-0379 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43767
2 | MS | SPML-KCM-MEP-MAS-FFG-0128 | Power Distribution | Panel | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43652
2 | MS | SPML-KCM-MEP-MAS-FFG-0129 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43274
2 | MS | SPML-KCM-MEP-MAS-FFG-0130 | Fire Fighting System | Clean Agent System | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43288
2 | MS | SPML-KCM-MEP-MAS-FFG-0131 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43650
2 | MS | SPML-KCM-MEP-MAS-FFG-0132 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43302
2 | MS | SPML-KCM-MEP-MAS-FFG-0168 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43589
2 | MS | SPML-KCM-MEP-MAS-FFG-0189 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43642
2 | MS | SPML-KCM-MEP-MAS-FFG-0190 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43559
2 | MS | SPML-KCM-MEP-MAS-FFG-0191 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43641
2 | MS | SPML-KCM-MEP-MAS-FFG-0218 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43653
2 | MS | SPML-KCM-MEP-MAS-FFG-0299 | Fire Fighting System | Clean Agent System | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43299
2 | MS | SPML-KCM-MEP-MAS-FFG-0314 | Fire Fighting System | Clean Agent System | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43316
2 | MS | SPML-KCM-MEP-MAS-FFG-0315 | Fire Fighting System | Clean Agent System | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43331
2 | MS | SPML-KCM-MEP-MAS-HVAC-0036 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43551
2 | MS | SPML-KCM-MEP-MAS-HVAC-0042 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43603
2 | MS | SPML-KCM-MEP-MAS-HVAC-0051 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43545
2 | MS | SPML-KCM-MEP-MAS-HVAC-0068 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43572
2 | MS | SPML-KCM-MEP-MAS-HVAC-0069 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43523
2 | MS | SPML-KCM-MEP-MAS-HVAC-0073 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44144
2 | MS | SPML-KCM-MEP-MAS-HVAC-0084 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43565
2 | MS | SPML-KCM-MEP-MAS-HVAC-0088 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43614
2 | MS | SPML-KCM-MEP-MAS-HVAC-0089 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43605
2 | MS | SPML-KCM-MEP-MAS-HVAC-0090 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43669
2 | MS | SPML-KCM-MEP-MAS-HVAC-0094 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43624
2 | MS | SPML-KCM-MEP-MAS-HVAC-0097 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43188
2 | MS | SPML-KCM-MEP-MAS-HVAC-0098 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43216
2 | MS | SPML-KCM-MEP-MAS-HVAC-0101 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43626
2 | MS | SPML-KCM-MEP-MAS-HVAC-0102 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43258
2 | MS | SPML-KCM-MEP-MAS-HVAC-0103 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43633
2 | MS | SPML-KCM-MEP-MAS-HVAC-0105 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43288
2 | MS | SPML-KCM-MEP-MAS-HVAC-0108 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43697
2 | MS | SPML-KCM-MEP-MAS-HVAC-0109 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43842
2 | MS | SPML-KCM-MEP-MAS-HVAC-0110 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43302
2 | MS | SPML-KCM-MEP-MAS-HVAC-0111 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43331
2 | MS | SPML-KCM-MEP-MAS-HVAC-0112 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43388
2 | MS | SPML-KCM-MEP-MAS-HVAC-0113 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43358
2 | MS | SPML-KCM-MEP-MAS-HVAC-0114 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43358
2 | MS | SPML-KCM-MEP-MAS-HVAC-0115 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 44206
2 | MS | SPML-KCM-MEP-MAS-HVAC-0116 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43377
2 | MS | SPML-KCM-MEP-MAS-HVAC-0117 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43381
2 | MS | SPML-KCM-MEP-MAS-HVAC-0120 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43386
2 | MS | SPML-KCM-MEP-MAS-HVAC-0122 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43412
2 | MS | SPML-KCM-MEP-MAS-HVAC-0126 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43425
2 | MS | SPML-KCM-MEP-MAS-HVAC-0127 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43565
2 | MS | SPML-KCM-MEP-MAS-HVAC-0135 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43487
2 | MS | SPML-KCM-MEP-MAS-HVAC-0136 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44138
2 | MS | SPML-KCM-MEP-MAS-HVAC-0137 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43481
2 | MS | SPML-KCM-MEP-MAS-HVAC-0138 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44138
2 | MS | SPML-KCM-MEP-MAS-HVAC-0141 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43642
2 | MS | SPML-KCM-MEP-MAS-HVAC-0144 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43493
2 | MS | SPML-KCM-MEP-MAS-HVAC-0145 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43652
2 | MS | SPML-KCM-MEP-MAS-HVAC-0155 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43505
2 | MS | SPML-KCM-MEP-MAS-HVAC-0158 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43516
2 | MS | SPML-KCM-MEP-MAS-HVAC-0159 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43579
2 | MS | SPML-KCM-MEP-MAS-HVAC-0163 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43516
2 | MS | SPML-KCM-MEP-MAS-HVAC-0164 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43534
2 | MS | SPML-KCM-MEP-MAS-HVAC-0165 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43517
2 | MS | SPML-KCM-MEP-MAS-HVAC-0166 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43523
2 | MS | SPML-KCM-MEP-MAS-HVAC-0171 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43519
2 | MS | SPML-KCM-MEP-MAS-HVAC-0172 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43519
2 | MS | SPML-KCM-MEP-MAS-HVAC-0174 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43521
2 | MS | SPML-KCM-MEP-MAS-HVAC-0175 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43522
2 | MS | SPML-KCM-MEP-MAS-HVAC-0176 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43523
2 | MS | SPML-KCM-MEP-MAS-HVAC-0177 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43587
2 | MS | SPML-KCM-MEP-MAS-HVAC-0184 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43842
2 | MS | SPML-KCM-MEP-MAS-HVAC-0185 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43653
2 | MS | SPML-KCM-MEP-MAS-HVAC-0198 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43529
2 | MS | SPML-KCM-MEP-MAS-HVAC-0200 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43638
2 | MS | SPML-KCM-MEP-MAS-HVAC-0203 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44157
2 | MS | SPML-KCM-MEP-MAS-HVAC-0204 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43655
2 | MS | SPML-KCM-MEP-MAS-HVAC-0213 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43177
2 | MS | SPML-KCM-MEP-MAS-HVAC-0214 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43216
2 | MS | SPML-KCM-MEP-MAS-HVAC-0217 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43585
2 | MS | SPML-KCM-MEP-MAS-HVAC-0226 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43571
2 | MS | SPML-KCM-MEP-MAS-HVAC-0241 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44138
2 | MS | SPML-KCM-MEP-MAS-HVAC-0253 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-MEP-MAS-HVAC-0257 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43278
2 | MS | SPML-KCM-MEP-MAS-HVAC-0264 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43278
2 | MS | SPML-KCM-MEP-MAS-HVAC-0270 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43564
2 | MS | SPML-KCM-MEP-MAS-HVAC-0272 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43274
2 | MS | SPML-KCM-MEP-MAS-HVAC-0280 | HVAC | Leak Detection | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44137
2 | MS | SPML-KCM-MEP-MAS-HVAC-0294 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43561
2 | MS | SPML-KCM-MEP-MAS-HVAC-0317 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43586
2 | MS | SPML-KCM-MEP-MAS-HVAC-0326 | Fire Fighting System | Deluge System | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44206
2 | MS | SPML-KCM-MEP-MAS-HVAC-0351 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43517
2 | MS | SPML-KCM-MEP-MAS-HVAC-0352 | EV | EV Charger | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43561
2 | MS | SPML-KCM-MEP-MAS-PL-0004 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43358
2 | MS | SPML-KCM-MEP-MAS-PL-0005 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43386
2 | MS | SPML-KCM-MEP-MAS-PL-0006 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43412
2 | MS | SPML-KCM-MEP-MAS-PL-0020 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43425
2 | MS | SPML-KCM-MEP-MAS-PL-0023 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43431
2 | MS | SPML-KCM-MEP-MAS-PL-0030 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43374
2 | MS | SPML-KCM-MEP-MAS-PL-0033 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43377
2 | MS | SPML-KCM-MEP-MAS-PL-0034 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43565
2 | MS | SPML-KCM-MEP-MAS-PL-0039 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43386
2 | MS | SPML-KCM-MEP-MAS-PL-0047 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43487
2 | MS | SPML-KCM-MEP-MAS-PL-0049 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44138
2 | MS | SPML-KCM-MEP-MAS-PL-0057 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43481
2 | MS | SPML-KCM-MEP-MAS-PL-0070 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43177
2 | MS | SPML-KCM-MEP-MAS-PL-0072 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43411
2 | MS | SPML-KCM-MEP-MAS-PL-0077 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43412
2 | MS | SPML-KCM-MEP-MAS-PL-0079 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43491
2 | MS | SPML-KCM-MEP-MAS-PL-0080 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43492
2 | MS | SPML-KCM-MEP-MAS-PL-0081 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43471
2 | MS | SPML-KCM-MEP-MAS-PL-0082 | HVAC | Condensate Drain | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43388
2 | MS | SPML-KCM-MEP-MAS-PL-0083 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
2 | MS | SPML-KCM-MEP-MAS-PL-0087 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43493
2 | MS | SPML-KCM-MEP-MAS-PL-0093 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43481
2 | MS | SPML-KCM-MEP-MAS-PL-0107 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43587
2 | MS | SPML-KCM-MEP-MAS-PL-0119 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43481
2 | MS | SPML-KCM-MEP-MAS-PL-0146 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43493
2 | MS | SPML-KCM-MEP-MAS-PL-0147 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43516
2 | MS | SPML-KCM-MEP-MAS-PL-0161 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43571
2 | MS | SPML-KCM-MEP-MAS-PL-0181 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43523
2 | MS | SPML-KCM-MEP-MAS-PL-0199 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43499
2 | MS | SPML-KCM-MEP-MAS-PL-0206 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43579
2 | MS | SPML-KCM-MEP-MAS-PL-0216 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43516
2 | MS | SPML-KCM-MEP-MAS-PL-0222 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43534
2 | MS | SPML-KCM-MEP-MAS-PL-0228 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43517
2 | MS | SPML-KCM-MEP-MAS-PL-0238 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43538
2 | MS | SPML-KCM-MEP-MAS-PL-0248 | HVAC | Condensate Drain | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43388
2 | MS | SPML-KCM-MEP-MAS-PL-0287 | Fuel System | Fuel Oil System | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43652
2 | MS | SPML-KCM-MEP-MAS-PL-0293 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43565
2 | MS | SPML-KCM-MEP-MAS-PL-0296 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
2 | MS | SPML-KCM-MEP-MAS-PL-0367 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43545
2 | MS | SPML-KCM-MEP-MAS-PL-0368 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43517
2 | MS | TS-0028 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43145
2 | MS | TS-0034 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43150
2 | MS | VES-KCM-BALUSTRADE-MAS-001 | Balustrade | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43881
3 | MIR | SPML-KCM-MEP-MIR-AC-465 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43684
3 | MIR | SPML-KCM-MEP-MIR-AC-728 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43991
3 | MIR | SPML-KCM-MEP-MIR-EL-0002 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43324
3 | MIR | SPML-KCM-MEP-MIR-EL-0002 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43316
3 | MIR | SPML-KCM-MEP-MIR-EL-0007 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43325
3 | MIR | SPML-KCM-MEP-MIR-EL-0009 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43337
3 | MIR | SPML-KCM-MEP-MIR-EL-0014 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43363
3 | MIR | SPML-KCM-MEP-MIR-EL-0015 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43368
3 | MIR | SPML-KCM-MEP-MIR-EL-0016 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43368
3 | MIR | SPML-KCM-MEP-MIR-EL-0017 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43368
3 | MIR | SPML-KCM-MEP-MIR-EL-0022 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43380
3 | MIR | SPML-KCM-MEP-MIR-EL-0028 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43394
3 | MIR | SPML-KCM-MEP-MIR-EL-0029 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43395
3 | MIR | SPML-KCM-MEP-MIR-EL-0030 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43395
3 | MIR | SPML-KCM-MEP-MIR-EL-0031 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43395
3 | MIR | SPML-KCM-MEP-MIR-EL-0041 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43428
3 | MIR | SPML-KCM-MEP-MIR-EL-0042 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43431
3 | MIR | SPML-KCM-MEP-MIR-EL-0043 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43431
3 | MIR | SPML-KCM-MEP-MIR-EL-0046 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43443
3 | MIR | SPML-KCM-MEP-MIR-EL-0048 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43452
3 | MIR | SPML-KCM-MEP-MIR-EL-0054 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43468
3 | MIR | SPML-KCM-MEP-MIR-EL-0057 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-0057 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43478
3 | MIR | SPML-KCM-MEP-MIR-EL-0058 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43480
3 | MIR | SPML-KCM-MEP-MIR-EL-0059 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43480
3 | MIR | SPML-KCM-MEP-MIR-EL-0059 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-0068 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43487
3 | MIR | SPML-KCM-MEP-MIR-EL-0076 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43493
3 | MIR | SPML-KCM-MEP-MIR-EL-0077 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43493
3 | MIR | SPML-KCM-MEP-MIR-EL-0079 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43498
3 | MIR | SPML-KCM-MEP-MIR-EL-0080 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43500
3 | MIR | SPML-KCM-MEP-MIR-EL-0081 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43500
3 | MIR | SPML-KCM-MEP-MIR-EL-0082 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43505
3 | MIR | SPML-KCM-MEP-MIR-EL-0083 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43505
3 | MIR | SPML-KCM-MEP-MIR-EL-0096 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43512
3 | MIR | SPML-KCM-MEP-MIR-EL-0097 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43512
3 | MIR | SPML-KCM-MEP-MIR-EL-0420 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44193
3 | MIR | SPML-KCM-MEP-MIR-EL-0657 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44193
3 | MIR | SPML-KCM-MEP-MIR-EL-111 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43527
3 | MIR | SPML-KCM-MEP-MIR-EL-112 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-112 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43530
3 | MIR | SPML-KCM-MEP-MIR-EL-113 | Power Distribution | Identification | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43542
3 | MIR | SPML-KCM-MEP-MIR-EL-113 | Power Distribution | Identification | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43527
3 | MIR | SPML-KCM-MEP-MIR-EL-120 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43550
3 | MIR | SPML-KCM-MEP-MIR-EL-120 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-120 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43530
3 | MIR | SPML-KCM-MEP-MIR-EL-121 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-121 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43530
3 | MIR | SPML-KCM-MEP-MIR-EL-126 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43550
3 | MIR | SPML-KCM-MEP-MIR-EL-126 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43533
3 | MIR | SPML-KCM-MEP-MIR-EL-127 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43533
3 | MIR | SPML-KCM-MEP-MIR-EL-142 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43537
3 | MIR | SPML-KCM-MEP-MIR-EL-149 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43544
3 | MIR | SPML-KCM-MEP-MIR-EL-150 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43544
3 | MIR | SPML-KCM-MEP-MIR-EL-156 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43544
3 | MIR | SPML-KCM-MEP-MIR-EL-165 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43547
3 | MIR | SPML-KCM-MEP-MIR-EL-174 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43550
3 | MIR | SPML-KCM-MEP-MIR-EL-175 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43550
3 | MIR | SPML-KCM-MEP-MIR-EL-176 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43550
3 | MIR | SPML-KCM-MEP-MIR-EL-181 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43552
3 | MIR | SPML-KCM-MEP-MIR-EL-182 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-182 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43552
3 | MIR | SPML-KCM-MEP-MIR-EL-183 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43552
3 | MIR | SPML-KCM-MEP-MIR-EL-185 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43554
3 | MIR | SPML-KCM-MEP-MIR-EL-191 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43555
3 | MIR | SPML-KCM-MEP-MIR-EL-204 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43562
3 | MIR | SPML-KCM-MEP-MIR-EL-208 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43564
3 | MIR | SPML-KCM-MEP-MIR-EL-209 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43575
3 | MIR | SPML-KCM-MEP-MIR-EL-209 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-209 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43564
3 | MIR | SPML-KCM-MEP-MIR-EL-210 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43564
3 | MIR | SPML-KCM-MEP-MIR-EL-211 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43564
3 | MIR | SPML-KCM-MEP-MIR-EL-216 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43583
3 | MIR | SPML-KCM-MEP-MIR-EL-216 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43566
3 | MIR | SPML-KCM-MEP-MIR-EL-221 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43569
3 | MIR | SPML-KCM-MEP-MIR-EL-228 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43575
3 | MIR | SPML-KCM-MEP-MIR-EL-235 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43578
3 | MIR | SPML-KCM-MEP-MIR-EL-244 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43583
3 | MIR | SPML-KCM-MEP-MIR-EL-245 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43583
3 | MIR | SPML-KCM-MEP-MIR-EL-246 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43583
3 | MIR | SPML-KCM-MEP-MIR-EL-247 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43583
3 | MIR | SPML-KCM-MEP-MIR-EL-248 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43583
3 | MIR | SPML-KCM-MEP-MIR-EL-253 | Power Distribution | UPS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43584
3 | MIR | SPML-KCM-MEP-MIR-EL-254 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43585
3 | MIR | SPML-KCM-MEP-MIR-EL-256 | HV System | Transformers | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43590
3 | MIR | SPML-KCM-MEP-MIR-EL-267 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43599
3 | MIR | SPML-KCM-MEP-MIR-EL-272 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43605
3 | MIR | SPML-KCM-MEP-MIR-EL-274 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43605
3 | MIR | SPML-KCM-MEP-MIR-EL-275 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43605
3 | MIR | SPML-KCM-MEP-MIR-EL-282 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43613
3 | MIR | SPML-KCM-MEP-MIR-EL-283 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43613
3 | MIR | SPML-KCM-MEP-MIR-EL-289 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43614
3 | MIR | SPML-KCM-MEP-MIR-EL-298 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43625
3 | MIR | SPML-KCM-MEP-MIR-EL-304 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43628
3 | MIR | SPML-KCM-MEP-MIR-EL-305 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43628
3 | MIR | SPML-KCM-MEP-MIR-EL-314 | Emergency Lighting | CBS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43634
3 | MIR | SPML-KCM-MEP-MIR-EL-315 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43634
3 | MIR | SPML-KCM-MEP-MIR-EL-316 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43652
3 | MIR | SPML-KCM-MEP-MIR-EL-316 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43635
3 | MIR | SPML-KCM-MEP-MIR-EL-333 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43641
3 | MIR | SPML-KCM-MEP-MIR-EL-334 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43641
3 | MIR | SPML-KCM-MEP-MIR-EL-335 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43645
3 | MIR | SPML-KCM-MEP-MIR-EL-336 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43645
3 | MIR | SPML-KCM-MEP-MIR-EL-337 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43645
3 | MIR | SPML-KCM-MEP-MIR-EL-338 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43645
3 | MIR | SPML-KCM-MEP-MIR-EL-342 | ELV | Access Control System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43646
3 | MIR | SPML-KCM-MEP-MIR-EL-344 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43647
3 | MIR | SPML-KCM-MEP-MIR-EL-345 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43647
3 | MIR | SPML-KCM-MEP-MIR-EL-347 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43648
3 | MIR | SPML-KCM-MEP-MIR-EL-348 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43648
3 | MIR | SPML-KCM-MEP-MIR-EL-349 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43648
3 | MIR | SPML-KCM-MEP-MIR-EL-350 | Earthing & Lighting Protection | Lightning Protection | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43648
3 | MIR | SPML-KCM-MEP-MIR-EL-368 | Power Distribution | Distribution Board | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43652
3 | MIR | SPML-KCM-MEP-MIR-EL-369 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43652
3 | MIR | SPML-KCM-MEP-MIR-EL-372 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43654
3 | MIR | SPML-KCM-MEP-MIR-EL-373 | Power Distribution | Distribution Board | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43654
3 | MIR | SPML-KCM-MEP-MIR-EL-374 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43654
3 | MIR | SPML-KCM-MEP-MIR-EL-375 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43654
3 | MIR | SPML-KCM-MEP-MIR-EL-383 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43655
3 | MIR | SPML-KCM-MEP-MIR-EL-384 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43655
3 | MIR | SPML-KCM-MEP-MIR-EL-385 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43663
3 | MIR | SPML-KCM-MEP-MIR-EL-385 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43657
3 | MIR | SPML-KCM-MEP-MIR-EL-388 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43673
3 | MIR | SPML-KCM-MEP-MIR-EL-388 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43660
3 | MIR | SPML-KCM-MEP-MIR-EL-389 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43667
3 | MIR | SPML-KCM-MEP-MIR-EL-389 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43660
3 | MIR | SPML-KCM-MEP-MIR-EL-390 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43660
3 | MIR | SPML-KCM-MEP-MIR-EL-391 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43660
3 | MIR | SPML-KCM-MEP-MIR-EL-392 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43660
3 | MIR | SPML-KCM-MEP-MIR-EL-393 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43660
3 | MIR | SPML-KCM-MEP-MIR-EL-397 | Power Distribution | Isolators | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-397 | Power Distribution | Isolators | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43662
3 | MIR | SPML-KCM-MEP-MIR-EL-398 | Power Distribution | Distribution Board | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43662
3 | MIR | SPML-KCM-MEP-MIR-EL-399 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43680
3 | MIR | SPML-KCM-MEP-MIR-EL-399 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43662
3 | MIR | SPML-KCM-MEP-MIR-EL-401 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43662
3 | MIR | SPML-KCM-MEP-MIR-EL-402 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43666
3 | MIR | SPML-KCM-MEP-MIR-EL-403 | Earthing & Lighting Protection | Lightning Protection | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43666
3 | MIR | SPML-KCM-MEP-MIR-EL-404 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43666
3 | MIR | SPML-KCM-MEP-MIR-EL-405 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43666
3 | MIR | SPML-KCM-MEP-MIR-EL-406 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43667
3 | MIR | SPML-KCM-MEP-MIR-EL-407 | Power Distribution | Distribution Board | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43666
3 | MIR | SPML-KCM-MEP-MIR-EL-408 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43667
3 | MIR | SPML-KCM-MEP-MIR-EL-418 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43668
3 | MIR | SPML-KCM-MEP-MIR-EL-419 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43671
3 | MIR | SPML-KCM-MEP-MIR-EL-420 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43669
3 | MIR | SPML-KCM-MEP-MIR-EL-426 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43674
3 | MIR | SPML-KCM-MEP-MIR-EL-427 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-427 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43673
3 | MIR | SPML-KCM-MEP-MIR-EL-428 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43673
3 | MIR | SPML-KCM-MEP-MIR-EL-430 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44088
3 | MIR | SPML-KCM-MEP-MIR-EL-430 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43674
3 | MIR | SPML-KCM-MEP-MIR-EL-433 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43675
3 | MIR | SPML-KCM-MEP-MIR-EL-435 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43675
3 | MIR | SPML-KCM-MEP-MIR-EL-440 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43676
3 | MIR | SPML-KCM-MEP-MIR-EL-443 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43677
3 | MIR | SPML-KCM-MEP-MIR-EL-445 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43677
3 | MIR | SPML-KCM-MEP-MIR-EL-454 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43681
3 | MIR | SPML-KCM-MEP-MIR-EL-455 | ELV | Access Control System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43681
3 | MIR | SPML-KCM-MEP-MIR-EL-455 | ELV | Access Control System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-462 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43683
3 | MIR | SPML-KCM-MEP-MIR-EL-463 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43683
3 | MIR | SPML-KCM-MEP-MIR-EL-464 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43683
3 | MIR | SPML-KCM-MEP-MIR-EL-469 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43691
3 | MIR | SPML-KCM-MEP-MIR-EL-470 | HV System | Transformers | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43692
3 | MIR | SPML-KCM-MEP-MIR-EL-480 | Power Distribution | Distribution Board | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43695
3 | MIR | SPML-KCM-MEP-MIR-EL-495 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43703
3 | MIR | SPML-KCM-MEP-MIR-EL-499 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43703
3 | MIR | SPML-KCM-MEP-MIR-EL-500 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43704
3 | MIR | SPML-KCM-MEP-MIR-EL-501 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43704
3 | MIR | SPML-KCM-MEP-MIR-EL-502 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43706
3 | MIR | SPML-KCM-MEP-MIR-EL-507 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-507 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43710
3 | MIR | SPML-KCM-MEP-MIR-EL-508 | Earthing & Lighting Protection | Lightning Protection | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43710
3 | MIR | SPML-KCM-MEP-MIR-EL-510 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43712
3 | MIR | SPML-KCM-MEP-MIR-EL-511 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43713
3 | MIR | SPML-KCM-MEP-MIR-EL-512 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43713
3 | MIR | SPML-KCM-MEP-MIR-EL-517 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43716
3 | MIR | SPML-KCM-MEP-MIR-EL-518 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43719
3 | MIR | SPML-KCM-MEP-MIR-EL-519 | Power Distribution | Isolators | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43722
3 | MIR | SPML-KCM-MEP-MIR-EL-521 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44086
3 | MIR | SPML-KCM-MEP-MIR-EL-521 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43723
3 | MIR | SPML-KCM-MEP-MIR-EL-522 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43723
3 | MIR | SPML-KCM-MEP-MIR-EL-532 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43725
3 | MIR | SPML-KCM-MEP-MIR-EL-533 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-533 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43725
3 | MIR | SPML-KCM-MEP-MIR-EL-534 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43726
3 | MIR | SPML-KCM-MEP-MIR-EL-535 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43726
3 | MIR | SPML-KCM-MEP-MIR-EL-541 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43729
3 | MIR | SPML-KCM-MEP-MIR-EL-542 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43729
3 | MIR | SPML-KCM-MEP-MIR-EL-543 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43729
3 | MIR | SPML-KCM-MEP-MIR-EL-544 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43729
3 | MIR | SPML-KCM-MEP-MIR-EL-545 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43729
3 | MIR | SPML-KCM-MEP-MIR-EL-546 | Power Distribution | Isolators | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43729
3 | MIR | SPML-KCM-MEP-MIR-EL-547 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43729
3 | MIR | SPML-KCM-MEP-MIR-EL-548 | Power Distribution | MDB | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43729
3 | MIR | SPML-KCM-MEP-MIR-EL-549 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43729
3 | MIR | SPML-KCM-MEP-MIR-EL-550 | ELV | Access Control System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43732
3 | MIR | SPML-KCM-MEP-MIR-EL-551 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-551 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43732
3 | MIR | SPML-KCM-MEP-MIR-EL-552 | Earthing & Lighting Protection | Lightning Protection | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43737
3 | MIR | SPML-KCM-MEP-MIR-EL-553 | Power Distribution | Isolators | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43737
3 | MIR | SPML-KCM-MEP-MIR-EL-554 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43737
3 | MIR | SPML-KCM-MEP-MIR-EL-555 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43737
3 | MIR | SPML-KCM-MEP-MIR-EL-556 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43737
3 | MIR | SPML-KCM-MEP-MIR-EL-557 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43737
3 | MIR | SPML-KCM-MEP-MIR-EL-558 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43737
3 | MIR | SPML-KCM-MEP-MIR-EL-559 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43737
3 | MIR | SPML-KCM-MEP-MIR-EL-560 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43733
3 | MIR | SPML-KCM-MEP-MIR-EL-564 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43738
3 | MIR | SPML-KCM-MEP-MIR-EL-566 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43739
3 | MIR | SPML-KCM-MEP-MIR-EL-572 | Power Distribution | UPS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43745
3 | MIR | SPML-KCM-MEP-MIR-EL-573 | ELV | Access Control System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43755
3 | MIR | SPML-KCM-MEP-MIR-EL-574 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43745
3 | MIR | SPML-KCM-MEP-MIR-EL-575 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43745
3 | MIR | SPML-KCM-MEP-MIR-EL-577 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43744
3 | MIR | SPML-KCM-MEP-MIR-EL-579 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43744
3 | MIR | SPML-KCM-MEP-MIR-EL-587 | Earthing & Lighting Protection | Lightning Protection | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43753
3 | MIR | SPML-KCM-MEP-MIR-EL-588 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43753
3 | MIR | SPML-KCM-MEP-MIR-EL-589 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43753
3 | MIR | SPML-KCM-MEP-MIR-EL-590 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43753
3 | MIR | SPML-KCM-MEP-MIR-EL-591 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43753
3 | MIR | SPML-KCM-MEP-MIR-EL-592 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43755
3 | MIR | SPML-KCM-MEP-MIR-EL-595 | ELV | Disabled Toilet Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43757
3 | MIR | SPML-KCM-MEP-MIR-EL-603 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43762
3 | MIR | SPML-KCM-MEP-MIR-EL-604 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43762
3 | MIR | SPML-KCM-MEP-MIR-EL-605 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43762
3 | MIR | SPML-KCM-MEP-MIR-EL-606 | Power Distribution | Isolators | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43762
3 | MIR | SPML-KCM-MEP-MIR-EL-607 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43762
3 | MIR | SPML-KCM-MEP-MIR-EL-608 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43762
3 | MIR | SPML-KCM-MEP-MIR-EL-609 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43771
3 | MIR | SPML-KCM-MEP-MIR-EL-610 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43765
3 | MIR | SPML-KCM-MEP-MIR-EL-611 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43765
3 | MIR | SPML-KCM-MEP-MIR-EL-612 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43765
3 | MIR | SPML-KCM-MEP-MIR-EL-613 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43765
3 | MIR | SPML-KCM-MEP-MIR-EL-614 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43765
3 | MIR | SPML-KCM-MEP-MIR-EL-620 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43799
3 | MIR | SPML-KCM-MEP-MIR-EL-621 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43767
3 | MIR | SPML-KCM-MEP-MIR-EL-622 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43771
3 | MIR | SPML-KCM-MEP-MIR-EL-623 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43771
3 | MIR | SPML-KCM-MEP-MIR-EL-624 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43774
3 | MIR | SPML-KCM-MEP-MIR-EL-625 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43775
3 | MIR | SPML-KCM-MEP-MIR-EL-626 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43775
3 | MIR | SPML-KCM-MEP-MIR-EL-627 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43775
3 | MIR | SPML-KCM-MEP-MIR-EL-633 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43779
3 | MIR | SPML-KCM-MEP-MIR-EL-634 | Power Distribution | Isolators | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-634 | Power Distribution | Isolators | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43779
3 | MIR | SPML-KCM-MEP-MIR-EL-635 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43780
3 | MIR | SPML-KCM-MEP-MIR-EL-636 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43781
3 | MIR | SPML-KCM-MEP-MIR-EL-637 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43782
3 | MIR | SPML-KCM-MEP-MIR-EL-638 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43783
3 | MIR | SPML-KCM-MEP-MIR-EL-639 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43782
3 | MIR | SPML-KCM-MEP-MIR-EL-640 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43782
3 | MIR | SPML-KCM-MEP-MIR-EL-642 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43783
3 | MIR | SPML-KCM-MEP-MIR-EL-649 | Power Distribution | Control Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43787
3 | MIR | SPML-KCM-MEP-MIR-EL-650 | Power Distribution | Capacitor Bank | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43787
3 | MIR | SPML-KCM-MEP-MIR-EL-651 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43787
3 | MIR | SPML-KCM-MEP-MIR-EL-652 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43790
3 | MIR | SPML-KCM-MEP-MIR-EL-653 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43790
3 | MIR | SPML-KCM-MEP-MIR-EL-654 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43790
3 | MIR | SPML-KCM-MEP-MIR-EL-655 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43792
3 | MIR | SPML-KCM-MEP-MIR-EL-655 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | D | 43816
3 | MIR | SPML-KCM-MEP-MIR-EL-656 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43792
3 | MIR | SPML-KCM-MEP-MIR-EL-657 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43793
3 | MIR | SPML-KCM-MEP-MIR-EL-658 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43793
3 | MIR | SPML-KCM-MEP-MIR-EL-659 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43793
3 | MIR | SPML-KCM-MEP-MIR-EL-660 | Earthing & Lighting Protection | Lightning Protection | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43793
3 | MIR | SPML-KCM-MEP-MIR-EL-661 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43795
3 | MIR | SPML-KCM-MEP-MIR-EL-662 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43816
3 | MIR | SPML-KCM-MEP-MIR-EL-662 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43795
3 | MIR | SPML-KCM-MEP-MIR-EL-663 | Power Distribution | Control Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43795
3 | MIR | SPML-KCM-MEP-MIR-EL-664 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43822
3 | MIR | SPML-KCM-MEP-MIR-EL-665 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43804
3 | MIR | SPML-KCM-MEP-MIR-EL-665 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-666 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43808
3 | MIR | SPML-KCM-MEP-MIR-EL-668 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43808
3 | MIR | SPML-KCM-MEP-MIR-EL-669 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43808
3 | MIR | SPML-KCM-MEP-MIR-EL-670 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43808
3 | MIR | SPML-KCM-MEP-MIR-EL-672 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43822
3 | MIR | SPML-KCM-MEP-MIR-EL-672 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | D | 43811
3 | MIR | SPML-KCM-MEP-MIR-EL-673 | Power Distribution | Control Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43811
3 | MIR | SPML-KCM-MEP-MIR-EL-674 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43813
3 | MIR | SPML-KCM-MEP-MIR-EL-675 | Power Distribution | Control Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43813
3 | MIR | SPML-KCM-MEP-MIR-EL-676 | Power Distribution | Control Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43813
3 | MIR | SPML-KCM-MEP-MIR-EL-677 | ELV | Access Control System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43815
3 | MIR | SPML-KCM-MEP-MIR-EL-679 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43822
3 | MIR | SPML-KCM-MEP-MIR-EL-680 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43822
3 | MIR | SPML-KCM-MEP-MIR-EL-681 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43822
3 | MIR | SPML-KCM-MEP-MIR-EL-682 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43822
3 | MIR | SPML-KCM-MEP-MIR-EL-683 | HV System | Transformers | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43822
3 | MIR | SPML-KCM-MEP-MIR-EL-684 | Power Distribution | Control Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43825
3 | MIR | SPML-KCM-MEP-MIR-EL-685 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43829
3 | MIR | SPML-KCM-MEP-MIR-EL-686 | Emergency Lighting | CBS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43825
3 | MIR | SPML-KCM-MEP-MIR-EL-687 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43825
3 | MIR | SPML-KCM-MEP-MIR-EL-688 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43828
3 | MIR | SPML-KCM-MEP-MIR-EL-689 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43829
3 | MIR | SPML-KCM-MEP-MIR-EL-690 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43842
3 | MIR | SPML-KCM-MEP-MIR-EL-691 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43843
3 | MIR | SPML-KCM-MEP-MIR-EL-692 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43843
3 | MIR | SPML-KCM-MEP-MIR-EL-693 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-EL-693 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43849
3 | MIR | SPML-KCM-MEP-MIR-EL-696 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43856
3 | MIR | SPML-KCM-MEP-MIR-EL-697 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43856
3 | MIR | SPML-KCM-MEP-MIR-EL-698 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43856
3 | MIR | SPML-KCM-MEP-MIR-EL-700 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43856
3 | MIR | SPML-KCM-MEP-MIR-EL-702 | Power Distribution | HV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43857
3 | MIR | SPML-KCM-MEP-MIR-EL-703 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43857
3 | MIR | SPML-KCM-MEP-MIR-EL-706 | Power Distribution | VFD | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44188
3 | MIR | SPML-KCM-MEP-MIR-EL-706 | Power Distribution | VFD | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43867
3 | MIR | SPML-KCM-MEP-MIR-EL-706 | Power Distribution | VFD | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 44145
3 | MIR | SPML-KCM-MEP-MIR-EL-710 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43874
3 | MIR | SPML-KCM-MEP-MIR-EL-711 | Earthing & Lighting Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43878
3 | MIR | SPML-KCM-MEP-MIR-EL-712 | Power Distribution | Identification | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43874
3 | MIR | SPML-KCM-MEP-MIR-EL-713 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43878
3 | MIR | SPML-KCM-MEP-MIR-EL-714 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43876
3 | MIR | SPML-KCM-MEP-MIR-EL-715 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43876
3 | MIR | SPML-KCM-MEP-MIR-EL-716 | Emergency Lighting | CBS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43876
3 | MIR | SPML-KCM-MEP-MIR-EL-717 | Power Distribution | VFD | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44188
3 | MIR | SPML-KCM-MEP-MIR-EL-717 | Power Distribution | VFD | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43879
3 | MIR | SPML-KCM-MEP-MIR-EL-717 | Power Distribution | VFD | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 44145
3 | MIR | SPML-KCM-MEP-MIR-EL-718 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43890
3 | MIR | SPML-KCM-MEP-MIR-EL-719 | Earthing & Lighting Protection | Lightning Protection | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43894
3 | MIR | SPML-KCM-MEP-MIR-EL-720 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43895
3 | MIR | SPML-KCM-MEP-MIR-EL-721 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43904
3 | MIR | SPML-KCM-MEP-MIR-EL-722 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43905
3 | MIR | SPML-KCM-MEP-MIR-EL-724 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43921
3 | MIR | SPML-KCM-MEP-MIR-EL-725 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43944
3 | MIR | SPML-KCM-MEP-MIR-EL-726 | Power Distribution | EV Charger | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43961
3 | MIR | SPML-KCM-MEP-MIR-EL-726 | Power Distribution | EV Charger | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43944
3 | MIR | SPML-KCM-MEP-MIR-EL-727 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43979
3 | MIR | SPML-KCM-MEP-MIR-EL-730 | Power Distribution | EV Charger | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44051
3 | MIR | SPML-KCM-MEP-MIR-EL-732 | Earthing & Lighting Protection | Lightning Protection | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-733 | Power Distribution | EV Charger | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-734 | Power Distribution | Identification | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-735 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-736 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-737 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-738 | Power Distribution | RMU | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-739 | HV System | Transformers | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-740 | Power Distribution | HV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-741 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-741 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | D | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-742 | Power Distribution | UPS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-743 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-744 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-745 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44117
3 | MIR | SPML-KCM-MEP-MIR-EL-745 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-746 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-747 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-748 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-749 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-750 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-751 | Power Distribution | Isolators | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-752 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44116
3 | MIR | SPML-KCM-MEP-MIR-EL-752 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-753 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-754 | ELV | Access Control System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-755 | ELV | Disabled Toilet Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-756 | Power Distribution | Control Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-757 | Power Distribution | Capacitor Bank | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44117
3 | MIR | SPML-KCM-MEP-MIR-EL-757 | Power Distribution | Capacitor Bank | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | D | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-758 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44117
3 | MIR | SPML-KCM-MEP-MIR-EL-758 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | D | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-759 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44150
3 | MIR | SPML-KCM-MEP-MIR-EL-759 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MEP-MIR-EL-759 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-760 | Power Distribution | Control Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-760 | Power Distribution | Control Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MEP-MIR-EL-761 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-762 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-763 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-764 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-765 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-766 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-767 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-768 | Emergency Lighting | CBS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44090
3 | MIR | SPML-KCM-MEP-MIR-EL-818 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44097
3 | MIR | SPML-KCM-MEP-MIR-EL-819 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44097
3 | MIR | SPML-KCM-MEP-MIR-EL-821 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44108
3 | MIR | SPML-KCM-MEP-MIR-EL-822 | ELV | Access Control System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44108
3 | MIR | SPML-KCM-MEP-MIR-EL-823 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44108
3 | MIR | SPML-KCM-MEP-MIR-EL-827 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MEP-MIR-EL-827 | Power Distribution | LV Cable | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MEP-MIR-EL-828 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44117
3 | MIR | SPML-KCM-MEP-MIR-EL-829 | ELV | Access Control System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44117
3 | MIR | SPML-KCM-MEP-MIR-EL-830 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44117
3 | MIR | SPML-KCM-MEP-MIR-FF-701 | Fire Fighting System | Water Deluge system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43856
3 | MIR | SPML-KCM-MEP-MIR-PL-0001 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43318
3 | MIR | SPML-KCM-MEP-MIR-PL-0001 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43312
3 | MIR | SPML-KCM-MEP-MIR-PL-0003 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43318
3 | MIR | SPML-KCM-MEP-MIR-PL-0004 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44101
3 | MIR | SPML-KCM-MEP-MIR-PL-0004 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43324
3 | MIR | SPML-KCM-MEP-MIR-PL-0005 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43324
3 | MIR | SPML-KCM-MEP-MIR-PL-0006 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43324
3 | MIR | SPML-KCM-MEP-MIR-PL-0008 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-0008 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43337
3 | MIR | SPML-KCM-MEP-MIR-PL-0010 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44110
3 | MIR | SPML-KCM-MEP-MIR-PL-0010 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43339
3 | MIR | SPML-KCM-MEP-MIR-PL-0011 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43354
3 | MIR | SPML-KCM-MEP-MIR-PL-0012 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43354
3 | MIR | SPML-KCM-MEP-MIR-PL-0013 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43354
3 | MIR | SPML-KCM-MEP-MIR-PL-0018 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43369
3 | MIR | SPML-KCM-MEP-MIR-PL-0019 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43369
3 | MIR | SPML-KCM-MEP-MIR-PL-0020 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43373
3 | MIR | SPML-KCM-MEP-MIR-PL-0021 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43379
3 | MIR | SPML-KCM-MEP-MIR-PL-0023 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43381
3 | MIR | SPML-KCM-MEP-MIR-PL-0024 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43386
3 | MIR | SPML-KCM-MEP-MIR-PL-0025 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43387
3 | MIR | SPML-KCM-MEP-MIR-PL-0026 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43389
3 | MIR | SPML-KCM-MEP-MIR-PL-0027 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43389
3 | MIR | SPML-KCM-MEP-MIR-PL-0032 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43398
3 | MIR | SPML-KCM-MEP-MIR-PL-0033 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43401
3 | MIR | SPML-KCM-MEP-MIR-PL-0034 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43411
3 | MIR | SPML-KCM-MEP-MIR-PL-0035 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43411
3 | MIR | SPML-KCM-MEP-MIR-PL-0036 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43416
3 | MIR | SPML-KCM-MEP-MIR-PL-0037 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43418
3 | MIR | SPML-KCM-MEP-MIR-PL-0038 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-0038 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43418
3 | MIR | SPML-KCM-MEP-MIR-PL-0039 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43421
3 | MIR | SPML-KCM-MEP-MIR-PL-0040 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43428
3 | MIR | SPML-KCM-MEP-MIR-PL-0044 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43440
3 | MIR | SPML-KCM-MEP-MIR-PL-0045 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43442
3 | MIR | SPML-KCM-MEP-MIR-PL-0047 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43443
3 | MIR | SPML-KCM-MEP-MIR-PL-0049 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43453
3 | MIR | SPML-KCM-MEP-MIR-PL-0050 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43453
3 | MIR | SPML-KCM-MEP-MIR-PL-0051 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43375
3 | MIR | SPML-KCM-MEP-MIR-PL-0052 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43464
3 | MIR | SPML-KCM-MEP-MIR-PL-0053 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43465
3 | MIR | SPML-KCM-MEP-MIR-PL-0055 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-0055 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43477
3 | MIR | SPML-KCM-MEP-MIR-PL-0056 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43481
3 | MIR | SPML-KCM-MEP-MIR-PL-0060 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43480
3 | MIR | SPML-KCM-MEP-MIR-PL-0061 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43481
3 | MIR | SPML-KCM-MEP-MIR-PL-0062 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43481
3 | MIR | SPML-KCM-MEP-MIR-PL-0063 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43482
3 | MIR | SPML-KCM-MEP-MIR-PL-0064 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43482
3 | MIR | SPML-KCM-MEP-MIR-PL-0065 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43485
3 | MIR | SPML-KCM-MEP-MIR-PL-0066 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44088
3 | MIR | SPML-KCM-MEP-MIR-PL-0066 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43487
3 | MIR | SPML-KCM-MEP-MIR-PL-0067 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43487
3 | MIR | SPML-KCM-MEP-MIR-PL-0069 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43488
3 | MIR | SPML-KCM-MEP-MIR-PL-0070 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44100
3 | MIR | SPML-KCM-MEP-MIR-PL-0070 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43492
3 | MIR | SPML-KCM-MEP-MIR-PL-0071 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43492
3 | MIR | SPML-KCM-MEP-MIR-PL-0072 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43492
3 | MIR | SPML-KCM-MEP-MIR-PL-0072 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43500
3 | MIR | SPML-KCM-MEP-MIR-PL-0073 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43492
3 | MIR | SPML-KCM-MEP-MIR-PL-0074 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44110
3 | MIR | SPML-KCM-MEP-MIR-PL-0074 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43493
3 | MIR | SPML-KCM-MEP-MIR-PL-0075 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43493
3 | MIR | SPML-KCM-MEP-MIR-PL-0078 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43499
3 | MIR | SPML-KCM-MEP-MIR-PL-0078 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43496
3 | MIR | SPML-KCM-MEP-MIR-PL-0084 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43506
3 | MIR | SPML-KCM-MEP-MIR-PL-0085 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43506
3 | MIR | SPML-KCM-MEP-MIR-PL-0086 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43507
3 | MIR | SPML-KCM-MEP-MIR-PL-0087 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43507
3 | MIR | SPML-KCM-MEP-MIR-PL-0088 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43520
3 | MIR | SPML-KCM-MEP-MIR-PL-0088 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44193
3 | MIR | SPML-KCM-MEP-MIR-PL-0089 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43508
3 | MIR | SPML-KCM-MEP-MIR-PL-0090 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43509
3 | MIR | SPML-KCM-MEP-MIR-PL-0091 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43510
3 | MIR | SPML-KCM-MEP-MIR-PL-0092 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43512
3 | MIR | SPML-KCM-MEP-MIR-PL-0093 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43512
3 | MIR | SPML-KCM-MEP-MIR-PL-0094 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43512
3 | MIR | SPML-KCM-MEP-MIR-PL-0095 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-0095 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43513
3 | MIR | SPML-KCM-MEP-MIR-PL-0098 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43513
3 | MIR | SPML-KCM-MEP-MIR-PL-0098 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-0099 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43514
3 | MIR | SPML-KCM-MEP-MIR-PL-0099 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-0100 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43519
3 | MIR | SPML-KCM-MEP-MIR-PL-0102 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43516
3 | MIR | SPML-KCM-MEP-MIR-PL-0103 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43519
3 | MIR | SPML-KCM-MEP-MIR-PL-0104 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43519
3 | MIR | SPML-KCM-MEP-MIR-PL-0105 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43519
3 | MIR | SPML-KCM-MEP-MIR-PL-0106 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43519
3 | MIR | SPML-KCM-MEP-MIR-PL-0107 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43521
3 | MIR | SPML-KCM-MEP-MIR-PL-0108 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43528
3 | MIR | SPML-KCM-MEP-MIR-PL-0137 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44193
3 | MIR | SPML-KCM-MEP-MIR-PL-109 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43523
3 | MIR | SPML-KCM-MEP-MIR-PL-110 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43526
3 | MIR | SPML-KCM-MEP-MIR-PL-114 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43528
3 | MIR | SPML-KCM-MEP-MIR-PL-114 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-115 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43528
3 | MIR | SPML-KCM-MEP-MIR-PL-116 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43528
3 | MIR | SPML-KCM-MEP-MIR-PL-117 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43529
3 | MIR | SPML-KCM-MEP-MIR-PL-118 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43529
3 | MIR | SPML-KCM-MEP-MIR-PL-119 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43529
3 | MIR | SPML-KCM-MEP-MIR-PL-122 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-122 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43530
3 | MIR | SPML-KCM-MEP-MIR-PL-123 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43530
3 | MIR | SPML-KCM-MEP-MIR-PL-124 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43533
3 | MIR | SPML-KCM-MEP-MIR-PL-125 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43533
3 | MIR | SPML-KCM-MEP-MIR-PL-128 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43534
3 | MIR | SPML-KCM-MEP-MIR-PL-129 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43534
3 | MIR | SPML-KCM-MEP-MIR-PL-130 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43534
3 | MIR | SPML-KCM-MEP-MIR-PL-131 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-131 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43534
3 | MIR | SPML-KCM-MEP-MIR-PL-132 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43534
3 | MIR | SPML-KCM-MEP-MIR-PL-133 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43534
3 | MIR | SPML-KCM-MEP-MIR-PL-133 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-134 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43535
3 | MIR | SPML-KCM-MEP-MIR-PL-135 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43535
3 | MIR | SPML-KCM-MEP-MIR-PL-136 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43535
3 | MIR | SPML-KCM-MEP-MIR-PL-137 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43535
3 | MIR | SPML-KCM-MEP-MIR-PL-138 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43537
3 | MIR | SPML-KCM-MEP-MIR-PL-139 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43544
3 | MIR | SPML-KCM-MEP-MIR-PL-140 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43537
3 | MIR | SPML-KCM-MEP-MIR-PL-141 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43537
3 | MIR | SPML-KCM-MEP-MIR-PL-143 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44110
3 | MIR | SPML-KCM-MEP-MIR-PL-143 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43538
3 | MIR | SPML-KCM-MEP-MIR-PL-144 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43541
3 | MIR | SPML-KCM-MEP-MIR-PL-145 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43540
3 | MIR | SPML-KCM-MEP-MIR-PL-146 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43540
3 | MIR | SPML-KCM-MEP-MIR-PL-147 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43541
3 | MIR | SPML-KCM-MEP-MIR-PL-148 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43542
3 | MIR | SPML-KCM-MEP-MIR-PL-148 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44088
3 | MIR | SPML-KCM-MEP-MIR-PL-151 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43544
3 | MIR | SPML-KCM-MEP-MIR-PL-152 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43543
3 | MIR | SPML-KCM-MEP-MIR-PL-153 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43543
3 | MIR | SPML-KCM-MEP-MIR-PL-154 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43543
3 | MIR | SPML-KCM-MEP-MIR-PL-155 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43543
3 | MIR | SPML-KCM-MEP-MIR-PL-157 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43544
3 | MIR | SPML-KCM-MEP-MIR-PL-158 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43545
3 | MIR | SPML-KCM-MEP-MIR-PL-159 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43545
3 | MIR | SPML-KCM-MEP-MIR-PL-160 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43545
3 | MIR | SPML-KCM-MEP-MIR-PL-161 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43545
3 | MIR | SPML-KCM-MEP-MIR-PL-162 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43547
3 | MIR | SPML-KCM-MEP-MIR-PL-163 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43547
3 | MIR | SPML-KCM-MEP-MIR-PL-164 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43547
3 | MIR | SPML-KCM-MEP-MIR-PL-166 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43547
3 | MIR | SPML-KCM-MEP-MIR-PL-167 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43547
3 | MIR | SPML-KCM-MEP-MIR-PL-168 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-168 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43552
3 | MIR | SPML-KCM-MEP-MIR-PL-168 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43547
3 | MIR | SPML-KCM-MEP-MIR-PL-169 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-169 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43548
3 | MIR | SPML-KCM-MEP-MIR-PL-170 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43548
3 | MIR | SPML-KCM-MEP-MIR-PL-171 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43548
3 | MIR | SPML-KCM-MEP-MIR-PL-172 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43549
3 | MIR | SPML-KCM-MEP-MIR-PL-173 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43550
3 | MIR | SPML-KCM-MEP-MIR-PL-177 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43550
3 | MIR | SPML-KCM-MEP-MIR-PL-178 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43550
3 | MIR | SPML-KCM-MEP-MIR-PL-179 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43552
3 | MIR | SPML-KCM-MEP-MIR-PL-180 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43552
3 | MIR | SPML-KCM-MEP-MIR-PL-184 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43552
3 | MIR | SPML-KCM-MEP-MIR-PL-186 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43554
3 | MIR | SPML-KCM-MEP-MIR-PL-187 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43554
3 | MIR | SPML-KCM-MEP-MIR-PL-188 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43554
3 | MIR | SPML-KCM-MEP-MIR-PL-188 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-189 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43554
3 | MIR | SPML-KCM-MEP-MIR-PL-190 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43555
3 | MIR | SPML-KCM-MEP-MIR-PL-192 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43558
3 | MIR | SPML-KCM-MEP-MIR-PL-193 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43557
3 | MIR | SPML-KCM-MEP-MIR-PL-194 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43557
3 | MIR | SPML-KCM-MEP-MIR-PL-195 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43557
3 | MIR | SPML-KCM-MEP-MIR-PL-196 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43557
3 | MIR | SPML-KCM-MEP-MIR-PL-197 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43557
3 | MIR | SPML-KCM-MEP-MIR-PL-198 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43559
3 | MIR | SPML-KCM-MEP-MIR-PL-199 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43559
3 | MIR | SPML-KCM-MEP-MIR-PL-200 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43559
3 | MIR | SPML-KCM-MEP-MIR-PL-201 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43559
3 | MIR | SPML-KCM-MEP-MIR-PL-202 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43561
3 | MIR | SPML-KCM-MEP-MIR-PL-203 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43561
3 | MIR | SPML-KCM-MEP-MIR-PL-205 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43562
3 | MIR | SPML-KCM-MEP-MIR-PL-205 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43562
3 | MIR | SPML-KCM-MEP-MIR-PL-206 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43563
3 | MIR | SPML-KCM-MEP-MIR-PL-207 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43563
3 | MIR | SPML-KCM-MEP-MIR-PL-212 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43566
3 | MIR | SPML-KCM-MEP-MIR-PL-213 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43566
3 | MIR | SPML-KCM-MEP-MIR-PL-214 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43566
3 | MIR | SPML-KCM-MEP-MIR-PL-215 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-215 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43566
3 | MIR | SPML-KCM-MEP-MIR-PL-217 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43569
3 | MIR | SPML-KCM-MEP-MIR-PL-218 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43569
3 | MIR | SPML-KCM-MEP-MIR-PL-219 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43573
3 | MIR | SPML-KCM-MEP-MIR-PL-219 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43569
3 | MIR | SPML-KCM-MEP-MIR-PL-220 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43569
3 | MIR | SPML-KCM-MEP-MIR-PL-222 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43570
3 | MIR | SPML-KCM-MEP-MIR-PL-223 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43570
3 | MIR | SPML-KCM-MEP-MIR-PL-224 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43572
3 | MIR | SPML-KCM-MEP-MIR-PL-225 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43572
3 | MIR | SPML-KCM-MEP-MIR-PL-226 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43572
3 | MIR | SPML-KCM-MEP-MIR-PL-227 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43586
3 | MIR | SPML-KCM-MEP-MIR-PL-227 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43572
3 | MIR | SPML-KCM-MEP-MIR-PL-227 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43584
3 | MIR | SPML-KCM-MEP-MIR-PL-229 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43575
3 | MIR | SPML-KCM-MEP-MIR-PL-230 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43575
3 | MIR | SPML-KCM-MEP-MIR-PL-231 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43575
3 | MIR | SPML-KCM-MEP-MIR-PL-232 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43576
3 | MIR | SPML-KCM-MEP-MIR-PL-233 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43576
3 | MIR | SPML-KCM-MEP-MIR-PL-234 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43577
3 | MIR | SPML-KCM-MEP-MIR-PL-236 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43577
3 | MIR | SPML-KCM-MEP-MIR-PL-237 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43577
3 | MIR | SPML-KCM-MEP-MIR-PL-238 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43577
3 | MIR | SPML-KCM-MEP-MIR-PL-239 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43577
3 | MIR | SPML-KCM-MEP-MIR-PL-240 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43577
3 | MIR | SPML-KCM-MEP-MIR-PL-241 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43577
3 | MIR | SPML-KCM-MEP-MIR-PL-242 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43579
3 | MIR | SPML-KCM-MEP-MIR-PL-243 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43579
3 | MIR | SPML-KCM-MEP-MIR-PL-249 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43583
3 | MIR | SPML-KCM-MEP-MIR-PL-250 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43584
3 | MIR | SPML-KCM-MEP-MIR-PL-251 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43584
3 | MIR | SPML-KCM-MEP-MIR-PL-252 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43584
3 | MIR | SPML-KCM-MEP-MIR-PL-255 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-255 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43585
3 | MIR | SPML-KCM-MEP-MIR-PL-257 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43590
3 | MIR | SPML-KCM-MEP-MIR-PL-258 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44102
3 | MIR | SPML-KCM-MEP-MIR-PL-258 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43590
3 | MIR | SPML-KCM-MEP-MIR-PL-259 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43590
3 | MIR | SPML-KCM-MEP-MIR-PL-260 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43590
3 | MIR | SPML-KCM-MEP-MIR-PL-261 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43590
3 | MIR | SPML-KCM-MEP-MIR-PL-262 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43590
3 | MIR | SPML-KCM-MEP-MIR-PL-263 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43596
3 | MIR | SPML-KCM-MEP-MIR-PL-264 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43596
3 | MIR | SPML-KCM-MEP-MIR-PL-265 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43596
3 | MIR | SPML-KCM-MEP-MIR-PL-266 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-266 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43597
3 | MIR | SPML-KCM-MEP-MIR-PL-269 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43600
3 | MIR | SPML-KCM-MEP-MIR-PL-270 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43600
3 | MIR | SPML-KCM-MEP-MIR-PL-271 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43600
3 | MIR | SPML-KCM-MEP-MIR-PL-273 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43605
3 | MIR | SPML-KCM-MEP-MIR-PL-276 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43607
3 | MIR | SPML-KCM-MEP-MIR-PL-277 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43607
3 | MIR | SPML-KCM-MEP-MIR-PL-278 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43608
3 | MIR | SPML-KCM-MEP-MIR-PL-278 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-279 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43608
3 | MIR | SPML-KCM-MEP-MIR-PL-280 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43611
3 | MIR | SPML-KCM-MEP-MIR-PL-281 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43612
3 | MIR | SPML-KCM-MEP-MIR-PL-284 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43613
3 | MIR | SPML-KCM-MEP-MIR-PL-284 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43634
3 | MIR | SPML-KCM-MEP-MIR-PL-285 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-285 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43614
3 | MIR | SPML-KCM-MEP-MIR-PL-286 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43614
3 | MIR | SPML-KCM-MEP-MIR-PL-287 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43614
3 | MIR | SPML-KCM-MEP-MIR-PL-288 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43614
3 | MIR | SPML-KCM-MEP-MIR-PL-290 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43628
3 | MIR | SPML-KCM-MEP-MIR-PL-290 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43617
3 | MIR | SPML-KCM-MEP-MIR-PL-291 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43615
3 | MIR | SPML-KCM-MEP-MIR-PL-292 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43617
3 | MIR | SPML-KCM-MEP-MIR-PL-293 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43617
3 | MIR | SPML-KCM-MEP-MIR-PL-294 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43617
3 | MIR | SPML-KCM-MEP-MIR-PL-295 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43618
3 | MIR | SPML-KCM-MEP-MIR-PL-296 | Fire Fighting System | FM200 | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43641
3 | MIR | SPML-KCM-MEP-MIR-PL-296 | Fire Fighting System | FM200 | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43625
3 | MIR | SPML-KCM-MEP-MIR-PL-297 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43625
3 | MIR | SPML-KCM-MEP-MIR-PL-299 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43626
3 | MIR | SPML-KCM-MEP-MIR-PL-300 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43626
3 | MIR | SPML-KCM-MEP-MIR-PL-301 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43627
3 | MIR | SPML-KCM-MEP-MIR-PL-302 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43628
3 | MIR | SPML-KCM-MEP-MIR-PL-303 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-303 | Power Distribution | Control Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43628
3 | MIR | SPML-KCM-MEP-MIR-PL-306 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43628
3 | MIR | SPML-KCM-MEP-MIR-PL-307 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43646
3 | MIR | SPML-KCM-MEP-MIR-PL-308 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43629
3 | MIR | SPML-KCM-MEP-MIR-PL-308 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43629
3 | MIR | SPML-KCM-MEP-MIR-PL-309 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43631
3 | MIR | SPML-KCM-MEP-MIR-PL-310 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43696
3 | MIR | SPML-KCM-MEP-MIR-PL-310 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43631
3 | MIR | SPML-KCM-MEP-MIR-PL-311 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43632
3 | MIR | SPML-KCM-MEP-MIR-PL-312 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43632
3 | MIR | SPML-KCM-MEP-MIR-PL-313 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-313 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43656
3 | MIR | SPML-KCM-MEP-MIR-PL-313 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43635
3 | MIR | SPML-KCM-MEP-MIR-PL-317 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43635
3 | MIR | SPML-KCM-MEP-MIR-PL-318 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43635
3 | MIR | SPML-KCM-MEP-MIR-PL-319 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43635
3 | MIR | SPML-KCM-MEP-MIR-PL-320 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43635
3 | MIR | SPML-KCM-MEP-MIR-PL-321 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43638
3 | MIR | SPML-KCM-MEP-MIR-PL-322 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43646
3 | MIR | SPML-KCM-MEP-MIR-PL-323 | Identification | Identification | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43638
3 | MIR | SPML-KCM-MEP-MIR-PL-324 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43638
3 | MIR | SPML-KCM-MEP-MIR-PL-325 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43638
3 | MIR | SPML-KCM-MEP-MIR-PL-326 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43638
3 | MIR | SPML-KCM-MEP-MIR-PL-327 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43638
3 | MIR | SPML-KCM-MEP-MIR-PL-328 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43639
3 | MIR | SPML-KCM-MEP-MIR-PL-329 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43639
3 | MIR | SPML-KCM-MEP-MIR-PL-330 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-330 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43706
3 | MIR | SPML-KCM-MEP-MIR-PL-331 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43640
3 | MIR | SPML-KCM-MEP-MIR-PL-332 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43641
3 | MIR | SPML-KCM-MEP-MIR-PL-339 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43646
3 | MIR | SPML-KCM-MEP-MIR-PL-340 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43646
3 | MIR | SPML-KCM-MEP-MIR-PL-341 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43646
3 | MIR | SPML-KCM-MEP-MIR-PL-346 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-346 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43647
3 | MIR | SPML-KCM-MEP-MIR-PL-351 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-351 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43649
3 | MIR | SPML-KCM-MEP-MIR-PL-352 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43649
3 | MIR | SPML-KCM-MEP-MIR-PL-353 | Identification | Identification | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43649
3 | MIR | SPML-KCM-MEP-MIR-PL-354 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43649
3 | MIR | SPML-KCM-MEP-MIR-PL-355 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43649
3 | MIR | SPML-KCM-MEP-MIR-PL-356 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43649
3 | MIR | SPML-KCM-MEP-MIR-PL-357 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43649
3 | MIR | SPML-KCM-MEP-MIR-PL-358 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-358 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43649
3 | MIR | SPML-KCM-MEP-MIR-PL-359 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43650
3 | MIR | SPML-KCM-MEP-MIR-PL-360 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43649
3 | MIR | SPML-KCM-MEP-MIR-PL-361 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43652
3 | MIR | SPML-KCM-MEP-MIR-PL-362 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43652
3 | MIR | SPML-KCM-MEP-MIR-PL-363 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43652
3 | MIR | SPML-KCM-MEP-MIR-PL-364 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43653
3 | MIR | SPML-KCM-MEP-MIR-PL-365 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43653
3 | MIR | SPML-KCM-MEP-MIR-PL-366 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43653
3 | MIR | SPML-KCM-MEP-MIR-PL-367 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43653
3 | MIR | SPML-KCM-MEP-MIR-PL-370 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43654
3 | MIR | SPML-KCM-MEP-MIR-PL-371 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43653
3 | MIR | SPML-KCM-MEP-MIR-PL-376 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43655
3 | MIR | SPML-KCM-MEP-MIR-PL-377 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43655
3 | MIR | SPML-KCM-MEP-MIR-PL-378 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43656
3 | MIR | SPML-KCM-MEP-MIR-PL-379 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43655
3 | MIR | SPML-KCM-MEP-MIR-PL-380 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43655
3 | MIR | SPML-KCM-MEP-MIR-PL-381 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43655
3 | MIR | SPML-KCM-MEP-MIR-PL-382 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43655
3 | MIR | SPML-KCM-MEP-MIR-PL-386 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43657
3 | MIR | SPML-KCM-MEP-MIR-PL-387 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43657
3 | MIR | SPML-KCM-MEP-MIR-PL-394 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-394 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43660
3 | MIR | SPML-KCM-MEP-MIR-PL-395 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-395 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43662
3 | MIR | SPML-KCM-MEP-MIR-PL-396 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43662
3 | MIR | SPML-KCM-MEP-MIR-PL-400 | HVAC | Dampers | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43663
3 | MIR | SPML-KCM-MEP-MIR-PL-409 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MEP-MIR-PL-410 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MEP-MIR-PL-411 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MEP-MIR-PL-412 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MEP-MIR-PL-413 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MEP-MIR-PL-414 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MEP-MIR-PL-415 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MEP-MIR-PL-416 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MEP-MIR-PL-417 | Power Distribution | Isolators | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MEP-MIR-PL-421 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MEP-MIR-PL-422 | Fire Fighting System | FM200 | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43671
3 | MIR | SPML-KCM-MEP-MIR-PL-422 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-423 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43674
3 | MIR | SPML-KCM-MEP-MIR-PL-423 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-424 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43674
3 | MIR | SPML-KCM-MEP-MIR-PL-425 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-425 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43674
3 | MIR | SPML-KCM-MEP-MIR-PL-429 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43673
3 | MIR | SPML-KCM-MEP-MIR-PL-432 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-432 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43674
3 | MIR | SPML-KCM-MEP-MIR-PL-434 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-434 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43676
3 | MIR | SPML-KCM-MEP-MIR-PL-436 | Fire Fighting System | FM200 | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43676
3 | MIR | SPML-KCM-MEP-MIR-PL-436 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-437 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43676
3 | MIR | SPML-KCM-MEP-MIR-PL-438 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43676
3 | MIR | SPML-KCM-MEP-MIR-PL-439 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43676
3 | MIR | SPML-KCM-MEP-MIR-PL-441 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43727
3 | MIR | SPML-KCM-MEP-MIR-PL-441 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43677
3 | MIR | SPML-KCM-MEP-MIR-PL-442 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-442 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43677
3 | MIR | SPML-KCM-MEP-MIR-PL-442 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43677
3 | MIR | SPML-KCM-MEP-MIR-PL-444 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-444 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43677
3 | MIR | SPML-KCM-MEP-MIR-PL-446 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43680
3 | MIR | SPML-KCM-MEP-MIR-PL-446 | HVAC | Dampers | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43718
3 | MIR | SPML-KCM-MEP-MIR-PL-447 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43680
3 | MIR | SPML-KCM-MEP-MIR-PL-448 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43680
3 | MIR | SPML-KCM-MEP-MIR-PL-449 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43678
3 | MIR | SPML-KCM-MEP-MIR-PL-450 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43680
3 | MIR | SPML-KCM-MEP-MIR-PL-451 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43696
3 | MIR | SPML-KCM-MEP-MIR-PL-451 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43681
3 | MIR | SPML-KCM-MEP-MIR-PL-451 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44101
3 | MIR | SPML-KCM-MEP-MIR-PL-452 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43696
3 | MIR | SPML-KCM-MEP-MIR-PL-452 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43696
3 | MIR | SPML-KCM-MEP-MIR-PL-452 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43681
3 | MIR | SPML-KCM-MEP-MIR-PL-453 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43681
3 | MIR | SPML-KCM-MEP-MIR-PL-453 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43696
3 | MIR | SPML-KCM-MEP-MIR-PL-456 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43702
3 | MIR | SPML-KCM-MEP-MIR-PL-456 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-457 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43682
3 | MIR | SPML-KCM-MEP-MIR-PL-458 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43682
3 | MIR | SPML-KCM-MEP-MIR-PL-459 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43682
3 | MIR | SPML-KCM-MEP-MIR-PL-460 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43682
3 | MIR | SPML-KCM-MEP-MIR-PL-461 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43682
3 | MIR | SPML-KCM-MEP-MIR-PL-466 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43691
3 | MIR | SPML-KCM-MEP-MIR-PL-467 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43691
3 | MIR | SPML-KCM-MEP-MIR-PL-468 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43691
3 | MIR | SPML-KCM-MEP-MIR-PL-471 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43692
3 | MIR | SPML-KCM-MEP-MIR-PL-472 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43692
3 | MIR | SPML-KCM-MEP-MIR-PL-473 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43692
3 | MIR | SPML-KCM-MEP-MIR-PL-474 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43692
3 | MIR | SPML-KCM-MEP-MIR-PL-475 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43697
3 | MIR | SPML-KCM-MEP-MIR-PL-476 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43692
3 | MIR | SPML-KCM-MEP-MIR-PL-477 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43692
3 | MIR | SPML-KCM-MEP-MIR-PL-478 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43697
3 | MIR | SPML-KCM-MEP-MIR-PL-479 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43697
3 | MIR | SPML-KCM-MEP-MIR-PL-481 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-481 | HVAC | Cooling Tower | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43696
3 | MIR | SPML-KCM-MEP-MIR-PL-482 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-482 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43697
3 | MIR | SPML-KCM-MEP-MIR-PL-483 | Fire Fighting System | FM200 | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43706
3 | MIR | SPML-KCM-MEP-MIR-PL-484 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43698
3 | MIR | SPML-KCM-MEP-MIR-PL-485 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43697
3 | MIR | SPML-KCM-MEP-MIR-PL-486 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43698
3 | MIR | SPML-KCM-MEP-MIR-PL-487 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43698
3 | MIR | SPML-KCM-MEP-MIR-PL-488 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44101
3 | MIR | SPML-KCM-MEP-MIR-PL-488 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43703
3 | MIR | SPML-KCM-MEP-MIR-PL-489 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43703
3 | MIR | SPML-KCM-MEP-MIR-PL-489 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-490 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43703
3 | MIR | SPML-KCM-MEP-MIR-PL-491 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43703
3 | MIR | SPML-KCM-MEP-MIR-PL-492 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43703
3 | MIR | SPML-KCM-MEP-MIR-PL-493 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43703
3 | MIR | SPML-KCM-MEP-MIR-PL-494 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43703
3 | MIR | SPML-KCM-MEP-MIR-PL-496 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43703
3 | MIR | SPML-KCM-MEP-MIR-PL-497 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43703
3 | MIR | SPML-KCM-MEP-MIR-PL-498 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43703
3 | MIR | SPML-KCM-MEP-MIR-PL-503 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43709
3 | MIR | SPML-KCM-MEP-MIR-PL-504 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43709
3 | MIR | SPML-KCM-MEP-MIR-PL-505 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43711
3 | MIR | SPML-KCM-MEP-MIR-PL-506 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-506 | HVAC | Cooling Tower | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43709
3 | MIR | SPML-KCM-MEP-MIR-PL-509 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43711
3 | MIR | SPML-KCM-MEP-MIR-PL-513 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43718
3 | MIR | SPML-KCM-MEP-MIR-PL-514 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43718
3 | MIR | SPML-KCM-MEP-MIR-PL-515 | HV System | Transformers | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43718
3 | MIR | SPML-KCM-MEP-MIR-PL-516 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43718
3 | MIR | SPML-KCM-MEP-MIR-PL-520 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-520 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43722
3 | MIR | SPML-KCM-MEP-MIR-PL-523 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43724
3 | MIR | SPML-KCM-MEP-MIR-PL-524 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43724
3 | MIR | SPML-KCM-MEP-MIR-PL-525 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43724
3 | MIR | SPML-KCM-MEP-MIR-PL-526 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43727
3 | MIR | SPML-KCM-MEP-MIR-PL-527 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43724
3 | MIR | SPML-KCM-MEP-MIR-PL-528 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43727
3 | MIR | SPML-KCM-MEP-MIR-PL-529 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43727
3 | MIR | SPML-KCM-MEP-MIR-PL-530 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-530 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43724
3 | MIR | SPML-KCM-MEP-MIR-PL-531 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43724
3 | MIR | SPML-KCM-MEP-MIR-PL-531 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44097
3 | MIR | SPML-KCM-MEP-MIR-PL-536 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43727
3 | MIR | SPML-KCM-MEP-MIR-PL-537 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43727
3 | MIR | SPML-KCM-MEP-MIR-PL-538 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43727
3 | MIR | SPML-KCM-MEP-MIR-PL-539 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43727
3 | MIR | SPML-KCM-MEP-MIR-PL-540 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43727
3 | MIR | SPML-KCM-MEP-MIR-PL-561 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43738
3 | MIR | SPML-KCM-MEP-MIR-PL-562 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43738
3 | MIR | SPML-KCM-MEP-MIR-PL-563 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43738
3 | MIR | SPML-KCM-MEP-MIR-PL-567 | Fire Fighting System | Foam Deluge system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43744
3 | MIR | SPML-KCM-MEP-MIR-PL-568 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43740
3 | MIR | SPML-KCM-MEP-MIR-PL-569 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43740
3 | MIR | SPML-KCM-MEP-MIR-PL-570 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-570 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43741
3 | MIR | SPML-KCM-MEP-MIR-PL-571 | Fuel System | Fuel Oil Piping | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43744
3 | MIR | SPML-KCM-MEP-MIR-PL-576 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43744
3 | MIR | SPML-KCM-MEP-MIR-PL-578 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43744
3 | MIR | SPML-KCM-MEP-MIR-PL-580 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43745
3 | MIR | SPML-KCM-MEP-MIR-PL-580 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-581 | HVAC | Dampers | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43745
3 | MIR | SPML-KCM-MEP-MIR-PL-582 | Fuel System | Fuel Oil Piping | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43751
3 | MIR | SPML-KCM-MEP-MIR-PL-583 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43751
3 | MIR | SPML-KCM-MEP-MIR-PL-584 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43751
3 | MIR | SPML-KCM-MEP-MIR-PL-585 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43751
3 | MIR | SPML-KCM-MEP-MIR-PL-586 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43752
3 | MIR | SPML-KCM-MEP-MIR-PL-593 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43753
3 | MIR | SPML-KCM-MEP-MIR-PL-593 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44100
3 | MIR | SPML-KCM-MEP-MIR-PL-594 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43755
3 | MIR | SPML-KCM-MEP-MIR-PL-596 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-596 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43757
3 | MIR | SPML-KCM-MEP-MIR-PL-597 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-597 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43761
3 | MIR | SPML-KCM-MEP-MIR-PL-598 | Manhole | Manhole | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-598 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43761
3 | MIR | SPML-KCM-MEP-MIR-PL-599 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43761
3 | MIR | SPML-KCM-MEP-MIR-PL-599 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-600 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43761
3 | MIR | SPML-KCM-MEP-MIR-PL-601 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43761
3 | MIR | SPML-KCM-MEP-MIR-PL-602 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43761
3 | MIR | SPML-KCM-MEP-MIR-PL-615 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43766
3 | MIR | SPML-KCM-MEP-MIR-PL-616 | HVAC | Dampers | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43766
3 | MIR | SPML-KCM-MEP-MIR-PL-617 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43766
3 | MIR | SPML-KCM-MEP-MIR-PL-618 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43766
3 | MIR | SPML-KCM-MEP-MIR-PL-619 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43766
3 | MIR | SPML-KCM-MEP-MIR-PL-628 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43775
3 | MIR | SPML-KCM-MEP-MIR-PL-629 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43775
3 | MIR | SPML-KCM-MEP-MIR-PL-630 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43775
3 | MIR | SPML-KCM-MEP-MIR-PL-630 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44101
3 | MIR | SPML-KCM-MEP-MIR-PL-631 | Manhole | Manhole | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43775
3 | MIR | SPML-KCM-MEP-MIR-PL-632 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43775
3 | MIR | SPML-KCM-MEP-MIR-PL-643 | HVAC | Duct Work | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43785
3 | MIR | SPML-KCM-MEP-MIR-PL-644 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43785
3 | MIR | SPML-KCM-MEP-MIR-PL-645 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43785
3 | MIR | SPML-KCM-MEP-MIR-PL-646 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43785
3 | MIR | SPML-KCM-MEP-MIR-PL-647 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43785
3 | MIR | SPML-KCM-MEP-MIR-PL-647 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44101
3 | MIR | SPML-KCM-MEP-MIR-PL-648 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43785
3 | MIR | SPML-KCM-MEP-MIR-PL-667 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-667 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43904
3 | MIR | SPML-KCM-MEP-MIR-PL-667 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43880
3 | MIR | SPML-KCM-MEP-MIR-PL-667 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43804
3 | MIR | SPML-KCM-MEP-MIR-PL-671 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43809
3 | MIR | SPML-KCM-MEP-MIR-PL-671 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-678 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-678 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43830
3 | MIR | SPML-KCM-MEP-MIR-PL-694 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43856
3 | MIR | SPML-KCM-MEP-MIR-PL-695 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43856
3 | MIR | SPML-KCM-MEP-MIR-PL-695 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43856
3 | MIR | SPML-KCM-MEP-MIR-PL-699 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43856
3 | MIR | SPML-KCM-MEP-MIR-PL-704 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43863
3 | MIR | SPML-KCM-MEP-MIR-PL-705 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43866
3 | MIR | SPML-KCM-MEP-MIR-PL-705 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-707 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43872
3 | MIR | SPML-KCM-MEP-MIR-PL-707 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44087
3 | MIR | SPML-KCM-MEP-MIR-PL-708 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43872
3 | MIR | SPML-KCM-MEP-MIR-PL-709 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43872
3 | MIR | SPML-KCM-MEP-MIR-PL-723 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-723 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43913
3 | MIR | SPML-KCM-MEP-MIR-PL-729 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 43727
3 | MIR | SPML-KCM-MEP-MIR-PL-729 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 44047
3 | MIR | SPML-KCM-MEP-MIR-PL-773 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MEP-MIR-PL-776 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44094
3 | MIR | SPML-KCM-MIR-0001 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43157
3 | MIR | SPML-KCM-MIR-0002 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43172
3 | MIR | SPML-KCM-MIR-0003 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43186
3 | MIR | SPML-KCM-MIR-0004 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43255
3 | MIR | SPML-KCM-MIR-0004 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43186
3 | MIR | SPML-KCM-MIR-0005 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43255
3 | MIR | SPML-KCM-MIR-0005 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43187
3 | MIR | SPML-KCM-MIR-0006 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43255
3 | MIR | SPML-KCM-MIR-0006 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43191
3 | MIR | SPML-KCM-MIR-0007 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43191
3 | MIR | SPML-KCM-MIR-0008 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43255
3 | MIR | SPML-KCM-MIR-0008 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43191
3 | MIR | SPML-KCM-MIR-0009 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43191
3 | MIR | SPML-KCM-MIR-0010 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0010 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43191
3 | MIR | SPML-KCM-MIR-0011 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43197
3 | MIR | SPML-KCM-MIR-0012 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43197
3 | MIR | SPML-KCM-MIR-0013 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0013 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43200
3 | MIR | SPML-KCM-MIR-0014 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43200
3 | MIR | SPML-KCM-MIR-0015 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43200
3 | MIR | SPML-KCM-MIR-0016 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43206
3 | MIR | SPML-KCM-MIR-0017 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43206
3 | MIR | SPML-KCM-MIR-0018 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43206
3 | MIR | SPML-KCM-MIR-0019 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43208
3 | MIR | SPML-KCM-MIR-0020 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43208
3 | MIR | SPML-KCM-MIR-0021 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43213
3 | MIR | SPML-KCM-MIR-0022 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43213
3 | MIR | SPML-KCM-MIR-0023 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43215
3 | MIR | SPML-KCM-MIR-0024 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43216
3 | MIR | SPML-KCM-MIR-0025 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43216
3 | MIR | SPML-KCM-MIR-0026 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43222
3 | MIR | SPML-KCM-MIR-0027 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43226
3 | MIR | SPML-KCM-MIR-0028 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43226
3 | MIR | SPML-KCM-MIR-0029 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43232
3 | MIR | SPML-KCM-MIR-0030 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43237
3 | MIR | SPML-KCM-MIR-0031 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43251
3 | MIR | SPML-KCM-MIR-0032 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43253
3 | MIR | SPML-KCM-MIR-0033 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43248
3 | MIR | SPML-KCM-MIR-0034 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43251
3 | MIR | SPML-KCM-MIR-0035 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43251
3 | MIR | SPML-KCM-MIR-0036 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43253
3 | MIR | SPML-KCM-MIR-0037 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43255
3 | MIR | SPML-KCM-MIR-0038 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43269
3 | MIR | SPML-KCM-MIR-0039 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43269
3 | MIR | SPML-KCM-MIR-0040 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43269
3 | MIR | SPML-KCM-MIR-0041 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43269
3 | MIR | SPML-KCM-MIR-0042 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43269
3 | MIR | SPML-KCM-MIR-0043 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43272
3 | MIR | SPML-KCM-MIR-0044 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43272
3 | MIR | SPML-KCM-MIR-0045 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43272
3 | MIR | SPML-KCM-MIR-0046 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43272
3 | MIR | SPML-KCM-MIR-0047 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43277
3 | MIR | SPML-KCM-MIR-0048 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43277
3 | MIR | SPML-KCM-MIR-0049 | Finishes | Wooden Partition | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0049 | Finishes | Wooden Partition | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43279
3 | MIR | SPML-KCM-MIR-0050 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43300
3 | MIR | SPML-KCM-MIR-0051 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43312
3 | MIR | SPML-KCM-MIR-0052 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43312
3 | MIR | SPML-KCM-MIR-0053 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43316
3 | MIR | SPML-KCM-MIR-0054 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43316
3 | MIR | SPML-KCM-MIR-0055 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43316
3 | MIR | SPML-KCM-MIR-0056 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43316
3 | MIR | SPML-KCM-MIR-0057 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43319
3 | MIR | SPML-KCM-MIR-0058 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43320
3 | MIR | SPML-KCM-MIR-0059 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43323
3 | MIR | SPML-KCM-MIR-0060 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43323
3 | MIR | SPML-KCM-MIR-0061 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43323
3 | MIR | SPML-KCM-MIR-0062 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43326
3 | MIR | SPML-KCM-MIR-0063 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43326
3 | MIR | SPML-KCM-MIR-0064 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43326
3 | MIR | SPML-KCM-MIR-0065 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43326
3 | MIR | SPML-KCM-MIR-0066 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44111
3 | MIR | SPML-KCM-MIR-0066 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43327
3 | MIR | SPML-KCM-MIR-0067 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0067 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43330
3 | MIR | SPML-KCM-MIR-0068 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43331
3 | MIR | SPML-KCM-MIR-0069 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43330
3 | MIR | SPML-KCM-MIR-0070 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43330
3 | MIR | SPML-KCM-MIR-0071 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43330
3 | MIR | SPML-KCM-MIR-0072 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43331
3 | MIR | SPML-KCM-MIR-0073 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0073 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43335
3 | MIR | SPML-KCM-MIR-0074 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43335
3 | MIR | SPML-KCM-MIR-0075 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43335
3 | MIR | SPML-KCM-MIR-0076 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43338
3 | MIR | SPML-KCM-MIR-0077 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43338
3 | MIR | SPML-KCM-MIR-0078 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43341
3 | MIR | SPML-KCM-MIR-0079 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43347
3 | MIR | SPML-KCM-MIR-0080 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43347
3 | MIR | SPML-KCM-MIR-0081 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43341
3 | MIR | SPML-KCM-MIR-0083 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43341
3 | MIR | SPML-KCM-MIR-0084 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43341
3 | MIR | SPML-KCM-MIR-0085 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43341
3 | MIR | SPML-KCM-MIR-0086 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43341
3 | MIR | SPML-KCM-MIR-0087 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43342
3 | MIR | SPML-KCM-MIR-0088 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43351
3 | MIR | SPML-KCM-MIR-0089 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43351
3 | MIR | SPML-KCM-MIR-0090 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43358
3 | MIR | SPML-KCM-MIR-0091 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43358
3 | MIR | SPML-KCM-MIR-0092 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43359
3 | MIR | SPML-KCM-MIR-0093 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43359
3 | MIR | SPML-KCM-MIR-0094 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43359
3 | MIR | SPML-KCM-MIR-0095 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43359
3 | MIR | SPML-KCM-MIR-0095A | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43367
3 | MIR | SPML-KCM-MIR-0096 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43361
3 | MIR | SPML-KCM-MIR-0097 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43362
3 | MIR | SPML-KCM-MIR-0098 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43367
3 | MIR | SPML-KCM-MIR-0099 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43367
3 | MIR | SPML-KCM-MIR-0100 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43374
3 | MIR | SPML-KCM-MIR-0101 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44142
3 | MIR | SPML-KCM-MIR-0101 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43368
3 | MIR | SPML-KCM-MIR-0102 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43374
3 | MIR | SPML-KCM-MIR-0103 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43384
3 | MIR | SPML-KCM-MIR-0104 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43384
3 | MIR | SPML-KCM-MIR-0105 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43390
3 | MIR | SPML-KCM-MIR-0106 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43397
3 | MIR | SPML-KCM-MIR-0107 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43397
3 | MIR | SPML-KCM-MIR-0108 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43397
3 | MIR | SPML-KCM-MIR-0109 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43397
3 | MIR | SPML-KCM-MIR-0110 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43400
3 | MIR | SPML-KCM-MIR-0111 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43400
3 | MIR | SPML-KCM-MIR-0112 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43401
3 | MIR | SPML-KCM-MIR-0113 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43402
3 | MIR | SPML-KCM-MIR-0114 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43402
3 | MIR | SPML-KCM-MIR-0115 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0115 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43405
3 | MIR | SPML-KCM-MIR-0115 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0116 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43407
3 | MIR | SPML-KCM-MIR-0117 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43408
3 | MIR | SPML-KCM-MIR-0118 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43408
3 | MIR | SPML-KCM-MIR-0119 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43411
3 | MIR | SPML-KCM-MIR-0120 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0120 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43416
3 | MIR | SPML-KCM-MIR-0121 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43416
3 | MIR | SPML-KCM-MIR-0122 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43424
3 | MIR | SPML-KCM-MIR-0123 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43424
3 | MIR | SPML-KCM-MIR-0124 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43424
3 | MIR | SPML-KCM-MIR-0125 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43425
3 | MIR | SPML-KCM-MIR-0126 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43430
3 | MIR | SPML-KCM-MIR-0127 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43430
3 | MIR | SPML-KCM-MIR-0127A | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43430
3 | MIR | SPML-KCM-MIR-0128 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43430
3 | MIR | SPML-KCM-MIR-0129 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43433
3 | MIR | SPML-KCM-MIR-0130 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43424
3 | MIR | SPML-KCM-MIR-0131 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43430
3 | MIR | SPML-KCM-MIR-0132 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43430
3 | MIR | SPML-KCM-MIR-0133 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43433
3 | MIR | SPML-KCM-MIR-0134 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43433
3 | MIR | SPML-KCM-MIR-0135 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43433
3 | MIR | SPML-KCM-MIR-0136 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43434
3 | MIR | SPML-KCM-MIR-0137 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43465
3 | MIR | SPML-KCM-MIR-0138 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0138 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43467
3 | MIR | SPML-KCM-MIR-0138 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0139 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43470
3 | MIR | SPML-KCM-MIR-0139 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43467
3 | MIR | SPML-KCM-MIR-0140 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43468
3 | MIR | SPML-KCM-MIR-0141 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43468
3 | MIR | SPML-KCM-MIR-0142 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0142 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43468
3 | MIR | SPML-KCM-MIR-0142 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0143 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0143 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43470
3 | MIR | SPML-KCM-MIR-0144 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43470
3 | MIR | SPML-KCM-MIR-0145 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43470
3 | MIR | SPML-KCM-MIR-0146 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0146 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43471
3 | MIR | SPML-KCM-MIR-0147 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43472
3 | MIR | SPML-KCM-MIR-0148 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43472
3 | MIR | SPML-KCM-MIR-0149 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43473
3 | MIR | SPML-KCM-MIR-0150 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43473
3 | MIR | SPML-KCM-MIR-0151 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44111
3 | MIR | SPML-KCM-MIR-0151 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43475
3 | MIR | SPML-KCM-MIR-0152 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43475
3 | MIR | SPML-KCM-MIR-0153 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43474
3 | MIR | SPML-KCM-MIR-0154 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43477
3 | MIR | SPML-KCM-MIR-0155 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43477
3 | MIR | SPML-KCM-MIR-0156 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43477
3 | MIR | SPML-KCM-MIR-0157 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43478
3 | MIR | SPML-KCM-MIR-0158 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43477
3 | MIR | SPML-KCM-MIR-0159 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43479
3 | MIR | SPML-KCM-MIR-0160 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43480
3 | MIR | SPML-KCM-MIR-0161 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43480
3 | MIR | SPML-KCM-MIR-0162 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43480
3 | MIR | SPML-KCM-MIR-0163 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43481
3 | MIR | SPML-KCM-MIR-0164 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43482
3 | MIR | SPML-KCM-MIR-0165 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43484
3 | MIR | SPML-KCM-MIR-0166 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43484
3 | MIR | SPML-KCM-MIR-0167 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43487
3 | MIR | SPML-KCM-MIR-0168 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0168 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43489
3 | MIR | SPML-KCM-MIR-0168 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0169 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43489
3 | MIR | SPML-KCM-MIR-0170 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0170 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43492
3 | MIR | SPML-KCM-MIR-0171 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43492
3 | MIR | SPML-KCM-MIR-0172 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43492
3 | MIR | SPML-KCM-MIR-0173 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43493
3 | MIR | SPML-KCM-MIR-0174 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44111
3 | MIR | SPML-KCM-MIR-0174 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43494
3 | MIR | SPML-KCM-MIR-0175 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0175 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43494
3 | MIR | SPML-KCM-MIR-0175 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0176 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43494
3 | MIR | SPML-KCM-MIR-0177 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43495
3 | MIR | SPML-KCM-MIR-0178 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0178 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43495
3 | MIR | SPML-KCM-MIR-0179 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43496
3 | MIR | SPML-KCM-MIR-0181 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43498
3 | MIR | SPML-KCM-MIR-0182 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43498
3 | MIR | SPML-KCM-MIR-0183 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44111
3 | MIR | SPML-KCM-MIR-0183 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43499
3 | MIR | SPML-KCM-MIR-0184 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44116
3 | MIR | SPML-KCM-MIR-0184 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43499
3 | MIR | SPML-KCM-MIR-0184 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0185 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43499
3 | MIR | SPML-KCM-MIR-0186 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43500
3 | MIR | SPML-KCM-MIR-0187 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43501
3 | MIR | SPML-KCM-MIR-0188 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43501
3 | MIR | SPML-KCM-MIR-0189 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44111
3 | MIR | SPML-KCM-MIR-0189 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43501
3 | MIR | SPML-KCM-MIR-0190 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43501
3 | MIR | SPML-KCM-MIR-0191 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43501
3 | MIR | SPML-KCM-MIR-0192 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43503
3 | MIR | SPML-KCM-MIR-0193 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43505
3 | MIR | SPML-KCM-MIR-0194 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0194 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43506
3 | MIR | SPML-KCM-MIR-0195 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43507
3 | MIR | SPML-KCM-MIR-0196 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43508
3 | MIR | SPML-KCM-MIR-0197 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43666
3 | MIR | SPML-KCM-MIR-0197 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43509
3 | MIR | SPML-KCM-MIR-0198 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0198 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43508
3 | MIR | SPML-KCM-MIR-0199 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0199 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43510
3 | MIR | SPML-KCM-MIR-0200 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43510
3 | MIR | SPML-KCM-MIR-0201 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44248
3 | MIR | SPML-KCM-MIR-0201 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43512
3 | MIR | SPML-KCM-MIR-0202 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43512
3 | MIR | SPML-KCM-MIR-0203 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43512
3 | MIR | SPML-KCM-MIR-0204 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0204 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43513
3 | MIR | SPML-KCM-MIR-0205 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43513
3 | MIR | SPML-KCM-MIR-0206 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0206 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43515
3 | MIR | SPML-KCM-MIR-0207 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43516
3 | MIR | SPML-KCM-MIR-0208 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43516
3 | MIR | SPML-KCM-MIR-0209 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43517
3 | MIR | SPML-KCM-MIR-0210 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0210 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43519
3 | MIR | SPML-KCM-MIR-0211 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44146
3 | MIR | SPML-KCM-MIR-0211 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43519
3 | MIR | SPML-KCM-MIR-0212 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43519
3 | MIR | SPML-KCM-MIR-0213 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0213 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43521
3 | MIR | SPML-KCM-MIR-0214 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43522
3 | MIR | SPML-KCM-MIR-0215 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0215 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43522
3 | MIR | SPML-KCM-MIR-0216 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43522
3 | MIR | SPML-KCM-MIR-0217 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43523
3 | MIR | SPML-KCM-MIR-0218 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43523
3 | MIR | SPML-KCM-MIR-0219 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43523
3 | MIR | SPML-KCM-MIR-0220 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0220 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43527
3 | MIR | SPML-KCM-MIR-0221 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43527
3 | MIR | SPML-KCM-MIR-0222 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43527
3 | MIR | SPML-KCM-MIR-0223 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0223 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43527
3 | MIR | SPML-KCM-MIR-0224 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43528
3 | MIR | SPML-KCM-MIR-0225 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43528
3 | MIR | SPML-KCM-MIR-0226 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43528
3 | MIR | SPML-KCM-MIR-0227 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43528
3 | MIR | SPML-KCM-MIR-0228 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43529
3 | MIR | SPML-KCM-MIR-0229 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0229 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43528
3 | MIR | SPML-KCM-MIR-0230 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43530
3 | MIR | SPML-KCM-MIR-0231 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0231 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43530
3 | MIR | SPML-KCM-MIR-0232 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43530
3 | MIR | SPML-KCM-MIR-0233 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43531
3 | MIR | SPML-KCM-MIR-0234 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43531
3 | MIR | SPML-KCM-MIR-0235 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0235 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43533
3 | MIR | SPML-KCM-MIR-0236 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43533
3 | MIR | SPML-KCM-MIR-0237 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43533
3 | MIR | SPML-KCM-MIR-0238 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43534
3 | MIR | SPML-KCM-MIR-0239 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43534
3 | MIR | SPML-KCM-MIR-0240 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43534
3 | MIR | SPML-KCM-MIR-0241 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43535
3 | MIR | SPML-KCM-MIR-0242 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0242 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43535
3 | MIR | SPML-KCM-MIR-0243 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43535
3 | MIR | SPML-KCM-MIR-0244 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0244 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43538
3 | MIR | SPML-KCM-MIR-0245 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43538
3 | MIR | SPML-KCM-MIR-0246 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43538
3 | MIR | SPML-KCM-MIR-0247 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43538
3 | MIR | SPML-KCM-MIR-0247R1 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43549
3 | MIR | SPML-KCM-MIR-0247R2 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43666
3 | MIR | SPML-KCM-MIR-0248 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0248 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43542
3 | MIR | SPML-KCM-MIR-0249 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43545
3 | MIR | SPML-KCM-MIR-0250 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43548
3 | MIR | SPML-KCM-MIR-0251 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44174
3 | MIR | SPML-KCM-MIR-0251 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43548
3 | MIR | SPML-KCM-MIR-0252 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43550
3 | MIR | SPML-KCM-MIR-0252R1 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43550
3 | MIR | SPML-KCM-MIR-0253 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43653
3 | MIR | SPML-KCM-MIR-0253 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43552
3 | MIR | SPML-KCM-MIR-0254 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43552
3 | MIR | SPML-KCM-MIR-0255 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43552
3 | MIR | SPML-KCM-MIR-0256 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43552
3 | MIR | SPML-KCM-MIR-0256R1 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43552
3 | MIR | SPML-KCM-MIR-0257 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43963
3 | MIR | SPML-KCM-MIR-0257 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43552
3 | MIR | SPML-KCM-MIR-0258 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43556
3 | MIR | SPML-KCM-MIR-0259 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43557
3 | MIR | SPML-KCM-MIR-0260 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43559
3 | MIR | SPML-KCM-MIR-0261 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43562
3 | MIR | SPML-KCM-MIR-0262 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43563
3 | MIR | SPML-KCM-MIR-0263 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0263 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43564
3 | MIR | SPML-KCM-MIR-0264 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0264 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43968
3 | MIR | SPML-KCM-MIR-0264 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43564
3 | MIR | SPML-KCM-MIR-0264 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43666
3 | MIR | SPML-KCM-MIR-0264 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43811
3 | MIR | SPML-KCM-MIR-0265 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43565
3 | MIR | SPML-KCM-MIR-0266 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0266 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43565
3 | MIR | SPML-KCM-MIR-0267 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43565
3 | MIR | SPML-KCM-MIR-0268 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43653
3 | MIR | SPML-KCM-MIR-0268 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43566
3 | MIR | SPML-KCM-MIR-0269 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43569
3 | MIR | SPML-KCM-MIR-0270 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43571
3 | MIR | SPML-KCM-MIR-0271 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0271 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43572
3 | MIR | SPML-KCM-MIR-0272 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43572
3 | MIR | SPML-KCM-MIR-0273 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43573
3 | MIR | SPML-KCM-MIR-0274 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43576
3 | MIR | SPML-KCM-MIR-0275 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0275 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43844
3 | MIR | SPML-KCM-MIR-0275 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43969
3 | MIR | SPML-KCM-MIR-0275 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43577
3 | MIR | SPML-KCM-MIR-0276 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43578
3 | MIR | SPML-KCM-MIR-0277 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43579
3 | MIR | SPML-KCM-MIR-0278 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0278 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43579
3 | MIR | SPML-KCM-MIR-0279 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43580
3 | MIR | SPML-KCM-MIR-0280 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44111
3 | MIR | SPML-KCM-MIR-0280 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43580
3 | MIR | SPML-KCM-MIR-0281 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43580
3 | MIR | SPML-KCM-MIR-0282 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43583
3 | MIR | SPML-KCM-MIR-0283 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0283 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43580
3 | MIR | SPML-KCM-MIR-0284 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43583
3 | MIR | SPML-KCM-MIR-0285 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43583
3 | MIR | SPML-KCM-MIR-0286 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43584
3 | MIR | SPML-KCM-MIR-0287 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0287 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43584
3 | MIR | SPML-KCM-MIR-0288 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43585
3 | MIR | SPML-KCM-MIR-0289 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43585
3 | MIR | SPML-KCM-MIR-0290 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43586
3 | MIR | SPML-KCM-MIR-0291 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43590
3 | MIR | SPML-KCM-MIR-0292 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0292 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43591
3 | MIR | SPML-KCM-MIR-0293 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43591
3 | MIR | SPML-KCM-MIR-0294 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43592
3 | MIR | SPML-KCM-MIR-0295 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0295 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43593
3 | MIR | SPML-KCM-MIR-0296 | Finishes | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0296 | Finishes | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43597
3 | MIR | SPML-KCM-MIR-0296 | Finishes | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43594
3 | MIR | SPML-KCM-MIR-0297 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43594
3 | MIR | SPML-KCM-MIR-0298 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43600
3 | MIR | SPML-KCM-MIR-0299 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43603
3 | MIR | SPML-KCM-MIR-0300 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43607
3 | MIR | SPML-KCM-MIR-0301 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43608
3 | MIR | SPML-KCM-MIR-0302 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43610
3 | MIR | SPML-KCM-MIR-0303 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43816
3 | MIR | SPML-KCM-MIR-0303 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43614
3 | MIR | SPML-KCM-MIR-0304 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43666
3 | MIR | SPML-KCM-MIR-0304 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43614
3 | MIR | SPML-KCM-MIR-0305 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43614
3 | MIR | SPML-KCM-MIR-0306 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43614
3 | MIR | SPML-KCM-MIR-0307 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43615
3 | MIR | SPML-KCM-MIR-0308 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43615
3 | MIR | SPML-KCM-MIR-0309 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43587
3 | MIR | SPML-KCM-MIR-0310 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43751
3 | MIR | SPML-KCM-MIR-0310 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43625
3 | MIR | SPML-KCM-MIR-0311 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43652
3 | MIR | SPML-KCM-MIR-0311 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43627
3 | MIR | SPML-KCM-MIR-0312 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43751
3 | MIR | SPML-KCM-MIR-0312 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43627
3 | MIR | SPML-KCM-MIR-0313 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43652
3 | MIR | SPML-KCM-MIR-0313 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43628
3 | MIR | SPML-KCM-MIR-0314 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43804
3 | MIR | SPML-KCM-MIR-0314 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43635
3 | MIR | SPML-KCM-MIR-0315 | Lift System | Escalator | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44131
3 | MIR | SPML-KCM-MIR-0315 | Lift System | Escalator | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43631
3 | MIR | SPML-KCM-MIR-0316 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43963
3 | MIR | SPML-KCM-MIR-0316 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43632
3 | MIR | SPML-KCM-MIR-0317 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43660
3 | MIR | SPML-KCM-MIR-0317 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43633
3 | MIR | SPML-KCM-MIR-0318 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0318 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43599
3 | MIR | SPML-KCM-MIR-0319 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43683
3 | MIR | SPML-KCM-MIR-0319 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43636
3 | MIR | SPML-KCM-MIR-0319 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43642
3 | MIR | SPML-KCM-MIR-0320 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43652
3 | MIR | SPML-KCM-MIR-0321 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43844
3 | MIR | SPML-KCM-MIR-0321 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43640
3 | MIR | SPML-KCM-MIR-0322 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0322 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43640
3 | MIR | SPML-KCM-MIR-0323 | Lift System | Elevator | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44131
3 | MIR | SPML-KCM-MIR-0323 | Lift System | Elevator | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43640
3 | MIR | SPML-KCM-MIR-0324 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43642
3 | MIR | SPML-KCM-MIR-0325 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0325 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43844
3 | MIR | SPML-KCM-MIR-0325 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43969
3 | MIR | SPML-KCM-MIR-0325 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43642
3 | MIR | SPML-KCM-MIR-0326 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43683
3 | MIR | SPML-KCM-MIR-0326 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43642
3 | MIR | SPML-KCM-MIR-0327 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0327 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43844
3 | MIR | SPML-KCM-MIR-0327 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43969
3 | MIR | SPML-KCM-MIR-0327 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43643
3 | MIR | SPML-KCM-MIR-0328 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0328 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43645
3 | MIR | SPML-KCM-MIR-0329 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44115
3 | MIR | SPML-KCM-MIR-0329 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43645
3 | MIR | SPML-KCM-MIR-0330 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43971
3 | MIR | SPML-KCM-MIR-0330 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43647
3 | MIR | SPML-KCM-MIR-0331 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43653
3 | MIR | SPML-KCM-MIR-0331 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43648
3 | MIR | SPML-KCM-MIR-0332 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43683
3 | MIR | SPML-KCM-MIR-0332 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43650
3 | MIR | SPML-KCM-MIR-0333 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44174
3 | MIR | SPML-KCM-MIR-0333 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43650
3 | MIR | SPML-KCM-MIR-0334 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43654
3 | MIR | SPML-KCM-MIR-0335 | Lift System | Travalator | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44131
3 | MIR | SPML-KCM-MIR-0335 | Lift System | Travalator | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43656
3 | MIR | SPML-KCM-MIR-0336 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43663
3 | MIR | SPML-KCM-MIR-0336 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43656
3 | MIR | SPML-KCM-MIR-0337 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43663
3 | MIR | SPML-KCM-MIR-0337 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43657
3 | MIR | SPML-KCM-MIR-0338 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43657
3 | MIR | SPML-KCM-MIR-0339 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MIR-0339 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43657
3 | MIR | SPML-KCM-MIR-0340 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43664
3 | MIR | SPML-KCM-MIR-0341 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43664
3 | MIR | SPML-KCM-MIR-0342 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43669
3 | MIR | SPML-KCM-MIR-0343 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44115
3 | MIR | SPML-KCM-MIR-0343 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43670
3 | MIR | SPML-KCM-MIR-0344 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43670
3 | MIR | SPML-KCM-MIR-0345 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44135
3 | MIR | SPML-KCM-MIR-0345 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43745
3 | MIR | SPML-KCM-MIR-0345 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43671
3 | MIR | SPML-KCM-MIR-0346 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43674
3 | MIR | SPML-KCM-MIR-0347 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44080
3 | MIR | SPML-KCM-MIR-0347 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43674
3 | MIR | SPML-KCM-MIR-0348 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43677
3 | MIR | SPML-KCM-MIR-0349 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43681
3 | MIR | SPML-KCM-MIR-0350 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43681
3 | MIR | SPML-KCM-MIR-0351 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43683
3 | MIR | SPML-KCM-MIR-0352 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43694
3 | MIR | SPML-KCM-MIR-0353 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43696
3 | MIR | SPML-KCM-MIR-0354 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43745
3 | MIR | SPML-KCM-MIR-0354 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43696
3 | MIR | SPML-KCM-MIR-0355 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44115
3 | MIR | SPML-KCM-MIR-0355 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43697
3 | MIR | SPML-KCM-MIR-0356 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43698
3 | MIR | SPML-KCM-MIR-0357 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43698
3 | MIR | SPML-KCM-MIR-0358 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43699
3 | MIR | SPML-KCM-MIR-0359 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43702
3 | MIR | SPML-KCM-MIR-0360 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43702
3 | MIR | SPML-KCM-MIR-0361 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43702
3 | MIR | SPML-KCM-MIR-0362 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43705
3 | MIR | SPML-KCM-MIR-0363 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43704
3 | MIR | SPML-KCM-MIR-0364 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43709
3 | MIR | SPML-KCM-MIR-0365 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43710
3 | MIR | SPML-KCM-MIR-0366 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0366 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43710
3 | MIR | SPML-KCM-MIR-0367 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43712
3 | MIR | SPML-KCM-MIR-0368 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43713
3 | MIR | SPML-KCM-MIR-0369 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43713
3 | MIR | SPML-KCM-MIR-0370 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0370 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43722
3 | MIR | SPML-KCM-MIR-0370 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44109
3 | MIR | SPML-KCM-MIR-0371 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0371 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43716
3 | MIR | SPML-KCM-MIR-0372 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44126
3 | MIR | SPML-KCM-MIR-0372 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43716
3 | MIR | SPML-KCM-MIR-0373 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0373 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43853
3 | MIR | SPML-KCM-MIR-0373 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43716
3 | MIR | SPML-KCM-MIR-0374 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43718
3 | MIR | SPML-KCM-MIR-0375 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43719
3 | MIR | SPML-KCM-MIR-0376 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43719
3 | MIR | SPML-KCM-MIR-0377 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43722
3 | MIR | SPML-KCM-MIR-0378 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44115
3 | MIR | SPML-KCM-MIR-0378 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43719
3 | MIR | SPML-KCM-MIR-0379 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43722
3 | MIR | SPML-KCM-MIR-0380 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43720
3 | MIR | SPML-KCM-MIR-0381 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43722
3 | MIR | SPML-KCM-MIR-0382 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0382 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43724
3 | MIR | SPML-KCM-MIR-0383 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0383 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43725
3 | MIR | SPML-KCM-MIR-0384 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0384 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43725
3 | MIR | SPML-KCM-MIR-0385 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43729
3 | MIR | SPML-KCM-MIR-0386 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0386 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43729
3 | MIR | SPML-KCM-MIR-0386 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44109
3 | MIR | SPML-KCM-MIR-0387 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0387 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43729
3 | MIR | SPML-KCM-MIR-0388 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0388 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43745
3 | MIR | SPML-KCM-MIR-0388 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43734
3 | MIR | SPML-KCM-MIR-0389 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0389 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43865
3 | MIR | SPML-KCM-MIR-0389 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43734
3 | MIR | SPML-KCM-MIR-0390 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0390 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43829
3 | MIR | SPML-KCM-MIR-0390 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43752
3 | MIR | SPML-KCM-MIR-0390 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43734
3 | MIR | SPML-KCM-MIR-0391 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0391 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43865
3 | MIR | SPML-KCM-MIR-0391 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43734
3 | MIR | SPML-KCM-MIR-0392 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43740
3 | MIR | SPML-KCM-MIR-0393 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0393 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43740
3 | MIR | SPML-KCM-MIR-0394 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0394 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43799
3 | MIR | SPML-KCM-MIR-0394 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43740
3 | MIR | SPML-KCM-MIR-0395 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43740
3 | MIR | SPML-KCM-MIR-0396 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43740
3 | MIR | SPML-KCM-MIR-0397 | ELV | CPMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44152
3 | MIR | SPML-KCM-MIR-0397 | ELV | CPMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43741
3 | MIR | SPML-KCM-MIR-0398 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43747
3 | MIR | SPML-KCM-MIR-0399 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0399 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43747
3 | MIR | SPML-KCM-MIR-0400 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43748
3 | MIR | SPML-KCM-MIR-0401 | Landscaping | Irrigation System | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44128
3 | MIR | SPML-KCM-MIR-0401 | Landscaping | Irrigation System | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43762
3 | MIR | SPML-KCM-MIR-0401 | Landscaping | Irrigation System | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 43750
3 | MIR | SPML-KCM-MIR-0402 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43751
3 | MIR | SPML-KCM-MIR-0403 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0403 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43750
3 | MIR | SPML-KCM-MIR-0404 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43963
3 | MIR | SPML-KCM-MIR-0404 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43754
3 | MIR | SPML-KCM-MIR-0404 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43804
3 | MIR | SPML-KCM-MIR-0405 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0405 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43829
3 | MIR | SPML-KCM-MIR-0405 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43752
3 | MIR | SPML-KCM-MIR-0406 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0406 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43752
3 | MIR | SPML-KCM-MIR-0407 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0407 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43752
3 | MIR | SPML-KCM-MIR-0408 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0408 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43799
3 | MIR | SPML-KCM-MIR-0408 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43752
3 | MIR | SPML-KCM-MIR-0409 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43799
3 | MIR | SPML-KCM-MIR-0409 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43753
3 | MIR | SPML-KCM-MIR-0410 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44038
3 | MIR | SPML-KCM-MIR-0410 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43753
3 | MIR | SPML-KCM-MIR-0411 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43753
3 | MIR | SPML-KCM-MIR-0412 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43754
3 | MIR | SPML-KCM-MIR-0413 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43757
3 | MIR | SPML-KCM-MIR-0414 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0414 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43799
3 | MIR | SPML-KCM-MIR-0414 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43757
3 | MIR | SPML-KCM-MIR-0415 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43760
3 | MIR | SPML-KCM-MIR-0416 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43760
3 | MIR | SPML-KCM-MIR-0417 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44172
3 | MIR | SPML-KCM-MIR-0417 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43762
3 | MIR | SPML-KCM-MIR-0418 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43762
3 | MIR | SPML-KCM-MIR-0419 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43762
3 | MIR | SPML-KCM-MIR-0420 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43762
3 | MIR | SPML-KCM-MIR-0421 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0421 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43762
3 | MIR | SPML-KCM-MIR-0422 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44173
3 | MIR | SPML-KCM-MIR-0422 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43762
3 | MIR | SPML-KCM-MIR-0423 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43762
3 | MIR | SPML-KCM-MIR-0424 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43764
3 | MIR | SPML-KCM-MIR-0425 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43765
3 | MIR | SPML-KCM-MIR-0426 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43766
3 | MIR | SPML-KCM-MIR-0427 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43766
3 | MIR | SPML-KCM-MIR-0428 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43766
3 | MIR | SPML-KCM-MIR-0429 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43767
3 | MIR | SPML-KCM-MIR-0430 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43767
3 | MIR | SPML-KCM-MIR-0431 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43789
3 | MIR | SPML-KCM-MIR-0432 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44157
3 | MIR | SPML-KCM-MIR-0432 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43781
3 | MIR | SPML-KCM-MIR-0432 | Loading Bay Equipment System | Overhead Door | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43768
3 | MIR | SPML-KCM-MIR-0433 | Finishes | Aluminium profile | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0433 | Finishes | Aluminium profile | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43768
3 | MIR | SPML-KCM-MIR-0434 | Finishes | Louvre | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0434 | Finishes | Louvre | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43848
3 | MIR | SPML-KCM-MIR-0434 | Finishes | Louvre | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43814
3 | MIR | SPML-KCM-MIR-0434 | Finishes | Louvre | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43768
3 | MIR | SPML-KCM-MIR-0435 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0435 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43799
3 | MIR | SPML-KCM-MIR-0435 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43768
3 | MIR | SPML-KCM-MIR-0436 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43771
3 | MIR | SPML-KCM-MIR-0437 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0437 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43769
3 | MIR | SPML-KCM-MIR-0438 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43771
3 | MIR | SPML-KCM-MIR-0439 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44109
3 | MIR | SPML-KCM-MIR-0439 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43771
3 | MIR | SPML-KCM-MIR-0440 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44146
3 | MIR | SPML-KCM-MIR-0440 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43771
3 | MIR | SPML-KCM-MIR-0441 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43771
3 | MIR | SPML-KCM-MIR-0442 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43771
3 | MIR | SPML-KCM-MIR-0443 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43771
3 | MIR | SPML-KCM-MIR-0444 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0444 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43772
3 | MIR | SPML-KCM-MIR-0445 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43772
3 | MIR | SPML-KCM-MIR-0446 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43774
3 | MIR | SPML-KCM-MIR-0447 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43774
3 | MIR | SPML-KCM-MIR-0448 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43774
3 | MIR | SPML-KCM-MIR-0449 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43774
3 | MIR | SPML-KCM-MIR-0450 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0450 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43774
3 | MIR | SPML-KCM-MIR-0451 | Finishes | Epoxy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0451 | Finishes | Epoxy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43774
3 | MIR | SPML-KCM-MIR-0452 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43774
3 | MIR | SPML-KCM-MIR-0453 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43774
3 | MIR | SPML-KCM-MIR-0454 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0454 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43829
3 | MIR | SPML-KCM-MIR-0454 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43774
3 | MIR | SPML-KCM-MIR-0455 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43774
3 | MIR | SPML-KCM-MIR-0456 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43774
3 | MIR | SPML-KCM-MIR-0457 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44244
3 | MIR | SPML-KCM-MIR-0457 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 44186
3 | MIR | SPML-KCM-MIR-0457 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43774
3 | MIR | SPML-KCM-MIR-0457 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43804
3 | MIR | SPML-KCM-MIR-0457 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43814
3 | MIR | SPML-KCM-MIR-0458 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43774
3 | MIR | SPML-KCM-MIR-0459 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0459 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43779
3 | MIR | SPML-KCM-MIR-0460 | Manhole | Manhole | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0460 | Manhole | Manhole | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43779
3 | MIR | SPML-KCM-MIR-0461 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43781
3 | MIR | SPML-KCM-MIR-0462 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43781
3 | MIR | SPML-KCM-MIR-0463 | Finishes | Raised Floor | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0463 | Finishes | Raised Floor | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43781
3 | MIR | SPML-KCM-MIR-0464 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44109
3 | MIR | SPML-KCM-MIR-0464 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43781
3 | MIR | SPML-KCM-MIR-0465 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43783
3 | MIR | SPML-KCM-MIR-0466 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44136
3 | MIR | SPML-KCM-MIR-0466 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43783
3 | MIR | SPML-KCM-MIR-0467 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0467 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43799
3 | MIR | SPML-KCM-MIR-0467 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43783
3 | MIR | SPML-KCM-MIR-0468 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0468 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43783
3 | MIR | SPML-KCM-MIR-0469 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0469 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43783
3 | MIR | SPML-KCM-MIR-0470 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43783
3 | MIR | SPML-KCM-MIR-0471 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43783
3 | MIR | SPML-KCM-MIR-0472 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43783
3 | MIR | SPML-KCM-MIR-0473 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0473 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43783
3 | MIR | SPML-KCM-MIR-0474 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0474 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43783
3 | MIR | SPML-KCM-MIR-0475 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43785
3 | MIR | SPML-KCM-MIR-0476 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43785
3 | MIR | SPML-KCM-MIR-0477 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43785
3 | MIR | SPML-KCM-MIR-0478 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0478 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43787
3 | MIR | SPML-KCM-MIR-0479 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43785
3 | MIR | SPML-KCM-MIR-0480 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44135
3 | MIR | SPML-KCM-MIR-0480 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43785
3 | MIR | SPML-KCM-MIR-0481 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44118
3 | MIR | SPML-KCM-MIR-0481 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43788
3 | MIR | SPML-KCM-MIR-0482 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43789
3 | MIR | SPML-KCM-MIR-0483 | Finishes | Aqua Panel | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43789
3 | MIR | SPML-KCM-MIR-0484 | Finishes | Louvre | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0484 | Finishes | Louvre | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43790
3 | MIR | SPML-KCM-MIR-0485 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43792
3 | MIR | SPML-KCM-MIR-0486 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43793
3 | MIR | SPML-KCM-MIR-0487 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43793
3 | MIR | SPML-KCM-MIR-0488 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43796
3 | MIR | SPML-KCM-MIR-0488 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43793
3 | MIR | SPML-KCM-MIR-0489 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0489 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43794
3 | MIR | SPML-KCM-MIR-0490 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43794
3 | MIR | SPML-KCM-MIR-0491 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44115
3 | MIR | SPML-KCM-MIR-0491 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43794
3 | MIR | SPML-KCM-MIR-0492 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44244
3 | MIR | SPML-KCM-MIR-0492 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44186
3 | MIR | SPML-KCM-MIR-0492 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43785
3 | MIR | SPML-KCM-MIR-0492 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43794
3 | MIR | SPML-KCM-MIR-0493 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0493 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43814
3 | MIR | SPML-KCM-MIR-0493 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43794
3 | MIR | SPML-KCM-MIR-0494 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0494 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43794
3 | MIR | SPML-KCM-MIR-0495 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
3 | MIR | SPML-KCM-MIR-0495 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43794
3 | MIR | SPML-KCM-MIR-0496 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44146
3 | MIR | SPML-KCM-MIR-0496 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43794
3 | MIR | SPML-KCM-MIR-0498 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43795
3 | MIR | SPML-KCM-MIR-0499 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43795
3 | MIR | SPML-KCM-MIR-0500 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43795
3 | MIR | SPML-KCM-MIR-0501 | Finishes | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43795
3 | MIR | SPML-KCM-MIR-0502 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0502 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43795
3 | MIR | SPML-KCM-MIR-0503 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0503 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43796
3 | MIR | SPML-KCM-MIR-0504 | Finishes | Aluminium profile | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0504 | Finishes | Aluminium profile | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43796
3 | MIR | SPML-KCM-MIR-0505 | Finishes | Aqua Panel | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43796
3 | MIR | SPML-KCM-MIR-0506 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44080
3 | MIR | SPML-KCM-MIR-0506 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43797
3 | MIR | SPML-KCM-MIR-0507 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0507 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43797
3 | MIR | SPML-KCM-MIR-0508 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43865
3 | MIR | SPML-KCM-MIR-0508 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43797
3 | MIR | SPML-KCM-MIR-0509 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43797
3 | MIR | SPML-KCM-MIR-0510 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43799
3 | MIR | SPML-KCM-MIR-0511 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43799
3 | MIR | SPML-KCM-MIR-0512 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43799
3 | MIR | SPML-KCM-MIR-0513 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0513 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43874
3 | MIR | SPML-KCM-MIR-0513 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0513 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43797
3 | MIR | SPML-KCM-MIR-0514 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44117
3 | MIR | SPML-KCM-MIR-0514 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43846
3 | MIR | SPML-KCM-MIR-0514 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0514 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43799
3 | MIR | SPML-KCM-MIR-0514 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43843
3 | MIR | SPML-KCM-MIR-0515 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0515 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43803
3 | MIR | SPML-KCM-MIR-0517 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0517 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43814
3 | MIR | SPML-KCM-MIR-0517 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43804
3 | MIR | SPML-KCM-MIR-0518 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44109
3 | MIR | SPML-KCM-MIR-0518 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43804
3 | MIR | SPML-KCM-MIR-0519 | Walls | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0519 | Walls | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43804
3 | MIR | SPML-KCM-MIR-0519 | Walls | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44109
3 | MIR | SPML-KCM-MIR-0519 | Walls | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44118
3 | MIR | SPML-KCM-MIR-0520 | Waste Management | Garbage Compactor | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44157
3 | MIR | SPML-KCM-MIR-0520 | Waste Management | Garbage Compactor | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43813
3 | MIR | SPML-KCM-MIR-0520 | Waste Management | Garbage Compactor | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43804
3 | MIR | SPML-KCM-MIR-0521 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44118
3 | MIR | SPML-KCM-MIR-0521 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43846
3 | MIR | SPML-KCM-MIR-0521 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0521 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43806
3 | MIR | SPML-KCM-MIR-0521 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43843
3 | MIR | SPML-KCM-MIR-0522 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44117
3 | MIR | SPML-KCM-MIR-0522 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43806
3 | MIR | SPML-KCM-MIR-0522 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0523 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43809
3 | MIR | SPML-KCM-MIR-0524 | Finishes | Aluminium profile | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0524 | Finishes | Aluminium profile | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43809
3 | MIR | SPML-KCM-MIR-0525 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0525 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43809
3 | MIR | SPML-KCM-MIR-0526 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43809
3 | MIR | SPML-KCM-MIR-0527 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43810
3 | MIR | SPML-KCM-MIR-0528 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44116
3 | MIR | SPML-KCM-MIR-0528 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43821
3 | MIR | SPML-KCM-MIR-0528 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43811
3 | MIR | SPML-KCM-MIR-0531 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44109
3 | MIR | SPML-KCM-MIR-0531 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43813
3 | MIR | SPML-KCM-MIR-0532 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0532 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43863
3 | MIR | SPML-KCM-MIR-0532 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0532 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43813
3 | MIR | SPML-KCM-MIR-0532 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43827
3 | MIR | SPML-KCM-MIR-0533 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44174
3 | MIR | SPML-KCM-MIR-0533 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43948
3 | MIR | SPML-KCM-MIR-0534 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43815
3 | MIR | SPML-KCM-MIR-0535 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43815
3 | MIR | SPML-KCM-MIR-0536 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44112
3 | MIR | SPML-KCM-MIR-0536 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43819
3 | MIR | SPML-KCM-MIR-0537 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43816
3 | MIR | SPML-KCM-MIR-0538 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43971
3 | MIR | SPML-KCM-MIR-0539 | Finishes | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43821
3 | MIR | SPML-KCM-MIR-0540 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44136
3 | MIR | SPML-KCM-MIR-0540 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43821
3 | MIR | SPML-KCM-MIR-0540 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44111
3 | MIR | SPML-KCM-MIR-0541 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44136
3 | MIR | SPML-KCM-MIR-0541 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43821
3 | MIR | SPML-KCM-MIR-0542 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44038
3 | MIR | SPML-KCM-MIR-0542 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43828
3 | MIR | SPML-KCM-MIR-0543 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43821
3 | MIR | SPML-KCM-MIR-0545 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43823
3 | MIR | SPML-KCM-MIR-0546 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43823
3 | MIR | SPML-KCM-MIR-0547 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43823
3 | MIR | SPML-KCM-MIR-0550 | Finishes | Aqua Panel | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43825
3 | MIR | SPML-KCM-MIR-0551 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43874
3 | MIR | SPML-KCM-MIR-0551 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43828
3 | MIR | SPML-KCM-MIR-0552 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44118
3 | MIR | SPML-KCM-MIR-0552 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43827
3 | MIR | SPML-KCM-MIR-0553 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44244
3 | MIR | SPML-KCM-MIR-0553 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43827
3 | MIR | SPML-KCM-MIR-0553 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43851
3 | MIR | SPML-KCM-MIR-0553 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 44186
3 | MIR | SPML-KCM-MIR-0554 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43828
3 | MIR | SPML-KCM-MIR-0555 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43828
3 | MIR | SPML-KCM-MIR-0556 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43828
3 | MIR | SPML-KCM-MIR-0557 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43828
3 | MIR | SPML-KCM-MIR-0558 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44244
3 | MIR | SPML-KCM-MIR-0558 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43923
3 | MIR | SPML-KCM-MIR-0558 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 44191
3 | MIR | SPML-KCM-MIR-0558 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | D | 43829
3 | MIR | SPML-KCM-MIR-0559 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44139
3 | MIR | SPML-KCM-MIR-0559 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 44033
3 | MIR | SPML-KCM-MIR-0559 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43828
3 | MIR | SPML-KCM-MIR-0560 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43828
3 | MIR | SPML-KCM-MIR-0561 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0561 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43926
3 | MIR | SPML-KCM-MIR-0561 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43829
3 | MIR | SPML-KCM-MIR-0562 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0562 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 44174
3 | MIR | SPML-KCM-MIR-0562 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43829
3 | MIR | SPML-KCM-MIR-0563 | Finishes | Aqua Panel | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43829
3 | MIR | SPML-KCM-MIR-0564 | Finishes | Aluminium profile | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0564 | Finishes | Aluminium profile | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43830
3 | MIR | SPML-KCM-MIR-0565 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0566 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44118
3 | MIR | SPML-KCM-MIR-0566 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43830
3 | MIR | SPML-KCM-MIR-0567 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43830
3 | MIR | SPML-KCM-MIR-0569 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43834
3 | MIR | SPML-KCM-MIR-0571 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43834
3 | MIR | SPML-KCM-MIR-0572 | Finishes | Aluminium profile | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0572 | Finishes | Aluminium profile | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43834
3 | MIR | SPML-KCM-MIR-0573 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0573 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43834
3 | MIR | SPML-KCM-MIR-0574 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43995
3 | MIR | SPML-KCM-MIR-0574 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43834
3 | MIR | SPML-KCM-MIR-0575 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44200
3 | MIR | SPML-KCM-MIR-0575 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43845
3 | MIR | SPML-KCM-MIR-0575 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44188
3 | MIR | SPML-KCM-MIR-0575 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43836
3 | MIR | SPML-KCM-MIR-0575 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43841
3 | MIR | SPML-KCM-MIR-0576 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0576 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43856
3 | MIR | SPML-KCM-MIR-0577 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43841
3 | MIR | SPML-KCM-MIR-0578 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43841
3 | MIR | SPML-KCM-MIR-0579 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44174
3 | MIR | SPML-KCM-MIR-0579 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43841
3 | MIR | SPML-KCM-MIR-0580 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43839
3 | MIR | SPML-KCM-MIR-0581 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44118
3 | MIR | SPML-KCM-MIR-0581 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43839
3 | MIR | SPML-KCM-MIR-0582 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0582 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43841
3 | MIR | SPML-KCM-MIR-0583 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0583 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43853
3 | MIR | SPML-KCM-MIR-0583 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43841
3 | MIR | SPML-KCM-MIR-0584 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44146
3 | MIR | SPML-KCM-MIR-0584 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43923
3 | MIR | SPML-KCM-MIR-0584 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44109
3 | MIR | SPML-KCM-MIR-0584 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43841
3 | MIR | SPML-KCM-MIR-0585 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43843
3 | MIR | SPML-KCM-MIR-0586 | Finishes | Aqua Panel | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43843
3 | MIR | SPML-KCM-MIR-0587 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43843
3 | MIR | SPML-KCM-MIR-0588 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43844
3 | MIR | SPML-KCM-MIR-0589 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43844
3 | MIR | SPML-KCM-MIR-0592 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0592 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43846
3 | MIR | SPML-KCM-MIR-0593 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0593 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43846
3 | MIR | SPML-KCM-MIR-0594 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0594 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43846
3 | MIR | SPML-KCM-MIR-0595 | Doors & Windows | Sliding Door | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0595 | Doors & Windows | Sliding Door | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44090
3 | MIR | SPML-KCM-MIR-0595 | Doors & Windows | Sliding Door | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0595 | Doors & Windows | Sliding Door | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43846
3 | MIR | SPML-KCM-MIR-0595 | Doors & Windows | Sliding Door | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43923
3 | MIR | SPML-KCM-MIR-0596 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44107
3 | MIR | SPML-KCM-MIR-0596 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43846
3 | MIR | SPML-KCM-MIR-0596 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0597 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43848
3 | MIR | SPML-KCM-MIR-0598 | Finishes | Aqua Panel | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43848
3 | MIR | SPML-KCM-MIR-0599 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44111
3 | MIR | SPML-KCM-MIR-0599 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43963
3 | MIR | SPML-KCM-MIR-0599 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43848
3 | MIR | SPML-KCM-MIR-0600 | Walls | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0600 | Walls | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43848
3 | MIR | SPML-KCM-MIR-0600 | Walls | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44112
3 | MIR | SPML-KCM-MIR-0601 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0601 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43923
3 | MIR | SPML-KCM-MIR-0601 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43849
3 | MIR | SPML-KCM-MIR-0602 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0602 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43923
3 | MIR | SPML-KCM-MIR-0602 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43849
3 | MIR | SPML-KCM-MIR-0603 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43911
3 | MIR | SPML-KCM-MIR-0603 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43850
3 | MIR | SPML-KCM-MIR-0608 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43850
3 | MIR | SPML-KCM-MIR-0609 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43850
3 | MIR | SPML-KCM-MIR-0610 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0610 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43850
3 | MIR | SPML-KCM-MIR-0610 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0611 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43850
3 | MIR | SPML-KCM-MIR-0612 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0612 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43851
3 | MIR | SPML-KCM-MIR-0613 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43852
3 | MIR | SPML-KCM-MIR-0615 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43853
3 | MIR | SPML-KCM-MIR-0616 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0616 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43923
3 | MIR | SPML-KCM-MIR-0616 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43853
3 | MIR | SPML-KCM-MIR-0617 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0617 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43923
3 | MIR | SPML-KCM-MIR-0617 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 44109
3 | MIR | SPML-KCM-MIR-0617 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | D | 43853
3 | MIR | SPML-KCM-MIR-0618 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0618 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43853
3 | MIR | SPML-KCM-MIR-0622 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43853
3 | MIR | SPML-KCM-MIR-0623 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43911
3 | MIR | SPML-KCM-MIR-0623 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43856
3 | MIR | SPML-KCM-MIR-0623 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43895
3 | MIR | SPML-KCM-MIR-0629 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0629 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43858
3 | MIR | SPML-KCM-MIR-0631 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43858
3 | MIR | SPML-KCM-MIR-0632 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43858
3 | MIR | SPML-KCM-MIR-0633 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43950
3 | MIR | SPML-KCM-MIR-0633 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43858
3 | MIR | SPML-KCM-MIR-0639 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43859
3 | MIR | SPML-KCM-MIR-0639 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44118
3 | MIR | SPML-KCM-MIR-0642 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0642 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43862
3 | MIR | SPML-KCM-MIR-0642 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0643 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0643 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43864
3 | MIR | SPML-KCM-MIR-0644 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44244
3 | MIR | SPML-KCM-MIR-0644 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43866
3 | MIR | SPML-KCM-MIR-0645 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43866
3 | MIR | SPML-KCM-MIR-0646 | Finishes | Acrylic Coating | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0646 | Finishes | Acrylic Coating | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43997
3 | MIR | SPML-KCM-MIR-0646 | Finishes | Acrylic Coating | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43869
3 | MIR | SPML-KCM-MIR-0647 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43867
3 | MIR | SPML-KCM-MIR-0648 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43870
3 | MIR | SPML-KCM-MIR-0649 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43870
3 | MIR | SPML-KCM-MIR-0650 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0650 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43870
3 | MIR | SPML-KCM-MIR-0657 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43871
3 | MIR | SPML-KCM-MIR-0658 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44128
3 | MIR | SPML-KCM-MIR-0658 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43872
3 | MIR | SPML-KCM-MIR-0658 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44110
3 | MIR | SPML-KCM-MIR-0659 | Finishes | Wooden Partition | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0659 | Finishes | Wooden Partition | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43921
3 | MIR | SPML-KCM-MIR-0659 | Finishes | Wooden Partition | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43872
3 | MIR | SPML-KCM-MIR-0659 | Finishes | Wooden Partition | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43898
3 | MIR | SPML-KCM-MIR-0660 | Finishes | Armour Coat | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0660 | Finishes | Armour Coat | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43919
3 | MIR | SPML-KCM-MIR-0660 | Finishes | Armour Coat | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 43872
3 | MIR | SPML-KCM-MIR-0661 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0661 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43872
3 | MIR | SPML-KCM-MIR-0661 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0664 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43873
3 | MIR | SPML-KCM-MIR-0667 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 44186
3 | MIR | SPML-KCM-MIR-0667 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43873
3 | MIR | SPML-KCM-MIR-0668 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0668 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43873
3 | MIR | SPML-KCM-MIR-0676 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43874
3 | MIR | SPML-KCM-MIR-0680 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43877
3 | MIR | SPML-KCM-MIR-0681 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0681 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43877
3 | MIR | SPML-KCM-MIR-0682 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44244
3 | MIR | SPML-KCM-MIR-0682 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43877
3 | MIR | SPML-KCM-MIR-0682 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 44186
3 | MIR | SPML-KCM-MIR-0688 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44112
3 | MIR | SPML-KCM-MIR-0688 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43879
3 | MIR | SPML-KCM-MIR-0689 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43879
3 | MIR | SPML-KCM-MIR-0690 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43879
3 | MIR | SPML-KCM-MIR-0691 | Finishes | Armour Coat | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0691 | Finishes | Armour Coat | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43879
3 | MIR | SPML-KCM-MIR-0692 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0692 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43879
3 | MIR | SPML-KCM-MIR-0693 | Finishes | Acrylic Coating | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43879
3 | MIR | SPML-KCM-MIR-0694 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0694 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43879
3 | MIR | SPML-KCM-MIR-0701 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44174
3 | MIR | SPML-KCM-MIR-0701 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43884
3 | MIR | SPML-KCM-MIR-0702 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43948
3 | MIR | SPML-KCM-MIR-0703 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0703 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43884
3 | MIR | SPML-KCM-MIR-0715 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43888
3 | MIR | SPML-KCM-MIR-0716 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0716 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43888
3 | MIR | SPML-KCM-MIR-0717 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44118
3 | MIR | SPML-KCM-MIR-0717 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43916
3 | MIR | SPML-KCM-MIR-0717 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43888
3 | MIR | SPML-KCM-MIR-0718 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43904
3 | MIR | SPML-KCM-MIR-0718 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | D | 43888
3 | MIR | SPML-KCM-MIR-0721 | Finishes | Aqua Panel | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43888
3 | MIR | SPML-KCM-MIR-0726 | Finishes | Vanity Countertop | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43898
3 | MIR | SPML-KCM-MIR-0728 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43901
3 | MIR | SPML-KCM-MIR-0740 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43906
3 | MIR | SPML-KCM-MIR-0743 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43908
3 | MIR | SPML-KCM-MIR-0743 | Upgrade | Upgrade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43908
3 | MIR | SPML-KCM-MIR-0747 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43911
3 | MIR | SPML-KCM-MIR-0748 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44109
3 | MIR | SPML-KCM-MIR-0748 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43911
3 | MIR | SPML-KCM-MIR-0749 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43914
3 | MIR | SPML-KCM-MIR-0749 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | D | 43912
3 | MIR | SPML-KCM-MIR-0750 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44138
3 | MIR | SPML-KCM-MIR-0750 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43912
3 | MIR | SPML-KCM-MIR-0750 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44114
3 | MIR | SPML-KCM-MIR-0755 | General | General | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44174
3 | MIR | SPML-KCM-MIR-0755 | General | General | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43916
3 | MIR | SPML-KCM-MIR-0756 | Finishes | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44174
3 | MIR | SPML-KCM-MIR-0756 | Finishes | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | D | 43916
3 | MIR | SPML-KCM-MIR-0757 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43916
3 | MIR | SPML-KCM-MIR-0758 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43918
3 | MIR | SPML-KCM-MIR-0761 | Finishes | Epoxy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0761 | Finishes | Epoxy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43919
3 | MIR | SPML-KCM-MIR-0762 | Finishes | Stone Carpet | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0762 | Finishes | Stone Carpet | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43919
3 | MIR | SPML-KCM-MIR-0763 | Cladding | ACP Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43919
3 | MIR | SPML-KCM-MIR-0764 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43919
3 | MIR | SPML-KCM-MIR-0765 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43919
3 | MIR | SPML-KCM-MIR-0766 | General | General | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43919
3 | MIR | SPML-KCM-MIR-0768 | Finishes | Vanity Countertop | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43920
3 | MIR | SPML-KCM-MIR-0769 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44191
3 | MIR | SPML-KCM-MIR-0769 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43920
3 | MIR | SPML-KCM-MIR-0770 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44157
3 | MIR | SPML-KCM-MIR-0770 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43921
3 | MIR | SPML-KCM-MIR-0772 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43926
3 | MIR | SPML-KCM-MIR-0773 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0773 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43926
3 | MIR | SPML-KCM-MIR-0774 | Finishes | Vanity Countertop | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43926
3 | MIR | SPML-KCM-MIR-0782 | Finishes | Baffle Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44109
3 | MIR | SPML-KCM-MIR-0782 | Finishes | Baffle Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43925
3 | MIR | SPML-KCM-MIR-0784 | Finishes | Wooden Partition | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0784 | Finishes | Wooden Partition | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43928
3 | MIR | SPML-KCM-MIR-0785 | Cladding | ACP Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44126
3 | MIR | SPML-KCM-MIR-0785 | Cladding | ACP Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43928
3 | MIR | SPML-KCM-MIR-0786 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44110
3 | MIR | SPML-KCM-MIR-0786 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43932
3 | MIR | SPML-KCM-MIR-0787 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44118
3 | MIR | SPML-KCM-MIR-0787 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43932
3 | MIR | SPML-KCM-MIR-0788 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43932
3 | MIR | SPML-KCM-MIR-0789 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0789 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43932
3 | MIR | SPML-KCM-MIR-0793 | Finishes | Gypsum Wall | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43933
3 | MIR | SPML-KCM-MIR-0794 | General | General | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43934
3 | MIR | SPML-KCM-MIR-0795 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44174
3 | MIR | SPML-KCM-MIR-0795 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43935
3 | MIR | SPML-KCM-MIR-0796 | Finishes | Vanity Countertop | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43937
3 | MIR | SPML-KCM-MIR-0797 | Finishes | Vanity Countertop | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43937
3 | MIR | SPML-KCM-MIR-0798 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43937
3 | MIR | SPML-KCM-MIR-0800 | Cladding | ACP Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43941
3 | MIR | SPML-KCM-MIR-0801 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43942
3 | MIR | SPML-KCM-MIR-0808 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43943
3 | MIR | SPML-KCM-MIR-0809 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43943
3 | MIR | SPML-KCM-MIR-0810 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43944
3 | MIR | SPML-KCM-MIR-0813 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43948
3 | MIR | SPML-KCM-MIR-0814 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43954
3 | MIR | SPML-KCM-MIR-0815 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43954
3 | MIR | SPML-KCM-MIR-0817 | General | General | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43955
3 | MIR | SPML-KCM-MIR-0834 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43971
3 | MIR | SPML-KCM-MIR-0836 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44140
3 | MIR | SPML-KCM-MIR-0836 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43972
3 | MIR | SPML-KCM-MIR-0839 | Finishes | Wooden Partition | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44114
3 | MIR | SPML-KCM-MIR-0839 | Finishes | Wooden Partition | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43979
3 | MIR | SPML-KCM-MIR-0842 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43990
3 | MIR | SPML-KCM-MIR-0851 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44002
3 | MIR | SPML-KCM-MIR-0858 | Waste Management | Garbage Compactor | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44142
3 | MIR | SPML-KCM-MIR-0858 | Waste Management | Garbage Compactor | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 44014
3 | MIR | SPML-KCM-MIR-0859 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44018
3 | MIR | SPML-KCM-MIR-0861 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44026
3 | MIR | SPML-KCM-MIR-0865 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44031
3 | MIR | SPML-KCM-MIR-0866 | Cladding | ACP Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44031
3 | MIR | SPML-KCM-MIR-0867 | Finishes | Stone Carpet | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44037
3 | MIR | SPML-KCM-MIR-0869 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0869 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 44039
3 | MIR | SPML-KCM-MIR-0870 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44055
3 | MIR | SPML-KCM-MIR-0871 | Finishes | Aqua Panel | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44055
3 | MIR | SPML-KCM-MIR-0874 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44075
3 | MIR | SPML-KCM-MIR-0876 | Pole | Flag Pole | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0876 | Pole | Flag Pole | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44087
3 | MIR | SPML-KCM-MIR-0877 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44093
3 | MIR | SPML-KCM-MIR-0878 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44116
3 | MIR | SPML-KCM-MIR-0879 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44105
3 | MIR | SPML-KCM-MIR-0880 | Finishes | Stone Carpet | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44107
3 | MIR | SPML-KCM-MIR-0881 | Cladding | ACP Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43925
3 | MIR | SPML-KCM-MIR-0882 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0882 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44097
3 | MIR | SPML-KCM-MIR-0883 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44149
3 | MIR | SPML-KCM-MIR-0883 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 44098
3 | MIR | SPML-KCM-MIR-0884 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44116
3 | MIR | SPML-KCM-MIR-0887 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0887 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44123
3 | MIR | SPML-KCM-MIR-0888 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44126
3 | MIR | SPML-KCM-MIR-0889 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44126
3 | MIR | SPML-KCM-MIR-0890 | General | General | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44126
3 | MIR | SPML-KCM-MIR-0891 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44135
3 | MIR | SPML-KCM-MIR-0892 | Finishes | Canopy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44244
3 | MIR | SPML-KCM-MIR-0892 | Finishes | Canopy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 44137
3 | MIR | SPML-KCM-MIR-0893 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44244
3 | MIR | SPML-KCM-MIR-0893 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 44152
3 | MIR | SPML-KCM-MIR-0894 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44518
3 | MIR | SPML-KCM-MIR-0894 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | C | 44152
3 | MIR | SPML-KCM-MIR-0895 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0895 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44152
3 | MIR | SPML-KCM-MIR-0896 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44172
3 | MIR | SPML-KCM-MIR-0897 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44172
3 | MIR | SPML-KCM-MIR-0898 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44172
3 | MIR | SPML-KCM-MIR-0899 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44172
3 | MIR | SPML-KCM-MIR-0900 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0901 | Cladding | ACP Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44173
3 | MIR | SPML-KCM-MIR-0902 | Cladding | ACP Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0903 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44173
3 | MIR | SPML-KCM-MIR-0904 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44173
3 | MIR | SPML-KCM-MIR-0905 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44173
3 | MIR | SPML-KCM-MIR-0906 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44173
3 | MIR | SPML-KCM-MIR-0907 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0908 | Walls | Plaster Works | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0909 | Finishes | Vanity Countertop | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0910 | Finishes | Vanity Countertop | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0911 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0912 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0913 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0914 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0915 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44173
3 | MIR | SPML-KCM-MIR-0916 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44173
3 | MIR | SPML-KCM-MIR-0917 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44173
3 | MIR | SPML-KCM-MIR-0919 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0920 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0921 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0922 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0923 | Finishes | Aqua Panel | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0924 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0925 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
3 | MIR | SPML-KCM-MIR-0926 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0927 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0928 | Paving System | Kerb Stone | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0929 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0930 | Finishes | Floor Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0931 | Floor | Grouting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0933 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0934 | Finishes | Stone Carpet | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0935 | General | General | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
3 | MIR | SPML-KCM-MIR-0936 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44254
3 | MIR | SPML-KCM-MIR-0936 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 44185
3 | MIR | SPML-KCM-MIR-0937 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0937 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44174
3 | MIR | SPML-KCM-MIR-0938 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
3 | MIR | SPML-KCM-MIR-0938 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 44179
3 | MIR | SPML-KCM-MIR-0939 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44244
3 | MIR | SPML-KCM-MIR-0939 | Foundation | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 44180
3 | MIR | SPML-KCM-MIR-0940 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44244
3 | MIR | SPML-KCM-MIR-0941 | Glazing | Glass Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44244
4 | WIR | SPML-KCM-A-IR- 2616 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43510
4 | WIR | SPML-KCM-A-IR- 2642 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-A-IR- 2643 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-A-IR- 2644 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-A-IR- 2677 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43517
4 | WIR | SPML-KCM-A-IR- 2678 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-A-IR- 2679 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-A-IR- 2680 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43517
4 | WIR | SPML-KCM-A-IR- 2697 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR- 2698 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43521
4 | WIR | SPML-KCM-A-IR- 2699 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43519
4 | WIR | SPML-KCM-A-IR- 2700 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43519
4 | WIR | SPML-KCM-A-IR- 2701 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR- 2713 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43522
4 | WIR | SPML-KCM-A-IR- 2715 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-A-IR- 2716 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-A-IR- 2717 | Foundation | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43633
4 | WIR | SPML-KCM-A-IR- 2729 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43498
4 | WIR | SPML-KCM-A-IR- 2735 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43523
4 | WIR | SPML-KCM-A-IR- 2736 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43526
4 | WIR | SPML-KCM-A-IR- 2739 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-A-IR- 2746 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43526
4 | WIR | SPML-KCM-A-IR- 2747 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-A-IR- 2748 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-A-IR- 2768 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43527
4 | WIR | SPML-KCM-A-IR- 2770 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43527
4 | WIR | SPML-KCM-A-IR- 2793 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43529
4 | WIR | SPML-KCM-A-IR- 2795 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43529
4 | WIR | SPML-KCM-A-IR- 2797 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43529
4 | WIR | SPML-KCM-A-IR- 2800 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 2802 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43530
4 | WIR | SPML-KCM-A-IR- 2815 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43533
4 | WIR | SPML-KCM-A-IR- 2822 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43533
4 | WIR | SPML-KCM-A-IR- 2823 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43533
4 | WIR | SPML-KCM-A-IR- 2824 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 2884 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43541
4 | WIR | SPML-KCM-A-IR- 2896 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43541
4 | WIR | SPML-KCM-A-IR- 2899 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43542
4 | WIR | SPML-KCM-A-IR- 2917 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 2918 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43544
4 | WIR | SPML-KCM-A-IR- 2936 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43548
4 | WIR | SPML-KCM-A-IR- 2942 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43548
4 | WIR | SPML-KCM-A-IR- 2944 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 2966 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-A-IR- 2967 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-A-IR- 2972 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-A-IR- 2977 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43558
4 | WIR | SPML-KCM-A-IR- 2985 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43551
4 | WIR | SPML-KCM-A-IR- 2986 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-A-IR- 2987 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-A-IR- 2992 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43552
4 | WIR | SPML-KCM-A-IR- 2995 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-A-IR- 2996 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-A-IR- 2998 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-A-IR- 3014 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43555
4 | WIR | SPML-KCM-A-IR- 3015 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43555
4 | WIR | SPML-KCM-A-IR- 3016 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43555
4 | WIR | SPML-KCM-A-IR- 3018 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | C | 43555
4 | WIR | SPML-KCM-A-IR- 3029 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-A-IR- 3030 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-A-IR- 3035 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-A-IR- 3036 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43559
4 | WIR | SPML-KCM-A-IR- 3037 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-A-IR- 3042 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43558
4 | WIR | SPML-KCM-A-IR- 3050 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43606
4 | WIR | SPML-KCM-A-IR- 3051 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43561
4 | WIR | SPML-KCM-A-IR- 3058 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43561
4 | WIR | SPML-KCM-A-IR- 3059 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43561
4 | WIR | SPML-KCM-A-IR- 3060 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-A-IR- 3061 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43561
4 | WIR | SPML-KCM-A-IR- 3063 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-A-IR- 3069 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43565
4 | WIR | SPML-KCM-A-IR- 3070 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43563
4 | WIR | SPML-KCM-A-IR- 3082 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-A-IR- 3083 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-A-IR- 3084 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43563
4 | WIR | SPML-KCM-A-IR- 3085 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43606
4 | WIR | SPML-KCM-A-IR- 3086 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43639
4 | WIR | SPML-KCM-A-IR- 3090 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43606
4 | WIR | SPML-KCM-A-IR- 3096 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43564
4 | WIR | SPML-KCM-A-IR- 3097 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43564
4 | WIR | SPML-KCM-A-IR- 3101 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44138
4 | WIR | SPML-KCM-A-IR- 3103 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43565
4 | WIR | SPML-KCM-A-IR- 3104 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43565
4 | WIR | SPML-KCM-A-IR- 3108 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44138
4 | WIR | SPML-KCM-A-IR- 3109 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43566
4 | WIR | SPML-KCM-A-IR- 3115 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43569
4 | WIR | SPML-KCM-A-IR- 3116 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43569
4 | WIR | SPML-KCM-A-IR- 3117 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43569
4 | WIR | SPML-KCM-A-IR- 3118 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43569
4 | WIR | SPML-KCM-A-IR- 3119 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43569
4 | WIR | SPML-KCM-A-IR- 3120 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43569
4 | WIR | SPML-KCM-A-IR- 3121 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43569
4 | WIR | SPML-KCM-A-IR- 3131 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43570
4 | WIR | SPML-KCM-A-IR- 3134 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43571
4 | WIR | SPML-KCM-A-IR- 3135 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43571
4 | WIR | SPML-KCM-A-IR- 3136 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43571
4 | WIR | SPML-KCM-A-IR- 3143 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43571
4 | WIR | SPML-KCM-A-IR- 3145 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43571
4 | WIR | SPML-KCM-A-IR- 3152 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43572
4 | WIR | SPML-KCM-A-IR- 3157 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43573
4 | WIR | SPML-KCM-A-IR- 3158 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43573
4 | WIR | SPML-KCM-A-IR- 3160 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43914
4 | WIR | SPML-KCM-A-IR- 3161 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43589
4 | WIR | SPML-KCM-A-IR- 3179 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43575
4 | WIR | SPML-KCM-A-IR- 3181 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43639
4 | WIR | SPML-KCM-A-IR- 3190 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43576
4 | WIR | SPML-KCM-A-IR- 3191 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43576
4 | WIR | SPML-KCM-A-IR- 3192 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43576
4 | WIR | SPML-KCM-A-IR- 3194 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43577
4 | WIR | SPML-KCM-A-IR- 3222 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43579
4 | WIR | SPML-KCM-A-IR- 3223 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43579
4 | WIR | SPML-KCM-A-IR- 3231 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43580
4 | WIR | SPML-KCM-A-IR- 3242 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR- 3244 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-A-IR- 3245 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43582
4 | WIR | SPML-KCM-A-IR- 3246 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43582
4 | WIR | SPML-KCM-A-IR- 3247 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43582
4 | WIR | SPML-KCM-A-IR- 3248 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43582
4 | WIR | SPML-KCM-A-IR- 3249 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43914
4 | WIR | SPML-KCM-A-IR- 3272 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-A-IR- 3278 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43649
4 | WIR | SPML-KCM-A-IR- 3279 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43585
4 | WIR | SPML-KCM-A-IR- 3296 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43586
4 | WIR | SPML-KCM-A-IR- 3297 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43586
4 | WIR | SPML-KCM-A-IR- 3300 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-A-IR- 3301 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43587
4 | WIR | SPML-KCM-A-IR- 3303 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43587
4 | WIR | SPML-KCM-A-IR- 3308 | Floor | Grouting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43587
4 | WIR | SPML-KCM-A-IR- 3310 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43589
4 | WIR | SPML-KCM-A-IR- 3311 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43589
4 | WIR | SPML-KCM-A-IR- 3312 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43914
4 | WIR | SPML-KCM-A-IR- 3316 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-A-IR- 3317 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-A-IR- 3331 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43645
4 | WIR | SPML-KCM-A-IR- 3332 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43914
4 | WIR | SPML-KCM-A-IR- 3337 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43914
4 | WIR | SPML-KCM-A-IR- 3338 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-A-IR- 3339 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43593
4 | WIR | SPML-KCM-A-IR- 3340 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43593
4 | WIR | SPML-KCM-A-IR- 3342 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43594
4 | WIR | SPML-KCM-A-IR- 3343 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43803
4 | WIR | SPML-KCM-A-IR- 3344 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43594
4 | WIR | SPML-KCM-A-IR- 3345 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43594
4 | WIR | SPML-KCM-A-IR- 3346 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43594
4 | WIR | SPML-KCM-A-IR- 3357 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 3359 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43918
4 | WIR | SPML-KCM-A-IR- 3361 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43598
4 | WIR | SPML-KCM-A-IR- 3362 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43598
4 | WIR | SPML-KCM-A-IR- 3363 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43598
4 | WIR | SPML-KCM-A-IR- 3364 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43598
4 | WIR | SPML-KCM-A-IR- 3370 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43918
4 | WIR | SPML-KCM-A-IR- 3371 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43601
4 | WIR | SPML-KCM-A-IR- 3372 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43609
4 | WIR | SPML-KCM-A-IR- 3373 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 3374 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43599
4 | WIR | SPML-KCM-A-IR- 3375 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43918
4 | WIR | SPML-KCM-A-IR- 3381 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43600
4 | WIR | SPML-KCM-A-IR- 3382 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43838
4 | WIR | SPML-KCM-A-IR- 3384 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43600
4 | WIR | SPML-KCM-A-IR- 3385 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43600
4 | WIR | SPML-KCM-A-IR- 3389 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43605
4 | WIR | SPML-KCM-A-IR- 3390 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43603
4 | WIR | SPML-KCM-A-IR- 3391 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43748
4 | WIR | SPML-KCM-A-IR- 3392 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43603
4 | WIR | SPML-KCM-A-IR- 3393 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43603
4 | WIR | SPML-KCM-A-IR- 3399 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43604
4 | WIR | SPML-KCM-A-IR- 3403 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43605
4 | WIR | SPML-KCM-A-IR- 3404 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43605
4 | WIR | SPML-KCM-A-IR- 3406 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43605
4 | WIR | SPML-KCM-A-IR- 3407 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43605
4 | WIR | SPML-KCM-A-IR- 3408 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43658
4 | WIR | SPML-KCM-A-IR- 3416 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43606
4 | WIR | SPML-KCM-A-IR- 3417 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43606
4 | WIR | SPML-KCM-A-IR- 3419 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43789
4 | WIR | SPML-KCM-A-IR- 3423 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43608
4 | WIR | SPML-KCM-A-IR- 3424 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43608
4 | WIR | SPML-KCM-A-IR- 3425 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43608
4 | WIR | SPML-KCM-A-IR- 3426 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43608
4 | WIR | SPML-KCM-A-IR- 3432 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43635
4 | WIR | SPML-KCM-A-IR- 3433 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43789
4 | WIR | SPML-KCM-A-IR- 3434 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43610
4 | WIR | SPML-KCM-A-IR- 3451 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43789
4 | WIR | SPML-KCM-A-IR- 3452 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43613
4 | WIR | SPML-KCM-A-IR- 3453 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43614
4 | WIR | SPML-KCM-A-IR- 3455 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43614
4 | WIR | SPML-KCM-A-IR- 3456 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43614
4 | WIR | SPML-KCM-A-IR- 3457 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43999
4 | WIR | SPML-KCM-A-IR- 3461 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 3463 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43615
4 | WIR | SPML-KCM-A-IR- 3465 | Car Park | Car Park Shade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43615
4 | WIR | SPML-KCM-A-IR- 3468 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43624
4 | WIR | SPML-KCM-A-IR- 3475 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43624
4 | WIR | SPML-KCM-A-IR- 3482 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 3483 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43951
4 | WIR | SPML-KCM-A-IR- 3487 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43625
4 | WIR | SPML-KCM-A-IR- 3488 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43625
4 | WIR | SPML-KCM-A-IR- 3490 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43625
4 | WIR | SPML-KCM-A-IR- 3491 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43625
4 | WIR | SPML-KCM-A-IR- 3492 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43764
4 | WIR | SPML-KCM-A-IR- 3495 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 3500 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43625
4 | WIR | SPML-KCM-A-IR- 3501 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43625
4 | WIR | SPML-KCM-A-IR- 3502 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43625
4 | WIR | SPML-KCM-A-IR- 3504 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43632
4 | WIR | SPML-KCM-A-IR- 3511 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43632
4 | WIR | SPML-KCM-A-IR- 3518 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43632
4 | WIR | SPML-KCM-A-IR- 3524 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43629
4 | WIR | SPML-KCM-A-IR- 3525 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43629
4 | WIR | SPML-KCM-A-IR- 3528 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43631
4 | WIR | SPML-KCM-A-IR- 3529 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43631
4 | WIR | SPML-KCM-A-IR- 3530 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43631
4 | WIR | SPML-KCM-A-IR- 3531 | Finishes | Mirror | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43631
4 | WIR | SPML-KCM-A-IR- 3532 | Finishes | Vanity Countertop | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43631
4 | WIR | SPML-KCM-A-IR- 3533 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43631
4 | WIR | SPML-KCM-A-IR- 3534 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43631
4 | WIR | SPML-KCM-A-IR- 3535 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43631
4 | WIR | SPML-KCM-A-IR- 3536 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43631
4 | WIR | SPML-KCM-A-IR- 3537 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43631
4 | WIR | SPML-KCM-A-IR- 3543 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43631
4 | WIR | SPML-KCM-A-IR- 3548 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43645
4 | WIR | SPML-KCM-A-IR- 3549 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43632
4 | WIR | SPML-KCM-A-IR- 3550 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43789
4 | WIR | SPML-KCM-A-IR- 3552 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43789
4 | WIR | SPML-KCM-A-IR- 3555 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43633
4 | WIR | SPML-KCM-A-IR- 3556 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43633
4 | WIR | SPML-KCM-A-IR- 3557 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43633
4 | WIR | SPML-KCM-A-IR- 3565 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43634
4 | WIR | SPML-KCM-A-IR- 3566 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-A-IR- 3569 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43634
4 | WIR | SPML-KCM-A-IR- 3570 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43634
4 | WIR | SPML-KCM-A-IR- 3571 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44095
4 | WIR | SPML-KCM-A-IR- 3572 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43634
4 | WIR | SPML-KCM-A-IR- 3573 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43634
4 | WIR | SPML-KCM-A-IR- 3576 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43635
4 | WIR | SPML-KCM-A-IR- 3577 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43635
4 | WIR | SPML-KCM-A-IR- 3578 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43635
4 | WIR | SPML-KCM-A-IR- 3579 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43635
4 | WIR | SPML-KCM-A-IR- 3580 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43635
4 | WIR | SPML-KCM-A-IR- 3581 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43635
4 | WIR | SPML-KCM-A-IR- 3582 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43639
4 | WIR | SPML-KCM-A-IR- 3583 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43813
4 | WIR | SPML-KCM-A-IR- 3584 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43790
4 | WIR | SPML-KCM-A-IR- 3593 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43636
4 | WIR | SPML-KCM-A-IR- 3594 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43639
4 | WIR | SPML-KCM-A-IR- 3595 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43636
4 | WIR | SPML-KCM-A-IR- 3596 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43636
4 | WIR | SPML-KCM-A-IR- 3597 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43639
4 | WIR | SPML-KCM-A-IR- 3599 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43639
4 | WIR | SPML-KCM-A-IR- 3600 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43639
4 | WIR | SPML-KCM-A-IR- 3602 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43642
4 | WIR | SPML-KCM-A-IR- 3605 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43790
4 | WIR | SPML-KCM-A-IR- 3609 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43643
4 | WIR | SPML-KCM-A-IR- 3610 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 3611 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43643
4 | WIR | SPML-KCM-A-IR- 3612 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43643
4 | WIR | SPML-KCM-A-IR- 3613 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43643
4 | WIR | SPML-KCM-A-IR- 3614 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43643
4 | WIR | SPML-KCM-A-IR- 3615 | Paving System | Kerb Stone | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43643
4 | WIR | SPML-KCM-A-IR- 3616 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43643
4 | WIR | SPML-KCM-A-IR- 3617 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43643
4 | WIR | SPML-KCM-A-IR- 3618 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43643
4 | WIR | SPML-KCM-A-IR- 3622 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43645
4 | WIR | SPML-KCM-A-IR- 3624 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43645
4 | WIR | SPML-KCM-A-IR- 3625 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43645
4 | WIR | SPML-KCM-A-IR- 3628 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-A-IR- 3629 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-A-IR- 3630 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-A-IR- 3631 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 3632 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-A-IR- 3633 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-A-IR- 3634 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-A-IR- 3635 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-A-IR- 3636 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-A-IR- 3637 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43718
4 | WIR | SPML-KCM-A-IR- 3638 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-A-IR- 3639 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-A-IR- 3640 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43939
4 | WIR | SPML-KCM-A-IR- 3641 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-A-IR- 3642 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-A-IR- 3643 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-A-IR- 3644 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 3645 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43649
4 | WIR | SPML-KCM-A-IR- 3648 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43650
4 | WIR | SPML-KCM-A-IR- 3649 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43674
4 | WIR | SPML-KCM-A-IR- 3650 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43647
4 | WIR | SPML-KCM-A-IR- 3651 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43650
4 | WIR | SPML-KCM-A-IR- 3655 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43649
4 | WIR | SPML-KCM-A-IR- 3656 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR- 3658 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43648
4 | WIR | SPML-KCM-A-IR- 3659 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR- 3660 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3662 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43645
4 | WIR | SPML-KCM-A-IR- 3667 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43642
4 | WIR | SPML-KCM-A-IR- 3668 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43640
4 | WIR | SPML-KCM-A-IR- 3669 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43816
4 | WIR | SPML-KCM-A-IR- 3673 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43723
4 | WIR | SPML-KCM-A-IR- 3674 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43790
4 | WIR | SPML-KCM-A-IR- 3675 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43850
4 | WIR | SPML-KCM-A-IR- 3676 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 3677 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 3682 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43678
4 | WIR | SPML-KCM-A-IR- 3684 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43641
4 | WIR | SPML-KCM-A-IR- 3691 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43642
4 | WIR | SPML-KCM-A-IR- 3692 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43650
4 | WIR | SPML-KCM-A-IR- 3694 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 3697 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43649
4 | WIR | SPML-KCM-A-IR- 3698 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43650
4 | WIR | SPML-KCM-A-IR- 3699 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43650
4 | WIR | SPML-KCM-A-IR- 3701 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3702 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3703 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3704 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43786
4 | WIR | SPML-KCM-A-IR- 3705 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3706 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3707 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43915
4 | WIR | SPML-KCM-A-IR- 3708 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43653
4 | WIR | SPML-KCM-A-IR- 3709 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-A-IR- 3710 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3711 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43655
4 | WIR | SPML-KCM-A-IR- 3712 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-A-IR- 3713 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3714 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR- 3717 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3718 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43731
4 | WIR | SPML-KCM-A-IR- 3719 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3720 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3721 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 3722 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-A-IR- 3723 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-A-IR- 3724 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43654
4 | WIR | SPML-KCM-A-IR- 3726 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3727 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43654
4 | WIR | SPML-KCM-A-IR- 3728 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43654
4 | WIR | SPML-KCM-A-IR- 3729 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43654
4 | WIR | SPML-KCM-A-IR- 3730 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 3731 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 3735 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43655
4 | WIR | SPML-KCM-A-IR- 3736 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43655
4 | WIR | SPML-KCM-A-IR- 3737 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43655
4 | WIR | SPML-KCM-A-IR- 3738 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43655
4 | WIR | SPML-KCM-A-IR- 3739 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43655
4 | WIR | SPML-KCM-A-IR- 3741 | GRP System | GRP Lining | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43661
4 | WIR | SPML-KCM-A-IR- 3743 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43656
4 | WIR | SPML-KCM-A-IR- 3744 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43656
4 | WIR | SPML-KCM-A-IR- 3745 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43656
4 | WIR | SPML-KCM-A-IR- 3746 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43656
4 | WIR | SPML-KCM-A-IR- 3747 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43656
4 | WIR | SPML-KCM-A-IR- 3748 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43656
4 | WIR | SPML-KCM-A-IR- 3749 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43656
4 | WIR | SPML-KCM-A-IR- 3751 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 3752 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43659
4 | WIR | SPML-KCM-A-IR- 3753 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43659
4 | WIR | SPML-KCM-A-IR- 3754 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43656
4 | WIR | SPML-KCM-A-IR- 3756 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43656
4 | WIR | SPML-KCM-A-IR- 3757 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43656
4 | WIR | SPML-KCM-A-IR- 3758 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43656
4 | WIR | SPML-KCM-A-IR- 3759 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43656
4 | WIR | SPML-KCM-A-IR- 3760 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43660
4 | WIR | SPML-KCM-A-IR- 3761 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 45868.3582
4 | WIR | SPML-KCM-A-IR- 3764 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-A-IR- 3767 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-A-IR- 3768 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 3769 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43915
4 | WIR | SPML-KCM-A-IR- 3770 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43915
4 | WIR | SPML-KCM-A-IR- 3771 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 3773 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43656
4 | WIR | SPML-KCM-A-IR- 3774 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43657
4 | WIR | SPML-KCM-A-IR- 3778 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 3779 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR- 3780 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-A-IR- 3781 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43659
4 | WIR | SPML-KCM-A-IR- 3782 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43659
4 | WIR | SPML-KCM-A-IR- 3783 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 3784 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43659
4 | WIR | SPML-KCM-A-IR- 3785 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43659
4 | WIR | SPML-KCM-A-IR- 3787 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-A-IR- 3788 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43659
4 | WIR | SPML-KCM-A-IR- 3789 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-A-IR- 3790 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 3792 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43659
4 | WIR | SPML-KCM-A-IR- 3795 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43659
4 | WIR | SPML-KCM-A-IR- 3796 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43659
4 | WIR | SPML-KCM-A-IR- 3800 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43659
4 | WIR | SPML-KCM-A-IR- 3801 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR- 3806 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 3808 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43661
4 | WIR | SPML-KCM-A-IR- 3809 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43661
4 | WIR | SPML-KCM-A-IR- 3810 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43661
4 | WIR | SPML-KCM-A-IR- 3811 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43661
4 | WIR | SPML-KCM-A-IR- 3812 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43661
4 | WIR | SPML-KCM-A-IR- 3813 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43661
4 | WIR | SPML-KCM-A-IR- 3814 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 3819 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 3820 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR- 3821 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 3822 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43629
4 | WIR | SPML-KCM-A-IR- 3823 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR- 3824 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43662
4 | WIR | SPML-KCM-A-IR- 3825 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43662
4 | WIR | SPML-KCM-A-IR- 3826 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43723
4 | WIR | SPML-KCM-A-IR- 3827 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 3828 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43662
4 | WIR | SPML-KCM-A-IR- 3829 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 3830 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43662
4 | WIR | SPML-KCM-A-IR- 3831 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43662
4 | WIR | SPML-KCM-A-IR- 3832 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43668
4 | WIR | SPML-KCM-A-IR- 3833 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43663
4 | WIR | SPML-KCM-A-IR- 3835 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43671
4 | WIR | SPML-KCM-A-IR- 3836 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43666
4 | WIR | SPML-KCM-A-IR- 3837 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43671
4 | WIR | SPML-KCM-A-IR- 3838 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43663
4 | WIR | SPML-KCM-A-IR- 3839 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43663
4 | WIR | SPML-KCM-A-IR- 3840 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 3841 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43663
4 | WIR | SPML-KCM-A-IR- 3843 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43663
4 | WIR | SPML-KCM-A-IR- 3844 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-A-IR- 3845 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43666
4 | WIR | SPML-KCM-A-IR- 3849 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 3850 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 3851 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 3852 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43915
4 | WIR | SPML-KCM-A-IR- 3853 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR- 3854 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43678
4 | WIR | SPML-KCM-A-IR- 3855 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-A-IR- 3856 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-A-IR- 3857 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-A-IR- 3858 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-A-IR- 3859 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43678
4 | WIR | SPML-KCM-A-IR- 3860 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44150
4 | WIR | SPML-KCM-A-IR- 3861 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 3864 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43666
4 | WIR | SPML-KCM-A-IR- 3865 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43666
4 | WIR | SPML-KCM-A-IR- 3866 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43749
4 | WIR | SPML-KCM-A-IR- 3867 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43666
4 | WIR | SPML-KCM-A-IR- 3868 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43666
4 | WIR | SPML-KCM-A-IR- 3869 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3870 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3871 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3872 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3873 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3874 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3876 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43666
4 | WIR | SPML-KCM-A-IR- 3877 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43724
4 | WIR | SPML-KCM-A-IR- 3879 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43668
4 | WIR | SPML-KCM-A-IR- 3880 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43668
4 | WIR | SPML-KCM-A-IR- 3881 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43668
4 | WIR | SPML-KCM-A-IR- 3882 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43668
4 | WIR | SPML-KCM-A-IR- 3883 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43668
4 | WIR | SPML-KCM-A-IR- 3888 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43669
4 | WIR | SPML-KCM-A-IR- 3889 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43674
4 | WIR | SPML-KCM-A-IR- 3891 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43675
4 | WIR | SPML-KCM-A-IR- 3896 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 3897 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43669
4 | WIR | SPML-KCM-A-IR- 3898 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43681
4 | WIR | SPML-KCM-A-IR- 3899 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43691
4 | WIR | SPML-KCM-A-IR- 3900 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43674
4 | WIR | SPML-KCM-A-IR- 3901 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43674
4 | WIR | SPML-KCM-A-IR- 3905 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-A-IR- 3906 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43669
4 | WIR | SPML-KCM-A-IR- 3907 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43669
4 | WIR | SPML-KCM-A-IR- 3908 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 3909 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 3910 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43669
4 | WIR | SPML-KCM-A-IR- 3911 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 3914 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44150
4 | WIR | SPML-KCM-A-IR- 3915 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43669
4 | WIR | SPML-KCM-A-IR- 3917 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 3918 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR- 3921 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 3922 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 3923 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43669
4 | WIR | SPML-KCM-A-IR- 3924 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43669
4 | WIR | SPML-KCM-A-IR- 3925 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 3926 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-A-IR- 3931 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-A-IR- 3935 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 3936 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR- 3937 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-A-IR- 3938 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3939 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3940 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-A-IR- 3941 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-A-IR- 3942 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-A-IR- 3943 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-A-IR- 3944 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43692
4 | WIR | SPML-KCM-A-IR- 3946 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3948 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43678
4 | WIR | SPML-KCM-A-IR- 3949 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 3950 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43671
4 | WIR | SPML-KCM-A-IR- 3951 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43671
4 | WIR | SPML-KCM-A-IR- 3952 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43676
4 | WIR | SPML-KCM-A-IR- 3953 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43671
4 | WIR | SPML-KCM-A-IR- 3954 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3957 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3962 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44152
4 | WIR | SPML-KCM-A-IR- 3963 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3964 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3965 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 3966 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43680
4 | WIR | SPML-KCM-A-IR- 3967 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 3968 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-A-IR- 3974 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43674
4 | WIR | SPML-KCM-A-IR- 3975 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43675
4 | WIR | SPML-KCM-A-IR- 3976 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43676
4 | WIR | SPML-KCM-A-IR- 3977 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43674
4 | WIR | SPML-KCM-A-IR- 3978 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43675
4 | WIR | SPML-KCM-A-IR- 3981 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 3982 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43676
4 | WIR | SPML-KCM-A-IR- 3983 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43676
4 | WIR | SPML-KCM-A-IR- 3984 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43675
4 | WIR | SPML-KCM-A-IR- 3988 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 3989 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43682
4 | WIR | SPML-KCM-A-IR- 3990 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43691
4 | WIR | SPML-KCM-A-IR- 3991 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43677
4 | WIR | SPML-KCM-A-IR- 3992 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43685
4 | WIR | SPML-KCM-A-IR- 3993 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43677
4 | WIR | SPML-KCM-A-IR- 3994 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43737
4 | WIR | SPML-KCM-A-IR- 3995 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43676
4 | WIR | SPML-KCM-A-IR- 3996 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43677
4 | WIR | SPML-KCM-A-IR- 3997 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 3998 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 3999 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 4000 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | D | 43676
4 | WIR | SPML-KCM-A-IR- 4001 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43677
4 | WIR | SPML-KCM-A-IR- 4003 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 4004 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43682
4 | WIR | SPML-KCM-A-IR- 4005 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 4006 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 4007 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 4008 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43677
4 | WIR | SPML-KCM-A-IR- 4009 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43677
4 | WIR | SPML-KCM-A-IR- 4010 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43677
4 | WIR | SPML-KCM-A-IR- 4011 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43677
4 | WIR | SPML-KCM-A-IR- 4012 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 4013 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43677
4 | WIR | SPML-KCM-A-IR- 4014 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44151
4 | WIR | SPML-KCM-A-IR- 4015 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43678
4 | WIR | SPML-KCM-A-IR- 4016 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43697
4 | WIR | SPML-KCM-A-IR- 4017 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43790
4 | WIR | SPML-KCM-A-IR- 4018 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 4021 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 4022 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 4025 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 4027 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 4029 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 4030 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 4031 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 4035 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43655
4 | WIR | SPML-KCM-A-IR- 4036 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-A-IR- 4040 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43691
4 | WIR | SPML-KCM-A-IR- 4041 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43681
4 | WIR | SPML-KCM-A-IR- 4042 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 4043 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43716
4 | WIR | SPML-KCM-A-IR- 4044 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43682
4 | WIR | SPML-KCM-A-IR- 4045 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43682
4 | WIR | SPML-KCM-A-IR- 4046 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 4047 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43691
4 | WIR | SPML-KCM-A-IR- 4048 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43683
4 | WIR | SPML-KCM-A-IR- 4049 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43692
4 | WIR | SPML-KCM-A-IR- 4050 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43696
4 | WIR | SPML-KCM-A-IR- 4053 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43993
4 | WIR | SPML-KCM-A-IR- 4054 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43683
4 | WIR | SPML-KCM-A-IR- 4055 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43683
4 | WIR | SPML-KCM-A-IR- 4056 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43683
4 | WIR | SPML-KCM-A-IR- 4057 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43993
4 | WIR | SPML-KCM-A-IR- 4058 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43995
4 | WIR | SPML-KCM-A-IR- 4059 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43692
4 | WIR | SPML-KCM-A-IR- 4060 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43684
4 | WIR | SPML-KCM-A-IR- 4061 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43684
4 | WIR | SPML-KCM-A-IR- 4062 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43993
4 | WIR | SPML-KCM-A-IR- 4063 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43691
4 | WIR | SPML-KCM-A-IR- 4066 | GRP System | GRP System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43691
4 | WIR | SPML-KCM-A-IR- 4068 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43687
4 | WIR | SPML-KCM-A-IR- 4069 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44108
4 | WIR | SPML-KCM-A-IR- 4071 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43691
4 | WIR | SPML-KCM-A-IR- 4072 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43697
4 | WIR | SPML-KCM-A-IR- 4073 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43995
4 | WIR | SPML-KCM-A-IR- 4074 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 4075 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43691
4 | WIR | SPML-KCM-A-IR- 4076 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43993
4 | WIR | SPML-KCM-A-IR- 4077 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43691
4 | WIR | SPML-KCM-A-IR- 4078 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43696
4 | WIR | SPML-KCM-A-IR- 4079 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43691
4 | WIR | SPML-KCM-A-IR- 4080 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43699
4 | WIR | SPML-KCM-A-IR- 4081 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43691
4 | WIR | SPML-KCM-A-IR- 4082 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43696
4 | WIR | SPML-KCM-A-IR- 4084 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43996
4 | WIR | SPML-KCM-A-IR- 4085 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 4086 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43703
4 | WIR | SPML-KCM-A-IR- 4087 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43696
4 | WIR | SPML-KCM-A-IR- 4088 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43694
4 | WIR | SPML-KCM-A-IR- 4089 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43692
4 | WIR | SPML-KCM-A-IR- 4093 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43694
4 | WIR | SPML-KCM-A-IR- 4095 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-A-IR- 4096 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43993
4 | WIR | SPML-KCM-A-IR- 4097 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43695
4 | WIR | SPML-KCM-A-IR- 4098 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43695
4 | WIR | SPML-KCM-A-IR- 4099 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43695
4 | WIR | SPML-KCM-A-IR- 4100 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43674
4 | WIR | SPML-KCM-A-IR- 4101 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43695
4 | WIR | SPML-KCM-A-IR- 4102 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43996
4 | WIR | SPML-KCM-A-IR- 4103 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43696
4 | WIR | SPML-KCM-A-IR- 4104 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43695
4 | WIR | SPML-KCM-A-IR- 4105 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43696
4 | WIR | SPML-KCM-A-IR- 4106 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43696
4 | WIR | SPML-KCM-A-IR- 4108 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43993
4 | WIR | SPML-KCM-A-IR- 4109 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43698
4 | WIR | SPML-KCM-A-IR- 4110 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43695
4 | WIR | SPML-KCM-A-IR- 4112 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43696
4 | WIR | SPML-KCM-A-IR- 4113 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43698
4 | WIR | SPML-KCM-A-IR- 4114 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43696
4 | WIR | SPML-KCM-A-IR- 4115 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 4116 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 4117 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43696
4 | WIR | SPML-KCM-A-IR- 4118 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43696
4 | WIR | SPML-KCM-A-IR- 4119 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43697
4 | WIR | SPML-KCM-A-IR- 4120 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43697
4 | WIR | SPML-KCM-A-IR- 4121 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43697
4 | WIR | SPML-KCM-A-IR- 4122 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43697
4 | WIR | SPML-KCM-A-IR- 4123 | Finishes | Hand Rail | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 4125 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43697
4 | WIR | SPML-KCM-A-IR- 4126 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43699
4 | WIR | SPML-KCM-A-IR- 4127 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 4128 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43697
4 | WIR | SPML-KCM-A-IR- 4129 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 4130 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 4131 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43698
4 | WIR | SPML-KCM-A-IR- 4134 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43698
4 | WIR | SPML-KCM-A-IR- 4135 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43699
4 | WIR | SPML-KCM-A-IR- 4136 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4137 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43698
4 | WIR | SPML-KCM-A-IR- 4138 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43698
4 | WIR | SPML-KCM-A-IR- 4139 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43698
4 | WIR | SPML-KCM-A-IR- 4140 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43698
4 | WIR | SPML-KCM-A-IR- 4141 | GRP System | GRP System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43941
4 | WIR | SPML-KCM-A-IR- 4143 | GRP System | GRP System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43698
4 | WIR | SPML-KCM-A-IR- 4144 | GRP System | GRP System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43698
4 | WIR | SPML-KCM-A-IR- 4145 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43699
4 | WIR | SPML-KCM-A-IR- 4146 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43699
4 | WIR | SPML-KCM-A-IR- 4147 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4148 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43699
4 | WIR | SPML-KCM-A-IR- 4149 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43699
4 | WIR | SPML-KCM-A-IR- 4150 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43699
4 | WIR | SPML-KCM-A-IR- 4151 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 4152 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43699
4 | WIR | SPML-KCM-A-IR- 4153 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43699
4 | WIR | SPML-KCM-A-IR- 4154 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43881
4 | WIR | SPML-KCM-A-IR- 4155 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4156 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4157 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4158 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43787
4 | WIR | SPML-KCM-A-IR- 4159 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43787
4 | WIR | SPML-KCM-A-IR- 4160 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4161 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4162 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4163 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 4164 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4165 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43787
4 | WIR | SPML-KCM-A-IR- 4166 | GRP System | GRP System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 4167 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4168 | Finishes | Vanity Countertop | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43701
4 | WIR | SPML-KCM-A-IR- 4169 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43702
4 | WIR | SPML-KCM-A-IR- 4170 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4171 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4172 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-A-IR- 4173 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43702
4 | WIR | SPML-KCM-A-IR- 4174 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43702
4 | WIR | SPML-KCM-A-IR- 4181 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 4182 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43836
4 | WIR | SPML-KCM-A-IR- 4183 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-A-IR- 4186 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43702
4 | WIR | SPML-KCM-A-IR- 4187 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43705
4 | WIR | SPML-KCM-A-IR- 4188 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43702
4 | WIR | SPML-KCM-A-IR- 4189 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43703
4 | WIR | SPML-KCM-A-IR- 4190 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43703
4 | WIR | SPML-KCM-A-IR- 4191 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4192 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43703
4 | WIR | SPML-KCM-A-IR- 4193 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44254
4 | WIR | SPML-KCM-A-IR- 4199 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-A-IR- 4200 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-A-IR- 4201 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43915
4 | WIR | SPML-KCM-A-IR- 4202 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43704
4 | WIR | SPML-KCM-A-IR- 4206 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43717
4 | WIR | SPML-KCM-A-IR- 4207 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4209 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43704
4 | WIR | SPML-KCM-A-IR- 4210 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43704
4 | WIR | SPML-KCM-A-IR- 4218 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-A-IR- 4220 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-A-IR- 4221 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43718
4 | WIR | SPML-KCM-A-IR- 4222 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43715
4 | WIR | SPML-KCM-A-IR- 4223 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43706
4 | WIR | SPML-KCM-A-IR- 4225 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43709
4 | WIR | SPML-KCM-A-IR- 4226 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-A-IR- 4227 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43713
4 | WIR | SPML-KCM-A-IR- 4228 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43685
4 | WIR | SPML-KCM-A-IR- 4230 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-A-IR- 4231 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43715
4 | WIR | SPML-KCM-A-IR- 4234 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-A-IR- 4235 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 4236 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43709
4 | WIR | SPML-KCM-A-IR- 4237 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43709
4 | WIR | SPML-KCM-A-IR- 4238 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43789
4 | WIR | SPML-KCM-A-IR- 4239 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4240 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43709
4 | WIR | SPML-KCM-A-IR- 4241 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43709
4 | WIR | SPML-KCM-A-IR- 4243 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43710
4 | WIR | SPML-KCM-A-IR- 4244 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43710
4 | WIR | SPML-KCM-A-IR- 4245 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43710
4 | WIR | SPML-KCM-A-IR- 4246 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43710
4 | WIR | SPML-KCM-A-IR- 4249 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43743
4 | WIR | SPML-KCM-A-IR- 4250 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-A-IR- 4251 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-A-IR- 4252 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-A-IR- 4253 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-A-IR- 4254 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-A-IR- 4255 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-A-IR- 4259 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43712
4 | WIR | SPML-KCM-A-IR- 4260 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-A-IR- 4261 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-A-IR- 4263 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-A-IR- 4264 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43717
4 | WIR | SPML-KCM-A-IR- 4266 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43743
4 | WIR | SPML-KCM-A-IR- 4267 | Finishes | Seating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 4268 | Finishes | Mirror | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43743
4 | WIR | SPML-KCM-A-IR- 4269 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43743
4 | WIR | SPML-KCM-A-IR- 4273 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43712
4 | WIR | SPML-KCM-A-IR- 4274 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 4279 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43712
4 | WIR | SPML-KCM-A-IR- 4280 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43712
4 | WIR | SPML-KCM-A-IR- 4281 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43712
4 | WIR | SPML-KCM-A-IR- 4282 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43712
4 | WIR | SPML-KCM-A-IR- 4283 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43719
4 | WIR | SPML-KCM-A-IR- 4284 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43713
4 | WIR | SPML-KCM-A-IR- 4285 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43713
4 | WIR | SPML-KCM-A-IR- 4286 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43715
4 | WIR | SPML-KCM-A-IR- 4287 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43715
4 | WIR | SPML-KCM-A-IR- 4288 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43713
4 | WIR | SPML-KCM-A-IR- 4289 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 4290 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43713
4 | WIR | SPML-KCM-A-IR- 4291 | Sealant | Fire Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 4292 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43729
4 | WIR | SPML-KCM-A-IR- 4293 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43713
4 | WIR | SPML-KCM-A-IR- 4294 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43715
4 | WIR | SPML-KCM-A-IR- 4295 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43713
4 | WIR | SPML-KCM-A-IR- 4296 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43733
4 | WIR | SPML-KCM-A-IR- 4297 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43733
4 | WIR | SPML-KCM-A-IR- 4303 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 4304 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43716
4 | WIR | SPML-KCM-A-IR- 4305 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 4306 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 4307 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43715
4 | WIR | SPML-KCM-A-IR- 4308 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43715
4 | WIR | SPML-KCM-A-IR- 4309 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43715
4 | WIR | SPML-KCM-A-IR- 4312 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43716
4 | WIR | SPML-KCM-A-IR- 4313 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43716
4 | WIR | SPML-KCM-A-IR- 4314 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-A-IR- 4315 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4316 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4317 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4318 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43716
4 | WIR | SPML-KCM-A-IR- 4319 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43716
4 | WIR | SPML-KCM-A-IR- 4320 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43716
4 | WIR | SPML-KCM-A-IR- 4321 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4322 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43743
4 | WIR | SPML-KCM-A-IR- 4324 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4325 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4326 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4329 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43863
4 | WIR | SPML-KCM-A-IR- 4330 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43677
4 | WIR | SPML-KCM-A-IR- 4331 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43716
4 | WIR | SPML-KCM-A-IR- 4332 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-A-IR- 4333 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43717
4 | WIR | SPML-KCM-A-IR- 4334 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43717
4 | WIR | SPML-KCM-A-IR- 4335 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43717
4 | WIR | SPML-KCM-A-IR- 4336 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43855
4 | WIR | SPML-KCM-A-IR- 4337 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43717
4 | WIR | SPML-KCM-A-IR- 4338 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43920
4 | WIR | SPML-KCM-A-IR- 4339 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43717
4 | WIR | SPML-KCM-A-IR- 4340 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43717
4 | WIR | SPML-KCM-A-IR- 4341 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43717
4 | WIR | SPML-KCM-A-IR- 4342 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43718
4 | WIR | SPML-KCM-A-IR- 4343 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43718
4 | WIR | SPML-KCM-A-IR- 4344 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4345 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4346 | Sealant | Fire Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 4347 | Sealant | Fire Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 4348 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43718
4 | WIR | SPML-KCM-A-IR- 4349 | Paving System | Kerb Stone | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43916
4 | WIR | SPML-KCM-A-IR- 4350 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 4351 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43718
4 | WIR | SPML-KCM-A-IR- 4352 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-A-IR- 4353 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43719
4 | WIR | SPML-KCM-A-IR- 4354 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43928
4 | WIR | SPML-KCM-A-IR- 4355 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43719
4 | WIR | SPML-KCM-A-IR- 4356 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43703
4 | WIR | SPML-KCM-A-IR- 4357 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43719
4 | WIR | SPML-KCM-A-IR- 4359 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43719
4 | WIR | SPML-KCM-A-IR- 4360 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43719
4 | WIR | SPML-KCM-A-IR- 4361 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43719
4 | WIR | SPML-KCM-A-IR- 4362 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43719
4 | WIR | SPML-KCM-A-IR- 4363 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4365 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43720
4 | WIR | SPML-KCM-A-IR- 4366 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43916
4 | WIR | SPML-KCM-A-IR- 4367 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-A-IR- 4368 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43729
4 | WIR | SPML-KCM-A-IR- 4369 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43729
4 | WIR | SPML-KCM-A-IR- 4370 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43720
4 | WIR | SPML-KCM-A-IR- 4371 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4372 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43722
4 | WIR | SPML-KCM-A-IR- 4373 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-A-IR- 4374 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 4376 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 4377 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43729
4 | WIR | SPML-KCM-A-IR- 4378 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-A-IR- 4379 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43722
4 | WIR | SPML-KCM-A-IR- 4380 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43920
4 | WIR | SPML-KCM-A-IR- 4381 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43920
4 | WIR | SPML-KCM-A-IR- 4382 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4384 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43916
4 | WIR | SPML-KCM-A-IR- 4385 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43916
4 | WIR | SPML-KCM-A-IR- 4386 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43724
4 | WIR | SPML-KCM-A-IR- 4387 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-A-IR- 4388 | Finishes | Coarse & Medium Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43723
4 | WIR | SPML-KCM-A-IR- 4389 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43723
4 | WIR | SPML-KCM-A-IR- 4390 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43723
4 | WIR | SPML-KCM-A-IR- 4391 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4393 | Finishes | Stone Carpet | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR- 4394 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4395 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43838
4 | WIR | SPML-KCM-A-IR- 4396 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43723
4 | WIR | SPML-KCM-A-IR- 4397 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-A-IR- 4398 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43723
4 | WIR | SPML-KCM-A-IR- 4399 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43724
4 | WIR | SPML-KCM-A-IR- 4400 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43724
4 | WIR | SPML-KCM-A-IR- 4401 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43724
4 | WIR | SPML-KCM-A-IR- 4402 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43724
4 | WIR | SPML-KCM-A-IR- 4403 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43724
4 | WIR | SPML-KCM-A-IR- 4404 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43916
4 | WIR | SPML-KCM-A-IR- 4405 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43577
4 | WIR | SPML-KCM-A-IR- 4406 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43724
4 | WIR | SPML-KCM-A-IR- 4407 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43724
4 | WIR | SPML-KCM-A-IR- 4408 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43724
4 | WIR | SPML-KCM-A-IR- 4409 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43723
4 | WIR | SPML-KCM-A-IR- 4410 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43724
4 | WIR | SPML-KCM-A-IR- 4411 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4413 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43725
4 | WIR | SPML-KCM-A-IR- 4414 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43724
4 | WIR | SPML-KCM-A-IR- 4416 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43916
4 | WIR | SPML-KCM-A-IR- 4417 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43920
4 | WIR | SPML-KCM-A-IR- 4418 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4419 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-A-IR- 4421 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43724
4 | WIR | SPML-KCM-A-IR- 4422 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43792
4 | WIR | SPML-KCM-A-IR- 4423 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43725
4 | WIR | SPML-KCM-A-IR- 4424 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4425 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 4426 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4427 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4428 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4430 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 4431 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43724
4 | WIR | SPML-KCM-A-IR- 4433 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43725
4 | WIR | SPML-KCM-A-IR- 4434 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43725
4 | WIR | SPML-KCM-A-IR- 4435 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4436 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43725
4 | WIR | SPML-KCM-A-IR- 4437 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43916
4 | WIR | SPML-KCM-A-IR- 4439 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43990
4 | WIR | SPML-KCM-A-IR- 4440 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43725
4 | WIR | SPML-KCM-A-IR- 4441 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43725
4 | WIR | SPML-KCM-A-IR- 4443 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43785
4 | WIR | SPML-KCM-A-IR- 4444 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4445 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43843
4 | WIR | SPML-KCM-A-IR- 4446 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4447 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-A-IR- 4449 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43733
4 | WIR | SPML-KCM-A-IR- 4451 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43727
4 | WIR | SPML-KCM-A-IR- 4452 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43727
4 | WIR | SPML-KCM-A-IR- 4453 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43944
4 | WIR | SPML-KCM-A-IR- 4454 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-A-IR- 4456 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43727
4 | WIR | SPML-KCM-A-IR- 4457 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4458 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43726
4 | WIR | SPML-KCM-A-IR- 4459 | Finishes | Coarse & Medium Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43726
4 | WIR | SPML-KCM-A-IR- 4460 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43726
4 | WIR | SPML-KCM-A-IR- 4461 | Finishes | Coarse & Medium Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43726
4 | WIR | SPML-KCM-A-IR- 4463 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43727
4 | WIR | SPML-KCM-A-IR- 4464 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 4465 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43727
4 | WIR | SPML-KCM-A-IR- 4466 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4467 | Paving System | Kerb Stone | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43944
4 | WIR | SPML-KCM-A-IR- 4468 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 4469 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4470 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4471 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43928
4 | WIR | SPML-KCM-A-IR- 4472 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43727
4 | WIR | SPML-KCM-A-IR- 4473 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-A-IR- 4474 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 4475 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 4476 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 4477 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43727
4 | WIR | SPML-KCM-A-IR- 4478 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43727
4 | WIR | SPML-KCM-A-IR- 4479 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4480 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-A-IR- 4481 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43727
4 | WIR | SPML-KCM-A-IR- 4482 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43733
4 | WIR | SPML-KCM-A-IR- 4483 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43733
4 | WIR | SPML-KCM-A-IR- 4484 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43764
4 | WIR | SPML-KCM-A-IR- 4486 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43732
4 | WIR | SPML-KCM-A-IR- 4487 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43733
4 | WIR | SPML-KCM-A-IR- 4488 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43733
4 | WIR | SPML-KCM-A-IR- 4489 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43732
4 | WIR | SPML-KCM-A-IR- 4490 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43732
4 | WIR | SPML-KCM-A-IR- 4491 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43739
4 | WIR | SPML-KCM-A-IR- 4492 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43730
4 | WIR | SPML-KCM-A-IR- 4493 | LandScaping | Irrigation System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 4494 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 4496 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-A-IR- 4497 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43730
4 | WIR | SPML-KCM-A-IR- 4498 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4499 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4500 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43730
4 | WIR | SPML-KCM-A-IR- 4505 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43737
4 | WIR | SPML-KCM-A-IR- 4506 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43965
4 | WIR | SPML-KCM-A-IR- 4507 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-A-IR- 4508 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-A-IR- 4509 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43730
4 | WIR | SPML-KCM-A-IR- 4510 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43730
4 | WIR | SPML-KCM-A-IR- 4512 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4514 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43730
4 | WIR | SPML-KCM-A-IR- 4515 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4517 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43732
4 | WIR | SPML-KCM-A-IR- 4518 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 4519 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43732
4 | WIR | SPML-KCM-A-IR- 4520 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43843
4 | WIR | SPML-KCM-A-IR- 4521 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43809
4 | WIR | SPML-KCM-A-IR- 4522 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43957
4 | WIR | SPML-KCM-A-IR- 4523 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43834
4 | WIR | SPML-KCM-A-IR- 4524 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43834
4 | WIR | SPML-KCM-A-IR- 4525 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4526 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43863
4 | WIR | SPML-KCM-A-IR- 4528 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-A-IR- 4529 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43709
4 | WIR | SPML-KCM-A-IR- 4530 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 4531 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43704
4 | WIR | SPML-KCM-A-IR- 4532 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43712
4 | WIR | SPML-KCM-A-IR- 4533 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43717
4 | WIR | SPML-KCM-A-IR- 4534 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 4535 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43738
4 | WIR | SPML-KCM-A-IR- 4536 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43733
4 | WIR | SPML-KCM-A-IR- 4537 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43944
4 | WIR | SPML-KCM-A-IR- 4538 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43869
4 | WIR | SPML-KCM-A-IR- 4539 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43792
4 | WIR | SPML-KCM-A-IR- 4541 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 4542 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43736
4 | WIR | SPML-KCM-A-IR- 4543 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43737
4 | WIR | SPML-KCM-A-IR- 4544 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 4546 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 4547 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43737
4 | WIR | SPML-KCM-A-IR- 4548 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43737
4 | WIR | SPML-KCM-A-IR- 4549 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43737
4 | WIR | SPML-KCM-A-IR- 4550 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43738
4 | WIR | SPML-KCM-A-IR- 4551 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43738
4 | WIR | SPML-KCM-A-IR- 4552 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43738
4 | WIR | SPML-KCM-A-IR- 4553 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43738
4 | WIR | SPML-KCM-A-IR- 4554 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43838
4 | WIR | SPML-KCM-A-IR- 4555 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43738
4 | WIR | SPML-KCM-A-IR- 4557 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-A-IR- 4558 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43813
4 | WIR | SPML-KCM-A-IR- 4559 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43738
4 | WIR | SPML-KCM-A-IR- 4560 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43738
4 | WIR | SPML-KCM-A-IR- 4561 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-A-IR- 4562 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43738
4 | WIR | SPML-KCM-A-IR- 4566 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4567 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 4568 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 4569 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43739
4 | WIR | SPML-KCM-A-IR- 4570 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43867
4 | WIR | SPML-KCM-A-IR- 4571 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43739
4 | WIR | SPML-KCM-A-IR- 4572 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43739
4 | WIR | SPML-KCM-A-IR- 4573 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43740
4 | WIR | SPML-KCM-A-IR- 4574 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43740
4 | WIR | SPML-KCM-A-IR- 4577 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43740
4 | WIR | SPML-KCM-A-IR- 4578 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43740
4 | WIR | SPML-KCM-A-IR- 4579 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR- 4580 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 4581 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43718
4 | WIR | SPML-KCM-A-IR- 4582 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43718
4 | WIR | SPML-KCM-A-IR- 4583 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43719
4 | WIR | SPML-KCM-A-IR- 4584 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43719
4 | WIR | SPML-KCM-A-IR- 4585 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 4586 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 4587 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43719
4 | WIR | SPML-KCM-A-IR- 4588 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43719
4 | WIR | SPML-KCM-A-IR- 4589 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 4590 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 4591 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43720
4 | WIR | SPML-KCM-A-IR- 4592 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43722
4 | WIR | SPML-KCM-A-IR- 4593 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4594 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | B | 43724
4 | WIR | SPML-KCM-A-IR- 4595 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-A-IR- 4596 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43740
4 | WIR | SPML-KCM-A-IR- 4597 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43740
4 | WIR | SPML-KCM-A-IR- 4598 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43944
4 | WIR | SPML-KCM-A-IR- 4599 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 4600 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43835
4 | WIR | SPML-KCM-A-IR- 4601 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43832
4 | WIR | SPML-KCM-A-IR- 4602 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43741
4 | WIR | SPML-KCM-A-IR- 4603 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43741
4 | WIR | SPML-KCM-A-IR- 4604 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43792
4 | WIR | SPML-KCM-A-IR- 4605 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43741
4 | WIR | SPML-KCM-A-IR- 4606 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43741
4 | WIR | SPML-KCM-A-IR- 4607 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 4609 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43741
4 | WIR | SPML-KCM-A-IR- 4610 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43743
4 | WIR | SPML-KCM-A-IR- 4611 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-A-IR- 4612 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 4614 | Finishes | Aluminium Extrusion | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 4615 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-A-IR- 4616 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-A-IR- 4617 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-A-IR- 4618 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4619 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-A-IR- 4620 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4621 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-A-IR- 4623 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 4624 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43835
4 | WIR | SPML-KCM-A-IR- 4625 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44025
4 | WIR | SPML-KCM-A-IR- 4626 | Finishes | Coarse & Medium Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43670
4 | WIR | SPML-KCM-A-IR- 4627 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43854
4 | WIR | SPML-KCM-A-IR- 4628 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-A-IR- 4629 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43835
4 | WIR | SPML-KCM-A-IR- 4630 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44077
4 | WIR | SPML-KCM-A-IR- 4631 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43743
4 | WIR | SPML-KCM-A-IR- 4632 | GRP System | GRP System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 4633 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44108
4 | WIR | SPML-KCM-A-IR- 4634 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR- 4635 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 4636 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-A-IR- 4638 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43744
4 | WIR | SPML-KCM-A-IR- 4639 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-A-IR- 4652 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-A-IR- 4653 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43743
4 | WIR | SPML-KCM-A-IR- 4654 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43927
4 | WIR | SPML-KCM-A-IR- 4655 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-A-IR- 4656 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-A-IR- 4657 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-A-IR- 4658 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-A-IR- 4659 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-A-IR- 4660 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-A-IR- 4664 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-A-IR- 4665 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4666 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-A-IR- 4667 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43747
4 | WIR | SPML-KCM-A-IR- 4668 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4669 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-A-IR- 4670 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-A-IR- 4671 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-A-IR- 4672 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43748
4 | WIR | SPML-KCM-A-IR- 4673 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 4674 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 4675 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43748
4 | WIR | SPML-KCM-A-IR- 4676 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43764
4 | WIR | SPML-KCM-A-IR- 4677 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43748
4 | WIR | SPML-KCM-A-IR- 4678 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43748
4 | WIR | SPML-KCM-A-IR- 4679 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43934
4 | WIR | SPML-KCM-A-IR- 4680 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43748
4 | WIR | SPML-KCM-A-IR- 4681 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43752
4 | WIR | SPML-KCM-A-IR- 4682 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4683 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4684 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4685 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-A-IR- 4686 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4687 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4688 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43813
4 | WIR | SPML-KCM-A-IR- 4689 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4690 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4693 | Roofing and Glazing System | Top Hat & Halter | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4694 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4696 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 4697 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-A-IR- 4700 | Paving System | Kerb Stone | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43944
4 | WIR | SPML-KCM-A-IR- 4701 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 4702 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43752
4 | WIR | SPML-KCM-A-IR- 4703 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43753
4 | WIR | SPML-KCM-A-IR- 4704 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-A-IR- 4705 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-A-IR- 4706 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43870
4 | WIR | SPML-KCM-A-IR- 4707 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-A-IR- 4708 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-A-IR- 4709 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-A-IR- 4710 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-A-IR- 4711 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-A-IR- 4712 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-A-IR- 4713 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-A-IR- 4714 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-A-IR- 4715 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-A-IR- 4716 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-A-IR- 4717 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-A-IR- 4718 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43771
4 | WIR | SPML-KCM-A-IR- 4719 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43754
4 | WIR | SPML-KCM-A-IR- 4720 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43753
4 | WIR | SPML-KCM-A-IR- 4721 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43753
4 | WIR | SPML-KCM-A-IR- 4722 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43753
4 | WIR | SPML-KCM-A-IR- 4723 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4724 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43753
4 | WIR | SPML-KCM-A-IR- 4725 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43754
4 | WIR | SPML-KCM-A-IR- 4726 | Finishes | Green Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-A-IR- 4727 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43754
4 | WIR | SPML-KCM-A-IR- 4728 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43754
4 | WIR | SPML-KCM-A-IR- 4729 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43754
4 | WIR | SPML-KCM-A-IR- 4730 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43754
4 | WIR | SPML-KCM-A-IR- 4731 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43754
4 | WIR | SPML-KCM-A-IR- 4745 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4746 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43944
4 | WIR | SPML-KCM-A-IR- 4748 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-A-IR- 4749 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-A-IR- 4750 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43602
4 | WIR | SPML-KCM-A-IR- 4751 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43602
4 | WIR | SPML-KCM-A-IR- 4752 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-A-IR- 4753 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43602
4 | WIR | SPML-KCM-A-IR- 4754 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44147
4 | WIR | SPML-KCM-A-IR- 4755 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-A-IR- 4756 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43890
4 | WIR | SPML-KCM-A-IR- 4757 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-A-IR- 4758 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43758
4 | WIR | SPML-KCM-A-IR- 4759 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43597
4 | WIR | SPML-KCM-A-IR- 4760 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-A-IR- 4761 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-A-IR- 4762 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-A-IR- 4763 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-A-IR- 4764 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43758
4 | WIR | SPML-KCM-A-IR- 4766 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-A-IR- 4767 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 4768 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 4769 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-A-IR- 4770 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 4771 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-A-IR- 4772 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43762
4 | WIR | SPML-KCM-A-IR- 4773 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4774 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4775 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43834
4 | WIR | SPML-KCM-A-IR- 4776 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-A-IR- 4777 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43762
4 | WIR | SPML-KCM-A-IR- 4778 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | B | 43758
4 | WIR | SPML-KCM-A-IR- 4779 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43759
4 | WIR | SPML-KCM-A-IR- 4780 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43759
4 | WIR | SPML-KCM-A-IR- 4781 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43759
4 | WIR | SPML-KCM-A-IR- 4782 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43759
4 | WIR | SPML-KCM-A-IR- 4783 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43568
4 | WIR | SPML-KCM-A-IR- 4784 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43608
4 | WIR | SPML-KCM-A-IR- 4785 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43611
4 | WIR | SPML-KCM-A-IR- 4786 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43771
4 | WIR | SPML-KCM-A-IR- 4787 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-A-IR- 4806 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-A-IR- 4807 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-A-IR- 4808 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-A-IR- 4809 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43761
4 | WIR | SPML-KCM-A-IR- 4810 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 4811 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43761
4 | WIR | SPML-KCM-A-IR- 4812 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43761
4 | WIR | SPML-KCM-A-IR- 4813 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43762
4 | WIR | SPML-KCM-A-IR- 4814 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 4815 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43762
4 | WIR | SPML-KCM-A-IR- 4816 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 4817 | Finishes | Coarse & Medium Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-A-IR- 4818 | Finishes | Coarse & Medium Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43860
4 | WIR | SPML-KCM-A-IR- 4819 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43838
4 | WIR | SPML-KCM-A-IR- 4820 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-A-IR- 4821 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-A-IR- 4822 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43681
4 | WIR | SPML-KCM-A-IR- 4823 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43764
4 | WIR | SPML-KCM-A-IR- 4824 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44072
4 | WIR | SPML-KCM-A-IR- 4825 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-A-IR- 4826 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-A-IR- 4827 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43842
4 | WIR | SPML-KCM-A-IR- 4828 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-A-IR- 4829 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43851
4 | WIR | SPML-KCM-A-IR- 4830 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43785
4 | WIR | SPML-KCM-A-IR- 4831 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43753
4 | WIR | SPML-KCM-A-IR- 4832 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 4833 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43835
4 | WIR | SPML-KCM-A-IR- 4834 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44108
4 | WIR | SPML-KCM-A-IR- 4835 | Car Park | Car Park Numbering | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 4836 | GRP System | GRP System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43764
4 | WIR | SPML-KCM-A-IR- 4837 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43859
4 | WIR | SPML-KCM-A-IR- 4838 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43786
4 | WIR | SPML-KCM-A-IR- 4839 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 4841 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44170
4 | WIR | SPML-KCM-A-IR- 4844 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-A-IR- 4848 | Finishes | Vapour Barrier | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-A-IR- 4849 | Finishes | Vapour Barrier | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-A-IR- 4854 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-A-IR- 4856 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43769
4 | WIR | SPML-KCM-A-IR- 4858 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-A-IR- 4859 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-A-IR- 4860 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-A-IR- 4861 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 4862 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4863 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43834
4 | WIR | SPML-KCM-A-IR- 4864 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43838
4 | WIR | SPML-KCM-A-IR- 4865 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 4867 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43771
4 | WIR | SPML-KCM-A-IR- 4868 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43928
4 | WIR | SPML-KCM-A-IR- 4870 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-A-IR- 4871 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-A-IR- 4872 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 4873 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 4874 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44076
4 | WIR | SPML-KCM-A-IR- 4875 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43778
4 | WIR | SPML-KCM-A-IR- 4876 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43778
4 | WIR | SPML-KCM-A-IR- 4877 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43848
4 | WIR | SPML-KCM-A-IR- 4878 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-A-IR- 4881 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43771
4 | WIR | SPML-KCM-A-IR- 4882 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43629
4 | WIR | SPML-KCM-A-IR- 4883 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43632
4 | WIR | SPML-KCM-A-IR- 4884 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43619
4 | WIR | SPML-KCM-A-IR- 4885 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43619
4 | WIR | SPML-KCM-A-IR- 4886 | Finishes | Vapour Barrier | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 4889 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 4890 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43776
4 | WIR | SPML-KCM-A-IR- 4891 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43621
4 | WIR | SPML-KCM-A-IR- 4892 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4893 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-A-IR- 4894 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4896 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4897 | Finishes | Grating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 4898 | Power Distribution | Small Power | Al Forsan Central Mall | NA | Electrical | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 4899 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43621
4 | WIR | SPML-KCM-A-IR- 4900 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43621
4 | WIR | SPML-KCM-A-IR- 4901 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43621
4 | WIR | SPML-KCM-A-IR- 4902 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 4904 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43775
4 | WIR | SPML-KCM-A-IR- 4906 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43775
4 | WIR | SPML-KCM-A-IR- 4907 | Finishes | Column Guard | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 4908 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43775
4 | WIR | SPML-KCM-A-IR- 4909 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4910 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43775
4 | WIR | SPML-KCM-A-IR- 4911 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43775
4 | WIR | SPML-KCM-A-IR- 4912 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43775
4 | WIR | SPML-KCM-A-IR- 4913 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43775
4 | WIR | SPML-KCM-A-IR- 4916 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44129
4 | WIR | SPML-KCM-A-IR- 4917 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43635
4 | WIR | SPML-KCM-A-IR- 4918 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43638
4 | WIR | SPML-KCM-A-IR- 4919 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43842
4 | WIR | SPML-KCM-A-IR- 4920 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43832
4 | WIR | SPML-KCM-A-IR- 4921 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 4922 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43782
4 | WIR | SPML-KCM-A-IR- 4923 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 4924 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 4925 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 4926 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 4927 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 4928 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 4929 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44121
4 | WIR | SPML-KCM-A-IR- 4931 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43835
4 | WIR | SPML-KCM-A-IR- 4932 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43835
4 | WIR | SPML-KCM-A-IR- 4933 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43842
4 | WIR | SPML-KCM-A-IR- 4934 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 4936 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43776
4 | WIR | SPML-KCM-A-IR- 4940 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43780
4 | WIR | SPML-KCM-A-IR- 4941 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43779
4 | WIR | SPML-KCM-A-IR- 4942 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43779
4 | WIR | SPML-KCM-A-IR- 4943 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR- 4945 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43780
4 | WIR | SPML-KCM-A-IR- 4947 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43992
4 | WIR | SPML-KCM-A-IR- 4948 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43780
4 | WIR | SPML-KCM-A-IR- 4953 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4954 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43781
4 | WIR | SPML-KCM-A-IR- 4955 | Finishes | Grating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 4956 | Sealant | Expansion Joint Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 4957 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43818
4 | WIR | SPML-KCM-A-IR- 4958 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 4960 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43783
4 | WIR | SPML-KCM-A-IR- 4962 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43996
4 | WIR | SPML-KCM-A-IR- 4966 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43785
4 | WIR | SPML-KCM-A-IR- 4967 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43786
4 | WIR | SPML-KCM-A-IR- 4968 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43785
4 | WIR | SPML-KCM-A-IR- 4969 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43786
4 | WIR | SPML-KCM-A-IR- 4970 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-A-IR- 4971 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43774
4 | WIR | SPML-KCM-A-IR- 4972 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43785
4 | WIR | SPML-KCM-A-IR- 4973 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43785
4 | WIR | SPML-KCM-A-IR- 4974 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43785
4 | WIR | SPML-KCM-A-IR- 4975 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-A-IR- 4976 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43773
4 | WIR | SPML-KCM-A-IR- 4977 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43785
4 | WIR | SPML-KCM-A-IR- 4982 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43786
4 | WIR | SPML-KCM-A-IR- 4983 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43786
4 | WIR | SPML-KCM-A-IR- 4984 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43786
4 | WIR | SPML-KCM-A-IR- 4985 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43786
4 | WIR | SPML-KCM-A-IR- 4989 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 4990 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 4991 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43786
4 | WIR | SPML-KCM-A-IR- 4992 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43787
4 | WIR | SPML-KCM-A-IR- 4993 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44173
4 | WIR | SPML-KCM-A-IR- 4994 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44173
4 | WIR | SPML-KCM-A-IR- 4995 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43788
4 | WIR | SPML-KCM-A-IR- 4997 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 4999 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43808
4 | WIR | SPML-KCM-A-IR- 5002 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43832
4 | WIR | SPML-KCM-A-IR- 5003 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43788
4 | WIR | SPML-KCM-A-IR- 5004 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43788
4 | WIR | SPML-KCM-A-IR- 5007 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43789
4 | WIR | SPML-KCM-A-IR- 5008 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 5009 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43789
4 | WIR | SPML-KCM-A-IR- 5010 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 5011 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43790
4 | WIR | SPML-KCM-A-IR- 5012 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43935
4 | WIR | SPML-KCM-A-IR- 5013 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43790
4 | WIR | SPML-KCM-A-IR- 5014 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43808
4 | WIR | SPML-KCM-A-IR- 5016 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43792
4 | WIR | SPML-KCM-A-IR- 5017 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43793
4 | WIR | SPML-KCM-A-IR- 5018 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 5019 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43848
4 | WIR | SPML-KCM-A-IR- 5020 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 5021 | Finishes | Coarse & Medium Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5022 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43792
4 | WIR | SPML-KCM-A-IR- 5023 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43796
4 | WIR | SPML-KCM-A-IR- 5028 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44150
4 | WIR | SPML-KCM-A-IR- 5029 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43792
4 | WIR | SPML-KCM-A-IR- 5030 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43792
4 | WIR | SPML-KCM-A-IR- 5031 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43792
4 | WIR | SPML-KCM-A-IR- 5034 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43795
4 | WIR | SPML-KCM-A-IR- 5035 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43815
4 | WIR | SPML-KCM-A-IR- 5036 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 5037 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43838
4 | WIR | SPML-KCM-A-IR- 5038 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43838
4 | WIR | SPML-KCM-A-IR- 5039 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43793
4 | WIR | SPML-KCM-A-IR- 5040 | Space Protection System | Bollards | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5042 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43795
4 | WIR | SPML-KCM-A-IR- 5043 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44173
4 | WIR | SPML-KCM-A-IR- 5044 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 5045 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43794
4 | WIR | SPML-KCM-A-IR- 5046 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 5047 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43794
4 | WIR | SPML-KCM-A-IR- 5048 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43794
4 | WIR | SPML-KCM-A-IR- 5049 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44170
4 | WIR | SPML-KCM-A-IR- 5055 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43795
4 | WIR | SPML-KCM-A-IR- 5056 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-A-IR- 5057 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-A-IR- 5058 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43795
4 | WIR | SPML-KCM-A-IR- 5059 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5060 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43939
4 | WIR | SPML-KCM-A-IR- 5061 | Sealant | Expansion Joint Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 5062 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43795
4 | WIR | SPML-KCM-A-IR- 5063 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43795
4 | WIR | SPML-KCM-A-IR- 5064 | Roofing and Glazing System | Top Hat & Halter | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43796
4 | WIR | SPML-KCM-A-IR- 5065 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5066 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44147
4 | WIR | SPML-KCM-A-IR- 5072 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5073 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-A-IR- 5074 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-A-IR- 5075 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-A-IR- 5076 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44174
4 | WIR | SPML-KCM-A-IR- 5077 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43817
4 | WIR | SPML-KCM-A-IR- 5078 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43821
4 | WIR | SPML-KCM-A-IR- 5079 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44132
4 | WIR | SPML-KCM-A-IR- 5080 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43848
4 | WIR | SPML-KCM-A-IR- 5081 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43841
4 | WIR | SPML-KCM-A-IR- 5082 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 5083 | Finishes | Coarse & Medium Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5084 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43817
4 | WIR | SPML-KCM-A-IR- 5085 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43799
4 | WIR | SPML-KCM-A-IR- 5086 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43799
4 | WIR | SPML-KCM-A-IR- 5087 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 5088 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43799
4 | WIR | SPML-KCM-A-IR- 5089 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43799
4 | WIR | SPML-KCM-A-IR- 5090 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43799
4 | WIR | SPML-KCM-A-IR- 5091 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5092 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-A-IR- 5093 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43797
4 | WIR | SPML-KCM-A-IR- 5094 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 5097 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43817
4 | WIR | SPML-KCM-A-IR- 5098 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43803
4 | WIR | SPML-KCM-A-IR- 5099 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43803
4 | WIR | SPML-KCM-A-IR- 5100 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44129
4 | WIR | SPML-KCM-A-IR- 5101 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43804
4 | WIR | SPML-KCM-A-IR- 5102 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43804
4 | WIR | SPML-KCM-A-IR- 5103 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43804
4 | WIR | SPML-KCM-A-IR- 5106 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43804
4 | WIR | SPML-KCM-A-IR- 5108 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44174
4 | WIR | SPML-KCM-A-IR- 5110 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5111 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5112 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 5113 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43806
4 | WIR | SPML-KCM-A-IR- 5114 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5115 | Finishes | Aesthetic Finishes | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43874
4 | WIR | SPML-KCM-A-IR- 5116 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43807
4 | WIR | SPML-KCM-A-IR- 5117 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43807
4 | WIR | SPML-KCM-A-IR- 5119 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 5120 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 5121 | Finishes | Coarse & Medium Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5122 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43817
4 | WIR | SPML-KCM-A-IR- 5123 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5125 | Finishes | Hand Rail | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 5126 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44132
4 | WIR | SPML-KCM-A-IR- 5128 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43839
4 | WIR | SPML-KCM-A-IR- 5129 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43807
4 | WIR | SPML-KCM-A-IR- 5130 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 5132 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43808
4 | WIR | SPML-KCM-A-IR- 5133 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43808
4 | WIR | SPML-KCM-A-IR- 5134 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43808
4 | WIR | SPML-KCM-A-IR- 5135 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 5136 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43814
4 | WIR | SPML-KCM-A-IR- 5138 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43808
4 | WIR | SPML-KCM-A-IR- 5139 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43814
4 | WIR | SPML-KCM-A-IR- 5140 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-A-IR- 5142 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43809
4 | WIR | SPML-KCM-A-IR- 5143 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43809
4 | WIR | SPML-KCM-A-IR- 5144 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-A-IR- 5145 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | B | 43809
4 | WIR | SPML-KCM-A-IR- 5147 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43832
4 | WIR | SPML-KCM-A-IR- 5148 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5149 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43810
4 | WIR | SPML-KCM-A-IR- 5150 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43810
4 | WIR | SPML-KCM-A-IR- 5155 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43786
4 | WIR | SPML-KCM-A-IR- 5156 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43787
4 | WIR | SPML-KCM-A-IR- 5159 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43852
4 | WIR | SPML-KCM-A-IR- 5161 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5167 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5168 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43817
4 | WIR | SPML-KCM-A-IR- 5169 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5170 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 5171 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44170
4 | WIR | SPML-KCM-A-IR- 5174 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 5180 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43815
4 | WIR | SPML-KCM-A-IR- 5181 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43816
4 | WIR | SPML-KCM-A-IR- 5182 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43935
4 | WIR | SPML-KCM-A-IR- 5184 | Finishes | Hand Rail | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 5186 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5187 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 5188 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43934
4 | WIR | SPML-KCM-A-IR- 5190 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43816
4 | WIR | SPML-KCM-A-IR- 5191 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43824
4 | WIR | SPML-KCM-A-IR- 5193 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43818
4 | WIR | SPML-KCM-A-IR- 5194 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43820
4 | WIR | SPML-KCM-A-IR- 5195 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5196 | Paving System | Interlock | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 5197 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 5199 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5200 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43818
4 | WIR | SPML-KCM-A-IR- 5201 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43818
4 | WIR | SPML-KCM-A-IR- 5202 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43821
4 | WIR | SPML-KCM-A-IR- 5203 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5204 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43820
4 | WIR | SPML-KCM-A-IR- 5205 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43820
4 | WIR | SPML-KCM-A-IR- 5206 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43820
4 | WIR | SPML-KCM-A-IR- 5207 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43821
4 | WIR | SPML-KCM-A-IR- 5208 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44087
4 | WIR | SPML-KCM-A-IR- 5210 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44083
4 | WIR | SPML-KCM-A-IR- 5211 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43821
4 | WIR | SPML-KCM-A-IR- 5212 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43820
4 | WIR | SPML-KCM-A-IR- 5213 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43820
4 | WIR | SPML-KCM-A-IR- 5214 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43820
4 | WIR | SPML-KCM-A-IR- 5217 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 5218 | Sealant | Expansion Joint Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 5219 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43821
4 | WIR | SPML-KCM-A-IR- 5222 | Sealant | Expansion Joint Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 5223 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43824
4 | WIR | SPML-KCM-A-IR- 5225 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43822
4 | WIR | SPML-KCM-A-IR- 5226 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43822
4 | WIR | SPML-KCM-A-IR- 5227 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43822
4 | WIR | SPML-KCM-A-IR- 5231 | Paving System | Interlock | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43827
4 | WIR | SPML-KCM-A-IR- 5232 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43824
4 | WIR | SPML-KCM-A-IR- 5233 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43824
4 | WIR | SPML-KCM-A-IR- 5234 | Finishes | Raised Floor | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 5241 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43827
4 | WIR | SPML-KCM-A-IR- 5242 | GRP System | GRP System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43825
4 | WIR | SPML-KCM-A-IR- 5244 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43846
4 | WIR | SPML-KCM-A-IR- 5245 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43827
4 | WIR | SPML-KCM-A-IR- 5246 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43827
4 | WIR | SPML-KCM-A-IR- 5247 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43827
4 | WIR | SPML-KCM-A-IR- 5249 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43827
4 | WIR | SPML-KCM-A-IR- 5250 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43827
4 | WIR | SPML-KCM-A-IR- 5251 | FF&E | Electric Cabinet | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-A-IR- 5253 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43827
4 | WIR | SPML-KCM-A-IR- 5254 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43827
4 | WIR | SPML-KCM-A-IR- 5255 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43829
4 | WIR | SPML-KCM-A-IR- 5256 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5257 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5258 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43828
4 | WIR | SPML-KCM-A-IR- 5259 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-A-IR- 5261 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43925
4 | WIR | SPML-KCM-A-IR- 5262 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43956
4 | WIR | SPML-KCM-A-IR- 5263 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 5264 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43827
4 | WIR | SPML-KCM-A-IR- 5265 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43838
4 | WIR | SPML-KCM-A-IR- 5266 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 5268 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43844
4 | WIR | SPML-KCM-A-IR- 5270 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5272 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43827
4 | WIR | SPML-KCM-A-IR- 5273 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43828
4 | WIR | SPML-KCM-A-IR- 5274 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43829
4 | WIR | SPML-KCM-A-IR- 5275 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43830
4 | WIR | SPML-KCM-A-IR- 5276 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43832
4 | WIR | SPML-KCM-A-IR- 5277 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43834
4 | WIR | SPML-KCM-A-IR- 5279 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 5282 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43869
4 | WIR | SPML-KCM-A-IR- 5283 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43890
4 | WIR | SPML-KCM-A-IR- 5284 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 5285 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43925
4 | WIR | SPML-KCM-A-IR- 5287 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43834
4 | WIR | SPML-KCM-A-IR- 5288 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43834
4 | WIR | SPML-KCM-A-IR- 5289 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43935
4 | WIR | SPML-KCM-A-IR- 5290 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43834
4 | WIR | SPML-KCM-A-IR- 5291 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43832
4 | WIR | SPML-KCM-A-IR- 5294 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43835
4 | WIR | SPML-KCM-A-IR- 5295 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5296 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43835
4 | WIR | SPML-KCM-A-IR- 5297 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43932
4 | WIR | SPML-KCM-A-IR- 5298 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43836
4 | WIR | SPML-KCM-A-IR- 5299 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43836
4 | WIR | SPML-KCM-A-IR- 5300 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43836
4 | WIR | SPML-KCM-A-IR- 5301 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5302 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5303 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43839
4 | WIR | SPML-KCM-A-IR- 5304 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 5306 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 5307 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 5309 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 5312 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 5313 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-A-IR- 5314 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43837
4 | WIR | SPML-KCM-A-IR- 5315 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5316 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5317 | Finishes | Green Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 5318 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43838
4 | WIR | SPML-KCM-A-IR- 5319 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43838
4 | WIR | SPML-KCM-A-IR- 5321 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5323 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43838
4 | WIR | SPML-KCM-A-IR- 5326 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5327 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43839
4 | WIR | SPML-KCM-A-IR- 5328 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43839
4 | WIR | SPML-KCM-A-IR- 5329 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43839
4 | WIR | SPML-KCM-A-IR- 5331 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43843
4 | WIR | SPML-KCM-A-IR- 5332 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43841
4 | WIR | SPML-KCM-A-IR- 5333 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43841
4 | WIR | SPML-KCM-A-IR- 5334 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43841
4 | WIR | SPML-KCM-A-IR- 5335 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 5336 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR- 5339 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 5340 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43872
4 | WIR | SPML-KCM-A-IR- 5341 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43841
4 | WIR | SPML-KCM-A-IR- 5342 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43841
4 | WIR | SPML-KCM-A-IR- 5343 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 5344 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43843
4 | WIR | SPML-KCM-A-IR- 5346 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43843
4 | WIR | SPML-KCM-A-IR- 5348 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43844
4 | WIR | SPML-KCM-A-IR- 5349 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5350 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43844
4 | WIR | SPML-KCM-A-IR- 5351 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43844
4 | WIR | SPML-KCM-A-IR- 5352 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5353 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5354 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43922
4 | WIR | SPML-KCM-A-IR- 5355 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43922
4 | WIR | SPML-KCM-A-IR- 5356 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43922
4 | WIR | SPML-KCM-A-IR- 5357 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43922
4 | WIR | SPML-KCM-A-IR- 5358 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43890
4 | WIR | SPML-KCM-A-IR- 5365 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43843
4 | WIR | SPML-KCM-A-IR- 5366 | Finishes | Marble | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 5367 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 5368 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 5369 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 5370 | Paving System | Kerb Stone | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 5371 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 5372 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5373 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5374 | Finishes | Green Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 5375 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44174
4 | WIR | SPML-KCM-A-IR- 5376 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5377 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43848
4 | WIR | SPML-KCM-A-IR- 5378 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5379 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5380 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5381 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5382 | Doors & Windows | Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5383 | Doors & Windows | Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 5384 | Doors & Windows | Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5385 | Doors & Windows | Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5387 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5388 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5389 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43844
4 | WIR | SPML-KCM-A-IR- 5392 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43845
4 | WIR | SPML-KCM-A-IR- 5393 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43845
4 | WIR | SPML-KCM-A-IR- 5394 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43845
4 | WIR | SPML-KCM-A-IR- 5395 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43845
4 | WIR | SPML-KCM-A-IR- 5396 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43845
4 | WIR | SPML-KCM-A-IR- 5397 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 5398 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 5401 | Paving System | Interlock | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 5402 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43939
4 | WIR | SPML-KCM-A-IR- 5403 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43848
4 | WIR | SPML-KCM-A-IR- 5404 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43842
4 | WIR | SPML-KCM-A-IR- 5405 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43848
4 | WIR | SPML-KCM-A-IR- 5406 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 5409 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 5410 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 5411 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 5413 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 5414 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5415 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 5416 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 5417 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 5418 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-A-IR- 5419 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5421 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43850
4 | WIR | SPML-KCM-A-IR- 5422 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43851
4 | WIR | SPML-KCM-A-IR- 5423 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43851
4 | WIR | SPML-KCM-A-IR- 5425 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43956
4 | WIR | SPML-KCM-A-IR- 5426 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 5427 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43925
4 | WIR | SPML-KCM-A-IR- 5428 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43851
4 | WIR | SPML-KCM-A-IR- 5429 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43851
4 | WIR | SPML-KCM-A-IR- 5430 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43851
4 | WIR | SPML-KCM-A-IR- 5431 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43851
4 | WIR | SPML-KCM-A-IR- 5432 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43851
4 | WIR | SPML-KCM-A-IR- 5433 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5435 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR- 5436 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44147
4 | WIR | SPML-KCM-A-IR- 5437 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 5438 | Finishes | Hand Rail | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-A-IR- 5440 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43985
4 | WIR | SPML-KCM-A-IR- 5441 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43983
4 | WIR | SPML-KCM-A-IR- 5442 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43852
4 | WIR | SPML-KCM-A-IR- 5443 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43853
4 | WIR | SPML-KCM-A-IR- 5444 | Sealant | Expansion Joint Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 5445 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43852
4 | WIR | SPML-KCM-A-IR- 5446 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43852
4 | WIR | SPML-KCM-A-IR- 5448 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 5449 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43852
4 | WIR | SPML-KCM-A-IR- 5451 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-A-IR- 5453 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 5454 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 5455 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 5456 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43864
4 | WIR | SPML-KCM-A-IR- 5457 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43855
4 | WIR | SPML-KCM-A-IR- 5458 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 5459 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43855
4 | WIR | SPML-KCM-A-IR- 5460 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43855
4 | WIR | SPML-KCM-A-IR- 5461 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43855
4 | WIR | SPML-KCM-A-IR- 5462 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43855
4 | WIR | SPML-KCM-A-IR- 5463 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43853
4 | WIR | SPML-KCM-A-IR- 5464 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43853
4 | WIR | SPML-KCM-A-IR- 5465 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | C | 43855
4 | WIR | SPML-KCM-A-IR- 5466 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | D | 43857
4 | WIR | SPML-KCM-A-IR- 5467 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43853
4 | WIR | SPML-KCM-A-IR- 5468 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5469 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5470 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43853
4 | WIR | SPML-KCM-A-IR- 5471 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43855
4 | WIR | SPML-KCM-A-IR- 5472 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43855
4 | WIR | SPML-KCM-A-IR- 5473 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43855
4 | WIR | SPML-KCM-A-IR- 5474 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43855
4 | WIR | SPML-KCM-A-IR- 5476 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43856
4 | WIR | SPML-KCM-A-IR- 5477 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43857
4 | WIR | SPML-KCM-A-IR- 5478 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43857
4 | WIR | SPML-KCM-A-IR- 5479 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43857
4 | WIR | SPML-KCM-A-IR- 5480 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43857
4 | WIR | SPML-KCM-A-IR- 5481 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43857
4 | WIR | SPML-KCM-A-IR- 5482 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43857
4 | WIR | SPML-KCM-A-IR- 5483 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43857
4 | WIR | SPML-KCM-A-IR- 5484 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43857
4 | WIR | SPML-KCM-A-IR- 5485 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5486 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44087
4 | WIR | SPML-KCM-A-IR- 5487 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44087
4 | WIR | SPML-KCM-A-IR- 5488 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43857
4 | WIR | SPML-KCM-A-IR- 5489 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43857
4 | WIR | SPML-KCM-A-IR- 5490 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43857
4 | WIR | SPML-KCM-A-IR- 5492 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44170
4 | WIR | SPML-KCM-A-IR- 5493 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5494 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 5495 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 5497 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43967
4 | WIR | SPML-KCM-A-IR- 5498 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 5500 | Finishes | Standing Seem | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5501 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 5503 | Rainwater Management System | Gutter System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 5504 | Roofing and Glazing System | Roof Finishes | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5505 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 5506 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 5507 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 5508 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 5509 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-A-IR- 5510 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-A-IR- 5511 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5512 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 5513 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 5514 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 5515 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 5516 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5517 | GRP System | GRP System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 5518 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 5519 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43836
4 | WIR | SPML-KCM-A-IR- 5520 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43836
4 | WIR | SPML-KCM-A-IR- 5521 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 5522 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-A-IR- 5523 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43859
4 | WIR | SPML-KCM-A-IR- 5524 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43869
4 | WIR | SPML-KCM-A-IR- 5525 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43839
4 | WIR | SPML-KCM-A-IR- 5526 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44019
4 | WIR | SPML-KCM-A-IR- 5527 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43926
4 | WIR | SPML-KCM-A-IR- 5528 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43860
4 | WIR | SPML-KCM-A-IR- 5529 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43860
4 | WIR | SPML-KCM-A-IR- 5530 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44020
4 | WIR | SPML-KCM-A-IR- 5531 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-A-IR- 5532 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43920
4 | WIR | SPML-KCM-A-IR- 5533 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43960
4 | WIR | SPML-KCM-A-IR- 5534 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44025
4 | WIR | SPML-KCM-A-IR- 5535 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43858
4 | WIR | SPML-KCM-A-IR- 5536 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43857
4 | WIR | SPML-KCM-A-IR- 5537 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-A-IR- 5538 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43858
4 | WIR | SPML-KCM-A-IR- 5540 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43773
4 | WIR | SPML-KCM-A-IR- 5541 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44007
4 | WIR | SPML-KCM-A-IR- 5545 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43883
4 | WIR | SPML-KCM-A-IR- 5546 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44137
4 | WIR | SPML-KCM-A-IR- 5547 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43860
4 | WIR | SPML-KCM-A-IR- 5548 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43836
4 | WIR | SPML-KCM-A-IR- 5550 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5552 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43862
4 | WIR | SPML-KCM-A-IR- 5554 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5555 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5556 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 5558 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-A-IR- 5561 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43863
4 | WIR | SPML-KCM-A-IR- 5562 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43836
4 | WIR | SPML-KCM-A-IR- 5563 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5564 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5574 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43863
4 | WIR | SPML-KCM-A-IR- 5575 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43863
4 | WIR | SPML-KCM-A-IR- 5576 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43954
4 | WIR | SPML-KCM-A-IR- 5577 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43863
4 | WIR | SPML-KCM-A-IR- 5578 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43909
4 | WIR | SPML-KCM-A-IR- 5579 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43863
4 | WIR | SPML-KCM-A-IR- 5581 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43836
4 | WIR | SPML-KCM-A-IR- 5584 | Car Park | Gate Barrier | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | C | 43864
4 | WIR | SPML-KCM-A-IR- 5585 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-A-IR- 5586 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-A-IR- 5590 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR- 5591 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 5592 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | B | 43936
4 | WIR | SPML-KCM-A-IR- 5593 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43930
4 | WIR | SPML-KCM-A-IR- 5594 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43866
4 | WIR | SPML-KCM-A-IR- 5599 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44003
4 | WIR | SPML-KCM-A-IR- 5600 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43867
4 | WIR | SPML-KCM-A-IR- 5601 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43867
4 | WIR | SPML-KCM-A-IR- 5602 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43867
4 | WIR | SPML-KCM-A-IR- 5603 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43867
4 | WIR | SPML-KCM-A-IR- 5604 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5607 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43866
4 | WIR | SPML-KCM-A-IR- 5608 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43866
4 | WIR | SPML-KCM-A-IR- 5610 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-A-IR- 5614 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43867
4 | WIR | SPML-KCM-A-IR- 5615 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR- 5616 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-A-IR- 5617 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43872
4 | WIR | SPML-KCM-A-IR- 5619 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43891
4 | WIR | SPML-KCM-A-IR- 5620 | Rainwater Management System | Gutter System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43869
4 | WIR | SPML-KCM-A-IR- 5621 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 5622 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43870
4 | WIR | SPML-KCM-A-IR- 5623 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43871
4 | WIR | SPML-KCM-A-IR- 5624 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43870
4 | WIR | SPML-KCM-A-IR- 5625 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43869
4 | WIR | SPML-KCM-A-IR- 5626 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43869
4 | WIR | SPML-KCM-A-IR- 5627 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43869
4 | WIR | SPML-KCM-A-IR- 5630 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43912
4 | WIR | SPML-KCM-A-IR- 5631 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43870
4 | WIR | SPML-KCM-A-IR- 5632 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43873
4 | WIR | SPML-KCM-A-IR- 5635 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-A-IR- 5636 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR- 5645 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-A-IR- 5647 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43890
4 | WIR | SPML-KCM-A-IR- 5648 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43872
4 | WIR | SPML-KCM-A-IR- 5650 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43873
4 | WIR | SPML-KCM-A-IR- 5652 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43872
4 | WIR | SPML-KCM-A-IR- 5653 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43906
4 | WIR | SPML-KCM-A-IR- 5654 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5655 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44017
4 | WIR | SPML-KCM-A-IR- 5657 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43877
4 | WIR | SPML-KCM-A-IR- 5660 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43877
4 | WIR | SPML-KCM-A-IR- 5663 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43886
4 | WIR | SPML-KCM-A-IR- 5664 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | C | 43877
4 | WIR | SPML-KCM-A-IR- 5665 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44010
4 | WIR | SPML-KCM-A-IR- 5671 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5677 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43873
4 | WIR | SPML-KCM-A-IR- 5678 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43874
4 | WIR | SPML-KCM-A-IR- 5679 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43965
4 | WIR | SPML-KCM-A-IR- 5681 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43946
4 | WIR | SPML-KCM-A-IR- 5684 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43874
4 | WIR | SPML-KCM-A-IR- 5685 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43873
4 | WIR | SPML-KCM-A-IR- 5686 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43873
4 | WIR | SPML-KCM-A-IR- 5687 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43876
4 | WIR | SPML-KCM-A-IR- 5688 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43877
4 | WIR | SPML-KCM-A-IR- 5689 | GRP System | GRP Lining | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44175
4 | WIR | SPML-KCM-A-IR- 5690 | GRP System | GRP Lining | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 5692 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43876
4 | WIR | SPML-KCM-A-IR- 5693 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43876
4 | WIR | SPML-KCM-A-IR- 5695 | Car Park | Car Park Numbering | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 5696 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43886
4 | WIR | SPML-KCM-A-IR- 5697 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43918
4 | WIR | SPML-KCM-A-IR- 5698 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 5699 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43957
4 | WIR | SPML-KCM-A-IR- 5700 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5701 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43925
4 | WIR | SPML-KCM-A-IR- 5702 | Finishes | Marble | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5703 | Finishes | Vanity Countertop | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 5704 | Finishes | Vanity Countertop | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 5706 | Finishes | Vanity Countertop | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5707 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43877
4 | WIR | SPML-KCM-A-IR- 5710 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43731
4 | WIR | SPML-KCM-A-IR- 5712 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43881
4 | WIR | SPML-KCM-A-IR- 5713 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 5714 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR- 5715 | GRP System | GRP System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 5716 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43920
4 | WIR | SPML-KCM-A-IR- 5718 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43881
4 | WIR | SPML-KCM-A-IR- 5719 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43879
4 | WIR | SPML-KCM-A-IR- 5720 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43891
4 | WIR | SPML-KCM-A-IR- 5722 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43989
4 | WIR | SPML-KCM-A-IR- 5724 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43892
4 | WIR | SPML-KCM-A-IR- 5725 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43879
4 | WIR | SPML-KCM-A-IR- 5726 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43869
4 | WIR | SPML-KCM-A-IR- 5727 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR- 5728 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43879
4 | WIR | SPML-KCM-A-IR- 5731 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43880
4 | WIR | SPML-KCM-A-IR- 5732 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43880
4 | WIR | SPML-KCM-A-IR- 5733 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43880
4 | WIR | SPML-KCM-A-IR- 5734 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43953
4 | WIR | SPML-KCM-A-IR- 5735 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43879
4 | WIR | SPML-KCM-A-IR- 5736 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43879
4 | WIR | SPML-KCM-A-IR- 5737 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43879
4 | WIR | SPML-KCM-A-IR- 5738 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5739 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43872
4 | WIR | SPML-KCM-A-IR- 5740 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43883
4 | WIR | SPML-KCM-A-IR- 5743 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43897
4 | WIR | SPML-KCM-A-IR- 5745 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44142
4 | WIR | SPML-KCM-A-IR- 5746 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44175
4 | WIR | SPML-KCM-A-IR- 5747 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43883
4 | WIR | SPML-KCM-A-IR- 5748 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43918
4 | WIR | SPML-KCM-A-IR- 5749 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43918
4 | WIR | SPML-KCM-A-IR- 5750 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43918
4 | WIR | SPML-KCM-A-IR- 5751 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR- 5752 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5754 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 5755 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43898
4 | WIR | SPML-KCM-A-IR- 5756 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5757 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43881
4 | WIR | SPML-KCM-A-IR- 5759 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-A-IR- 5760 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43988
4 | WIR | SPML-KCM-A-IR- 5764 | GRP System | GRP Lining | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 5765 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5766 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43893
4 | WIR | SPML-KCM-A-IR- 5769 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43883
4 | WIR | SPML-KCM-A-IR- 5772 | Sealant | Expansion Joint Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43955
4 | WIR | SPML-KCM-A-IR- 5773 | Sealant | Expansion Joint Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43955
4 | WIR | SPML-KCM-A-IR- 5774 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43953
4 | WIR | SPML-KCM-A-IR- 5775 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43953
4 | WIR | SPML-KCM-A-IR- 5777 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44147
4 | WIR | SPML-KCM-A-IR- 5778 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43892
4 | WIR | SPML-KCM-A-IR- 5780 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43893
4 | WIR | SPML-KCM-A-IR- 5782 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 5783 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 5785 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43918
4 | WIR | SPML-KCM-A-IR- 5786 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-A-IR- 5787 | Finishes | Green Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-A-IR- 5788 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43890
4 | WIR | SPML-KCM-A-IR- 5789 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43890
4 | WIR | SPML-KCM-A-IR- 5790 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR- 5796 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43954
4 | WIR | SPML-KCM-A-IR- 5799 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43936
4 | WIR | SPML-KCM-A-IR- 5800 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5801 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43893
4 | WIR | SPML-KCM-A-IR- 5802 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43867
4 | WIR | SPML-KCM-A-IR- 5803 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43892
4 | WIR | SPML-KCM-A-IR- 5810 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5814 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43890
4 | WIR | SPML-KCM-A-IR- 5815 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43866
4 | WIR | SPML-KCM-A-IR- 5816 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43946
4 | WIR | SPML-KCM-A-IR- 5817 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43946
4 | WIR | SPML-KCM-A-IR- 5818 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43946
4 | WIR | SPML-KCM-A-IR- 5819 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43946
4 | WIR | SPML-KCM-A-IR- 5821 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43939
4 | WIR | SPML-KCM-A-IR- 5822 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR- 5824 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43890
4 | WIR | SPML-KCM-A-IR- 5825 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43895
4 | WIR | SPML-KCM-A-IR- 5826 | Paving System | Interlock | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 5827 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5829 | Paving System | Interlock | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5830 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44149
4 | WIR | SPML-KCM-A-IR- 5835 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43890
4 | WIR | SPML-KCM-A-IR- 5836 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43992
4 | WIR | SPML-KCM-A-IR- 5837 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43894
4 | WIR | SPML-KCM-A-IR- 5838 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43894
4 | WIR | SPML-KCM-A-IR- 5839 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5840 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44203
4 | WIR | SPML-KCM-A-IR- 5841 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 5842 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44132
4 | WIR | SPML-KCM-A-IR- 5843 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-A-IR- 5844 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5849 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-A-IR- 5850 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-A-IR- 5851 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43937
4 | WIR | SPML-KCM-A-IR- 5852 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43895
4 | WIR | SPML-KCM-A-IR- 5853 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43955
4 | WIR | SPML-KCM-A-IR- 5854 | GRP System | GRP Lining | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 5855 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43894
4 | WIR | SPML-KCM-A-IR- 5856 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43894
4 | WIR | SPML-KCM-A-IR- 5857 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 5858 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43893
4 | WIR | SPML-KCM-A-IR- 5859 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43893
4 | WIR | SPML-KCM-A-IR- 5868 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43908
4 | WIR | SPML-KCM-A-IR- 5871 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43894
4 | WIR | SPML-KCM-A-IR- 5872 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43905
4 | WIR | SPML-KCM-A-IR- 5874 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43897
4 | WIR | SPML-KCM-A-IR- 5875 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43939
4 | WIR | SPML-KCM-A-IR- 5876 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 5880 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 5882 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43883
4 | WIR | SPML-KCM-A-IR- 5884 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 5885 | Car Park | Car Park Shade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 5888 | Finishes | Column Guard | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 5892 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43900
4 | WIR | SPML-KCM-A-IR- 5894 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43898
4 | WIR | SPML-KCM-A-IR- 5895 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43898
4 | WIR | SPML-KCM-A-IR- 5896 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43902
4 | WIR | SPML-KCM-A-IR- 5897 | Car Park | Car Park Shade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 5904 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43898
4 | WIR | SPML-KCM-A-IR- 5905 | Pole | Street Light Pole | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 5906 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43897
4 | WIR | SPML-KCM-A-IR- 5907 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43900
4 | WIR | SPML-KCM-A-IR- 5908 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 5909 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 5910 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44086
4 | WIR | SPML-KCM-A-IR- 5911 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43898
4 | WIR | SPML-KCM-A-IR- 5915 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44254
4 | WIR | SPML-KCM-A-IR- 5919 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 5920 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44101
4 | WIR | SPML-KCM-A-IR- 5921 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 5923 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44205
4 | WIR | SPML-KCM-A-IR- 5924 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43900
4 | WIR | SPML-KCM-A-IR- 5927 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43900
4 | WIR | SPML-KCM-A-IR- 5928 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43900
4 | WIR | SPML-KCM-A-IR- 5929 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 5930 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43782
4 | WIR | SPML-KCM-A-IR- 5931 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44101
4 | WIR | SPML-KCM-A-IR- 5932 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44101
4 | WIR | SPML-KCM-A-IR- 5933 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 5934 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 5935 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 5936 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43935
4 | WIR | SPML-KCM-A-IR- 5937 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR- 5938 | Finishes | Channel Grating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 5939 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 5940 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR- 5941 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 5942 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43902
4 | WIR | SPML-KCM-A-IR- 5943 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43902
4 | WIR | SPML-KCM-A-IR- 5946 | Finishes | Hand Rail | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 5947 | Finishes | Hand Rail | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 5948 | Finishes | Hand Rail | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 5949 | Finishes | Hand Rail | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 5950 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43900
4 | WIR | SPML-KCM-A-IR- 5951 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43946
4 | WIR | SPML-KCM-A-IR- 5957 | Doors & Windows | Aluminium Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 5958 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 5959 | Paving System | Kerb Stone | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43901
4 | WIR | SPML-KCM-A-IR- 5960 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 5961 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5963 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5964 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43901
4 | WIR | SPML-KCM-A-IR- 5965 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 5966 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44108
4 | WIR | SPML-KCM-A-IR- 5968 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43902
4 | WIR | SPML-KCM-A-IR- 5969 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43904
4 | WIR | SPML-KCM-A-IR- 5970 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43904
4 | WIR | SPML-KCM-A-IR- 5971 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR- 5972 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44089
4 | WIR | SPML-KCM-A-IR- 5973 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43902
4 | WIR | SPML-KCM-A-IR- 5979 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43997
4 | WIR | SPML-KCM-A-IR- 5980 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43905
4 | WIR | SPML-KCM-A-IR- 5981 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43904
4 | WIR | SPML-KCM-A-IR- 5982 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43904
4 | WIR | SPML-KCM-A-IR- 5983 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43904
4 | WIR | SPML-KCM-A-IR- 5984 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-A-IR- 5985 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 5995 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43905
4 | WIR | SPML-KCM-A-IR- 5996 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43905
4 | WIR | SPML-KCM-A-IR- 5998 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-A-IR- 5999 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43908
4 | WIR | SPML-KCM-A-IR- 6000 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43911
4 | WIR | SPML-KCM-A-IR- 6001 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR- 6006 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR- 6007 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR- 6011 | Column | Numbering | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6016 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43911
4 | WIR | SPML-KCM-A-IR- 6017 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43911
4 | WIR | SPML-KCM-A-IR- 6019 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43944
4 | WIR | SPML-KCM-A-IR- 6020 | Rainwater Management System | Gutter System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6021 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43946
4 | WIR | SPML-KCM-A-IR- 6022 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44005
4 | WIR | SPML-KCM-A-IR- 6028 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43909
4 | WIR | SPML-KCM-A-IR- 6029 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43911
4 | WIR | SPML-KCM-A-IR- 6034 | Doors & Windows | Aluminium Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6035 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43913
4 | WIR | SPML-KCM-A-IR- 6036 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43911
4 | WIR | SPML-KCM-A-IR- 6041 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6042 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43912
4 | WIR | SPML-KCM-A-IR- 6043 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43921
4 | WIR | SPML-KCM-A-IR- 6044 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44026
4 | WIR | SPML-KCM-A-IR- 6048 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6049 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43912
4 | WIR | SPML-KCM-A-IR- 6052 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6059 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6061 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43915
4 | WIR | SPML-KCM-A-IR- 6063 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6065 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44233
4 | WIR | SPML-KCM-A-IR- 6066 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6067 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43914
4 | WIR | SPML-KCM-A-IR- 6071 | Cladding | Glass Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44124
4 | WIR | SPML-KCM-A-IR- 6072 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43914
4 | WIR | SPML-KCM-A-IR- 6073 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43918
4 | WIR | SPML-KCM-A-IR- 6074 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43918
4 | WIR | SPML-KCM-A-IR- 6075 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43926
4 | WIR | SPML-KCM-A-IR- 6076 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 6077 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43932
4 | WIR | SPML-KCM-A-IR- 6078 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43914
4 | WIR | SPML-KCM-A-IR- 6079 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43915
4 | WIR | SPML-KCM-A-IR- 6080 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43918
4 | WIR | SPML-KCM-A-IR- 6081 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43919
4 | WIR | SPML-KCM-A-IR- 6082 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43926
4 | WIR | SPML-KCM-A-IR- 6083 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6084 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43914
4 | WIR | SPML-KCM-A-IR- 6085 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6086 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43914
4 | WIR | SPML-KCM-A-IR- 6088 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 6089 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6091 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44017
4 | WIR | SPML-KCM-A-IR- 6095 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6096 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 6097 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 6098 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 6107 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43955
4 | WIR | SPML-KCM-A-IR- 6108 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43919
4 | WIR | SPML-KCM-A-IR- 6112 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 6113 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44203
4 | WIR | SPML-KCM-A-IR- 6114 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 6116 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43926
4 | WIR | SPML-KCM-A-IR- 6117 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43927
4 | WIR | SPML-KCM-A-IR- 6118 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43930
4 | WIR | SPML-KCM-A-IR- 6119 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43932
4 | WIR | SPML-KCM-A-IR- 6120 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43927
4 | WIR | SPML-KCM-A-IR- 6121 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43930
4 | WIR | SPML-KCM-A-IR- 6123 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43927
4 | WIR | SPML-KCM-A-IR- 6124 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43932
4 | WIR | SPML-KCM-A-IR- 6125 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43927
4 | WIR | SPML-KCM-A-IR- 6126 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43932
4 | WIR | SPML-KCM-A-IR- 6127 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6128 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43930
4 | WIR | SPML-KCM-A-IR- 6129 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43933
4 | WIR | SPML-KCM-A-IR- 6130 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44130
4 | WIR | SPML-KCM-A-IR- 6131 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44130
4 | WIR | SPML-KCM-A-IR- 6133 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44137
4 | WIR | SPML-KCM-A-IR- 6134 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44142
4 | WIR | SPML-KCM-A-IR- 6135 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43981
4 | WIR | SPML-KCM-A-IR- 6136 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44210
4 | WIR | SPML-KCM-A-IR- 6137 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44210
4 | WIR | SPML-KCM-A-IR- 6140 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43921
4 | WIR | SPML-KCM-A-IR- 6141 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43921
4 | WIR | SPML-KCM-A-IR- 6144 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43921
4 | WIR | SPML-KCM-A-IR- 6145 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6148 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43999
4 | WIR | SPML-KCM-A-IR- 6149 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43922
4 | WIR | SPML-KCM-A-IR- 6150 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR- 6151 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6152 | Finishes | Baffle Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44119
4 | WIR | SPML-KCM-A-IR- 6153 | Finishes | Canopy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6155 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43923
4 | WIR | SPML-KCM-A-IR- 6156 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43923
4 | WIR | SPML-KCM-A-IR- 6159 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43927
4 | WIR | SPML-KCM-A-IR- 6160 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6161 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43927
4 | WIR | SPML-KCM-A-IR- 6162 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43927
4 | WIR | SPML-KCM-A-IR- 6163 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43927
4 | WIR | SPML-KCM-A-IR- 6164 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43927
4 | WIR | SPML-KCM-A-IR- 6165 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43927
4 | WIR | SPML-KCM-A-IR- 6166 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43925
4 | WIR | SPML-KCM-A-IR- 6167 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43925
4 | WIR | SPML-KCM-A-IR- 6171 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6172 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43909
4 | WIR | SPML-KCM-A-IR- 6173 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43907
4 | WIR | SPML-KCM-A-IR- 6174 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43905
4 | WIR | SPML-KCM-A-IR- 6175 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43901
4 | WIR | SPML-KCM-A-IR- 6176 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 6177 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6179 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6181 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6182 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43926
4 | WIR | SPML-KCM-A-IR- 6183 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 6185 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43926
4 | WIR | SPML-KCM-A-IR- 6186 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43926
4 | WIR | SPML-KCM-A-IR- 6187 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43926
4 | WIR | SPML-KCM-A-IR- 6188 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6189 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43926
4 | WIR | SPML-KCM-A-IR- 6191 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6195 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43929
4 | WIR | SPML-KCM-A-IR- 6196 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43929
4 | WIR | SPML-KCM-A-IR- 6197 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43929
4 | WIR | SPML-KCM-A-IR- 6198 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43929
4 | WIR | SPML-KCM-A-IR- 6199 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44137
4 | WIR | SPML-KCM-A-IR- 6201 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6202 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 6203 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 6204 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43930
4 | WIR | SPML-KCM-A-IR- 6205 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43930
4 | WIR | SPML-KCM-A-IR- 6206 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43930
4 | WIR | SPML-KCM-A-IR- 6207 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6208 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6209 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43930
4 | WIR | SPML-KCM-A-IR- 6210 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43930
4 | WIR | SPML-KCM-A-IR- 6211 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43930
4 | WIR | SPML-KCM-A-IR- 6212 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 6213 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 6214 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43930
4 | WIR | SPML-KCM-A-IR- 6215 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43930
4 | WIR | SPML-KCM-A-IR- 6216 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43932
4 | WIR | SPML-KCM-A-IR- 6219 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6220 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR- 6221 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43946
4 | WIR | SPML-KCM-A-IR- 6222 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43946
4 | WIR | SPML-KCM-A-IR- 6223 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44129
4 | WIR | SPML-KCM-A-IR- 6224 | Finishes | Aluminium Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43985
4 | WIR | SPML-KCM-A-IR- 6228 | Column | Numbering | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6229 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43972
4 | WIR | SPML-KCM-A-IR- 6230 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43933
4 | WIR | SPML-KCM-A-IR- 6231 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43953
4 | WIR | SPML-KCM-A-IR- 6238 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 6239 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43934
4 | WIR | SPML-KCM-A-IR- 6240 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6241 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6242 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6246 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44124
4 | WIR | SPML-KCM-A-IR- 6257 | Finishes | Marble | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6259 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 6262 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6263 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 6264 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43951
4 | WIR | SPML-KCM-A-IR- 6265 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43936
4 | WIR | SPML-KCM-A-IR- 6266 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 6268 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR- 6269 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 6272 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6276 | Finishes | Aluminium Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6278 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43942
4 | WIR | SPML-KCM-A-IR- 6281 | Cladding | Glass Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6285 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43943
4 | WIR | SPML-KCM-A-IR- 6286 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43943
4 | WIR | SPML-KCM-A-IR- 6291 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43946
4 | WIR | SPML-KCM-A-IR- 6299 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43951
4 | WIR | SPML-KCM-A-IR- 6302 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6307 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43955
4 | WIR | SPML-KCM-A-IR- 6308 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43957
4 | WIR | SPML-KCM-A-IR- 6309 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43956
4 | WIR | SPML-KCM-A-IR- 6316 | Finishes | Aesthetic Finishes | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43958
4 | WIR | SPML-KCM-A-IR- 6317 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6318 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6319 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44205
4 | WIR | SPML-KCM-A-IR- 6320 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 6324 | Finishes | Baffle Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 6325 | Finishes | Marble | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6326 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 6334 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6335 | Space Protection System | Bollards | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44167
4 | WIR | SPML-KCM-A-IR- 6336 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44131
4 | WIR | SPML-KCM-A-IR- 6337 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 6338 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43964
4 | WIR | SPML-KCM-A-IR- 6339 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6342 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44214
4 | WIR | SPML-KCM-A-IR- 6343 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44214
4 | WIR | SPML-KCM-A-IR- 6346 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44005
4 | WIR | SPML-KCM-A-IR- 6350 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6351 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6352 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6356 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44132
4 | WIR | SPML-KCM-A-IR- 6358 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43970
4 | WIR | SPML-KCM-A-IR- 6360 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6361 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 6362 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 6363 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 6364 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR- 6365 | Space Protection System | Bollards | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6366 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6370 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43978
4 | WIR | SPML-KCM-A-IR- 6371 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43981
4 | WIR | SPML-KCM-A-IR- 6372 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43978
4 | WIR | SPML-KCM-A-IR- 6373 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6375 | FF&E | Utility Cabinet | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44040
4 | WIR | SPML-KCM-A-IR- 6383 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-A-IR- 6388 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 6390 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44034
4 | WIR | SPML-KCM-A-IR- 6394 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6395 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6399 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6400 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44035
4 | WIR | SPML-KCM-A-IR- 6401 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44118
4 | WIR | SPML-KCM-A-IR- 6402 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6408 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6409 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6412 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6413 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6414 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 6415 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-A-IR- 6417 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44040
4 | WIR | SPML-KCM-A-IR- 6418 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44048
4 | WIR | SPML-KCM-A-IR- 6431 | Doors & Windows | Aluminium Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6435 | Space Protection System | Bollards | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR- 6441 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44138
4 | WIR | SPML-KCM-A-IR- 6442 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44147
4 | WIR | SPML-KCM-A-IR- 6443 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44074
4 | WIR | SPML-KCM-A-IR- 6445 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR- 6447 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44060
4 | WIR | SPML-KCM-A-IR- 6448 | Finishes | Aluminium Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44060
4 | WIR | SPML-KCM-A-IR- 6449 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6457 | Glazing | Balustrade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6458 | Glazing | Balustrade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 6461 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44084
4 | WIR | SPML-KCM-A-IR- 6463 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44203
4 | WIR | SPML-KCM-A-IR- 6464 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 6465 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44203
4 | WIR | SPML-KCM-A-IR- 6466 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 6481 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44069
4 | WIR | SPML-KCM-A-IR- 6485 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 6486 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44070
4 | WIR | SPML-KCM-A-IR- 6488 | Finishes | Grating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6489 | Pole | Light Pole | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6490 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6491 | Finishes | Baffle Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-A-IR- 6495 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR- 6496 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44074
4 | WIR | SPML-KCM-A-IR- 6498 | Cladding | Glass Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6499 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44205
4 | WIR | SPML-KCM-A-IR- 6500 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6502 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 6504 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 6505 | Loading Bay Equipment System | Overhead Door | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44081
4 | WIR | SPML-KCM-A-IR- 6506 | Loading Bay Equipment System | Overhead Door | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 6507 | Loading Bay Equipment System | Overhead Door | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44081
4 | WIR | SPML-KCM-A-IR- 6508 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-A-IR- 6510 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6511 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6512 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6513 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44053
4 | WIR | SPML-KCM-A-IR- 6514 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR- 6515 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR- 6516 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 6517 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44066
4 | WIR | SPML-KCM-A-IR- 6518 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6519 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44056
4 | WIR | SPML-KCM-A-IR- 6520 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 6521 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR- 6522 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43589
4 | WIR | SPML-KCM-A-IR- 6523 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43589
4 | WIR | SPML-KCM-A-IR- 6526 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44075
4 | WIR | SPML-KCM-A-IR- 6527 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 6528 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 6529 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44093
4 | WIR | SPML-KCM-A-IR- 6530 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6532 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR- 6534 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6536 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44124
4 | WIR | SPML-KCM-A-IR- 6537 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44128
4 | WIR | SPML-KCM-A-IR- 6539 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6540 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 6541 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 6542 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44261
4 | WIR | SPML-KCM-A-IR- 6546 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44090
4 | WIR | SPML-KCM-A-IR- 6547 | Cladding | Glass Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44254
4 | WIR | SPML-KCM-A-IR- 6554 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6556 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6557 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44048
4 | WIR | SPML-KCM-A-IR- 6558 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR- 6559 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 6560 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44093
4 | WIR | SPML-KCM-A-IR- 6561 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44118
4 | WIR | SPML-KCM-A-IR- 6562 | Sealant | Fire Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44084
4 | WIR | SPML-KCM-A-IR- 6563 | Sealant | Fire Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44084
4 | WIR | SPML-KCM-A-IR- 6564 | Sealant | Fire Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44084
4 | WIR | SPML-KCM-A-IR- 6565 | Sealant | Fire Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44084
4 | WIR | SPML-KCM-A-IR- 6566 | Sealant | Fire Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44084
4 | WIR | SPML-KCM-A-IR- 6567 | Sealant | Fire Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44084
4 | WIR | SPML-KCM-A-IR- 6569 | Cladding | Glass Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6570 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR- 6571 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 6575 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6576 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44076
4 | WIR | SPML-KCM-A-IR- 6577 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 6579 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6581 | Finishes | Aluminium Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 6583 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6584 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6587 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 6588 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-A-IR- 6589 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44087
4 | WIR | SPML-KCM-A-IR- 6590 | Finishes | Aluminium Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44124
4 | WIR | SPML-KCM-A-IR- 6591 | FF&E | Wooden Benches | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 6592 | FF&E | Wooden Benches | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44150
4 | WIR | SPML-KCM-A-IR- 6593 | FF&E | Wooden Benches | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR- 6594 | Finishes | Wooden Partition | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44139
4 | WIR | SPML-KCM-A-IR- 6595 | Finishes | Wooden Partition | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44088
4 | WIR | SPML-KCM-A-IR- 6596 | Finishes | Louvre | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 6597 | Finishes | Louvre | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6598 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6599 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 6601 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6603 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44098
4 | WIR | SPML-KCM-A-IR- 6605 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44088
4 | WIR | SPML-KCM-A-IR- 6606 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44088
4 | WIR | SPML-KCM-A-IR- 6607 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6608 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44122
4 | WIR | SPML-KCM-A-IR- 6609 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6611 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44124
4 | WIR | SPML-KCM-A-IR- 6612 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6613 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44089
4 | WIR | SPML-KCM-A-IR- 6614 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44089
4 | WIR | SPML-KCM-A-IR- 6615 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44095
4 | WIR | SPML-KCM-A-IR- 6616 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6617 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44137
4 | WIR | SPML-KCM-A-IR- 6618 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-A-IR- 6619 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-A-IR- 6620 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44128
4 | WIR | SPML-KCM-A-IR- 6622 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44089
4 | WIR | SPML-KCM-A-IR- 6625 | Doors & Windows | Sliding Door | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 6626 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 6627 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44091
4 | WIR | SPML-KCM-A-IR- 6628 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 6630 | FF&E | Wooden Benches | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44090
4 | WIR | SPML-KCM-A-IR- 6631 | FF&E | Wooden Benches | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44090
4 | WIR | SPML-KCM-A-IR- 6632 | FF&E | Wooden Benches | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44090
4 | WIR | SPML-KCM-A-IR- 6636 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44080
4 | WIR | SPML-KCM-A-IR- 6637 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 6638 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44095
4 | WIR | SPML-KCM-A-IR- 6639 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR- 6640 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44044
4 | WIR | SPML-KCM-A-IR- 6641 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6644 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR- 6646 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR- 6647 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6648 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44124
4 | WIR | SPML-KCM-A-IR- 6649 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44094
4 | WIR | SPML-KCM-A-IR- 6653 | Doors & Windows | GSM Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6656 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6661 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6662 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6664 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43955
4 | WIR | SPML-KCM-A-IR- 6665 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR- 6666 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-A-IR- 6667 | Finishes | Marble | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 6668 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6669 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6670 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 6671 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44105
4 | WIR | SPML-KCM-A-IR- 6672 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44096
4 | WIR | SPML-KCM-A-IR- 6673 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44098
4 | WIR | SPML-KCM-A-IR- 6675 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44097
4 | WIR | SPML-KCM-A-IR- 6676 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 6677 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6678 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 6681 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-A-IR- 6682 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6683 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6684 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR- 6685 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44098
4 | WIR | SPML-KCM-A-IR- 6686 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 6687 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44103
4 | WIR | SPML-KCM-A-IR- 6688 | Finishes | Mirror | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44175
4 | WIR | SPML-KCM-A-IR- 6689 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6690 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-A-IR- 6691 | Finishes | Mirror | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44175
4 | WIR | SPML-KCM-A-IR- 6692 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6693 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6696 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44101
4 | WIR | SPML-KCM-A-IR- 6700 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44101
4 | WIR | SPML-KCM-A-IR- 6701 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44102
4 | WIR | SPML-KCM-A-IR- 6704 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6705 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6708 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6710 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6711 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6712 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6713 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6714 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6715 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44118
4 | WIR | SPML-KCM-A-IR- 6716 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6717 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6718 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6720 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-A-IR- 6721 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR- 6722 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44104
4 | WIR | SPML-KCM-A-IR- 6727 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-A-IR- 6729 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44128
4 | WIR | SPML-KCM-A-IR- 6730 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44137
4 | WIR | SPML-KCM-A-IR- 6731 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6732 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44107
4 | WIR | SPML-KCM-A-IR- 6733 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44107
4 | WIR | SPML-KCM-A-IR- 6734 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44107
4 | WIR | SPML-KCM-A-IR- 6736 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 6737 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44089
4 | WIR | SPML-KCM-A-IR- 6738 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44109
4 | WIR | SPML-KCM-A-IR- 6739 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44088
4 | WIR | SPML-KCM-A-IR- 6740 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44109
4 | WIR | SPML-KCM-A-IR- 6741 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44087
4 | WIR | SPML-KCM-A-IR- 6742 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44105
4 | WIR | SPML-KCM-A-IR- 6743 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44109
4 | WIR | SPML-KCM-A-IR- 6744 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR- 6745 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-A-IR- 6746 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44206
4 | WIR | SPML-KCM-A-IR- 6748 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44199
4 | WIR | SPML-KCM-A-IR- 6750 | FF&E | Totem | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44107
4 | WIR | SPML-KCM-A-IR- 6751 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44206
4 | WIR | SPML-KCM-A-IR- 6752 | Parking Bay Accessories | Handicapped Parking | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6755 | Finishes | Column Guard | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 6756 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44117
4 | WIR | SPML-KCM-A-IR- 6757 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 6758 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44108
4 | WIR | SPML-KCM-A-IR- 6759 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44107
4 | WIR | SPML-KCM-A-IR- 6760 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR- 6761 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44107
4 | WIR | SPML-KCM-A-IR- 6762 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR- 6765 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44075
4 | WIR | SPML-KCM-A-IR- 6766 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44080
4 | WIR | SPML-KCM-A-IR- 6769 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44144
4 | WIR | SPML-KCM-A-IR- 6770 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44151
4 | WIR | SPML-KCM-A-IR- 6771 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR- 6772 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43852
4 | WIR | SPML-KCM-A-IR- 6773 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43855
4 | WIR | SPML-KCM-A-IR- 6774 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6775 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44124
4 | WIR | SPML-KCM-A-IR- 6777 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6778 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44108
4 | WIR | SPML-KCM-A-IR- 6779 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44108
4 | WIR | SPML-KCM-A-IR- 6780 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44108
4 | WIR | SPML-KCM-A-IR- 6781 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6782 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6783 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44140
4 | WIR | SPML-KCM-A-IR- 6786 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44109
4 | WIR | SPML-KCM-A-IR- 6787 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44109
4 | WIR | SPML-KCM-A-IR- 6788 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44109
4 | WIR | SPML-KCM-A-IR- 6789 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44109
4 | WIR | SPML-KCM-A-IR- 6790 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44109
4 | WIR | SPML-KCM-A-IR- 6791 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44109
4 | WIR | SPML-KCM-A-IR- 6792 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44138
4 | WIR | SPML-KCM-A-IR- 6800 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6801 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-A-IR- 6802 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6803 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6804 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6805 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-A-IR- 6806 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 6807 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44110
4 | WIR | SPML-KCM-A-IR- 6808 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6809 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-A-IR- 6810 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6811 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44110
4 | WIR | SPML-KCM-A-IR- 6812 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6813 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6814 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6816 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6817 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-A-IR- 6818 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 6823 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6824 | Finishes | Urinals | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6825 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6826 | Finishes | Urinals | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6827 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6828 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6829 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR- 6830 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6831 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44203
4 | WIR | SPML-KCM-A-IR- 6835 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6844 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6857 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6858 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44128
4 | WIR | SPML-KCM-A-IR- 6859 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 6860 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6861 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6862 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6863 | FF&E | Totem | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR- 6865 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6866 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6867 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6868 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6869 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6870 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6871 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR- 6872 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 6873 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR- 6876 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 6878 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 6879 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 6881 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-A-IR- 6885 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-A-IR- 6886 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-A-IR- 6887 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-A-IR- 6888 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6889 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-A-IR- 6896 | Rainwater Management System | Gutters | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6898 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-A-IR- 6899 | Finishes | Aluminum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44119
4 | WIR | SPML-KCM-A-IR- 6913 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6915 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6918 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6924 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR- 6925 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6927 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6928 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 6929 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 6930 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 6931 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44112
4 | WIR | SPML-KCM-A-IR- 6933 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6935 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44123
4 | WIR | SPML-KCM-A-IR- 6937 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6938 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6939 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44184
4 | WIR | SPML-KCM-A-IR- 6940 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR- 6941 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 6942 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-A-IR- 6943 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6952 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 6954 | Finishes | OTS Hand Rail | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR- 6955 | Paving System | Interlock | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6956 | Paving System | Kerb Stone | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6966 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR- 6972 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6973 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44117
4 | WIR | SPML-KCM-A-IR- 6974 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6976 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6985 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6986 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6987 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6988 | Finishes | Stucco Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-A-IR- 6991 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44144
4 | WIR | SPML-KCM-A-IR- 6992 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44144
4 | WIR | SPML-KCM-A-IR- 6996 | Manhole | Manhole | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR- 6997 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44117
4 | WIR | SPML-KCM-A-IR- 6999 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR- 7001 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44221
4 | WIR | SPML-KCM-A-IR- 7080 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-A-IR- 7081 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR- 7082 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR- 7132 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 7133 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR- 7134 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR- 7135 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR- 7140 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR- 7141 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR- 7142 | Doors & Windows | Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44129
4 | WIR | SPML-KCM-A-IR-2428 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-A-IR-2448 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-A-IR-2537 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43506
4 | WIR | SPML-KCM-A-IR-2538 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43506
4 | WIR | SPML-KCM-A-IR-2546 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-A-IR-2564 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43507
4 | WIR | SPML-KCM-A-IR-2565 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43507
4 | WIR | SPML-KCM-A-IR-2620 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-A-IR-2667 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-A-IR-2719 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43521
4 | WIR | SPML-KCM-A-IR-2784 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-A-IR-2785 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-A-IR-6158 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44093
4 | WIR | SPML-KCM-A-IR-6978 | Paving System | Interlock | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44179
4 | WIR | SPML-KCM-A-IR-7002 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR-7017 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44128
4 | WIR | SPML-KCM-A-IR-7020 | Paving System | Kerb Stone | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7022 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7023 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7026 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44129
4 | WIR | SPML-KCM-A-IR-7027 | Space Protection System | Bollards | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44137
4 | WIR | SPML-KCM-A-IR-7029 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR-7030 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44121
4 | WIR | SPML-KCM-A-IR-7031 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44121
4 | WIR | SPML-KCM-A-IR-7032 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7033 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR-7034 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44121
4 | WIR | SPML-KCM-A-IR-7035 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44121
4 | WIR | SPML-KCM-A-IR-7036 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44121
4 | WIR | SPML-KCM-A-IR-7037 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44118
4 | WIR | SPML-KCM-A-IR-7038 | Finishes | Baffle Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-A-IR-7039 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44121
4 | WIR | SPML-KCM-A-IR-7040 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR-7043 | Cladding | ACP Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR-7045 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44129
4 | WIR | SPML-KCM-A-IR-7046 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR-7047 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44128
4 | WIR | SPML-KCM-A-IR-7048 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44128
4 | WIR | SPML-KCM-A-IR-7049 | Finishes | Mirror | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44175
4 | WIR | SPML-KCM-A-IR-7050 | Cladding | Wooden Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7051 | Finishes | Mirror | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44175
4 | WIR | SPML-KCM-A-IR-7052 | Finishes | Mirror | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44175
4 | WIR | SPML-KCM-A-IR-7053 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44129
4 | WIR | SPML-KCM-A-IR-7054 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44129
4 | WIR | SPML-KCM-A-IR-7055 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR-7056 | Cladding | Glass Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44128
4 | WIR | SPML-KCM-A-IR-7058 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44121
4 | WIR | SPML-KCM-A-IR-7065 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR-7066 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR-7067 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR-7068 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR-7069 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7073 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7074 | Car Park | Car Park Shade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7078 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR-7084 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44123
4 | WIR | SPML-KCM-A-IR-7086 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR-7095 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR-7096 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44119
4 | WIR | SPML-KCM-A-IR-7097 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44119
4 | WIR | SPML-KCM-A-IR-7098 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44138
4 | WIR | SPML-KCM-A-IR-7099 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44138
4 | WIR | SPML-KCM-A-IR-7100 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44138
4 | WIR | SPML-KCM-A-IR-7103 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7104 | Finishes | Canopy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7105 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7106 | Finishes | OTS Hand Rail | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7113 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-A-IR-7122 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7126 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44123
4 | WIR | SPML-KCM-A-IR-7127 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44123
4 | WIR | SPML-KCM-A-IR-7128 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44123
4 | WIR | SPML-KCM-A-IR-7129 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-A-IR-7145 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44206
4 | WIR | SPML-KCM-A-IR-7146 | Finishes | Wall Sticker | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7147 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7149 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44130
4 | WIR | SPML-KCM-A-IR-7162 | GRP System | GRP Lining | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44175
4 | WIR | SPML-KCM-A-IR-7181 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7187 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44135
4 | WIR | SPML-KCM-A-IR-7188 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR-7189 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR-7191 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR-7194 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44105
4 | WIR | SPML-KCM-A-IR-7196 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44105
4 | WIR | SPML-KCM-A-IR-7199 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44105
4 | WIR | SPML-KCM-A-IR-7202 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR-7203 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR-7204 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR-7205 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR-7206 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR-7207 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44132
4 | WIR | SPML-KCM-A-IR-7208 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44132
4 | WIR | SPML-KCM-A-IR-7212 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR-7213 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-A-IR-7214 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44137
4 | WIR | SPML-KCM-A-IR-7216 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR-7217 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44138
4 | WIR | SPML-KCM-A-IR-7218 | Finishes | Vanity Countertop | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7219 | Finishes | Toilet Cubicles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44254
4 | WIR | SPML-KCM-A-IR-7224 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44151
4 | WIR | SPML-KCM-A-IR-7225 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-A-IR-7243 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44144
4 | WIR | SPML-KCM-A-IR-7244 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44144
4 | WIR | SPML-KCM-A-IR-7245 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 45868.3583
4 | WIR | SPML-KCM-A-IR-7246 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44144
4 | WIR | SPML-KCM-A-IR-7247 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44138
4 | WIR | SPML-KCM-A-IR-7248 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44144
4 | WIR | SPML-KCM-A-IR-7249 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44144
4 | WIR | SPML-KCM-A-IR-7250 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44144
4 | WIR | SPML-KCM-A-IR-7253 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-A-IR-7254 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-A-IR-7255 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-A-IR-7256 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR-7257 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-A-IR-7258 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-A-IR-7259 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-A-IR-7260 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-A-IR-7261 | Finishes | Aluminium profile | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR-7262 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7266 | NCRs and Exceptions | Exceptions | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7267 | NCRs and Exceptions | Exceptions | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7270 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7276 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR-7277 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR-7278 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-A-IR-7279 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7284 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7285 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7286 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44152
4 | WIR | SPML-KCM-A-IR-7291 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-A-IR-7292 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7293 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7294 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7295 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7296 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7297 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7298 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7299 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-A-IR-7300 | NCRs and Exceptions | Exceptions | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7302 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7303 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7304 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7305 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7306 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7307 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7308 | Acoustic Insulaiton | PU Foam | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7309 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7310 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7311 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7312 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-A-IR-7313 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR-7314 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7315 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7316 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7317 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7318 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7319 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR-7320 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR-7328 | Furnitures | Shoe Rack | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7332 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44149
4 | WIR | SPML-KCM-A-IR-7333 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44149
4 | WIR | SPML-KCM-A-IR-7334 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44149
4 | WIR | SPML-KCM-A-IR-7335 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44149
4 | WIR | SPML-KCM-A-IR-7336 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-A-IR-7337 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-A-IR-7341 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7342 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7343 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7345 | Pole | Flag Pole | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-A-IR-7347 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-A-IR-7348 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-A-IR-7349 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44152
4 | WIR | SPML-KCM-A-IR-7350 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-A-IR-7362 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44254
4 | WIR | SPML-KCM-A-IR-7369 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR-7370 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR-7371 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR-7372 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR-7373 | Doors & Windows | Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44174
4 | WIR | SPML-KCM-A-IR-7374 | Doors & Windows | Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44174
4 | WIR | SPML-KCM-A-IR-7375 | Doors & Windows | Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44174
4 | WIR | SPML-KCM-A-IR-7379 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-A-IR-7387 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-A-IR-7397 | Finishes | Aesthetic Finishes | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-A-IR-7399 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-A-IR-7428 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR-7431 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR-7435 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-A-IR-7436 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-A-IR-7437 | Doors & Windows | Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7438 | Doors & Windows | Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7445 | FF&E | Totem | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR-7446 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-A-IR-7448 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR-7449 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-A-IR-7450 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7451 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7453 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7454 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7455 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7457 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7458 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7459 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7460 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7461 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7462 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7465 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7466 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44174
4 | WIR | SPML-KCM-A-IR-7467 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7468 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7469 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR-7470 | Finishes | Mirror | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44174
4 | WIR | SPML-KCM-A-IR-7471 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR-7472 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44174
4 | WIR | SPML-KCM-A-IR-7473 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR-7474 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44261
4 | WIR | SPML-KCM-A-IR-7475 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR-7476 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-A-IR-7477 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-A-IR-7478 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR-7479 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR-7480 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR-7481 | Finishes | Setting Out | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44254
4 | WIR | SPML-KCM-A-IR-7482 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7484 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7485 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7486 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7487 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7489 | Loading Bay Equipment System | Overhead Door | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7490 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7491 | Finishes | Sanitary Fixtures | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7493 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-A-IR-7494 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7496 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR-7497 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR-7498 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7499 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR-7500 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR-7501 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR-7502 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR-7503 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-A-IR-7508 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7509 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7510 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7511 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7512 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7513 | Parking Bay Accessories | Wheel Stopper | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-A-IR-7514 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7515 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7516 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7518 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7519 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7520 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7521 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7522 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7523 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR-7524 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-A-IR-7525 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-A-IR-7526 | FF&E | Wooden Benches | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-A-IR-7527 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44188
4 | WIR | SPML-KCM-A-IR-7528 | Finishes | Wooden Beeding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44171
4 | WIR | SPML-KCM-A-IR-7529 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR-7530 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44233
4 | WIR | SPML-KCM-A-IR-7531 | Finishes | Mirror | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44175
4 | WIR | SPML-KCM-A-IR-7532 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR-7533 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-A-IR-7534 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR-7535 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR-7536 | Roof Drainage | Canopy Gutter | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR-7537 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-A-IR-7538 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR-7539 | Doors & Windows | Doors | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR-7540 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44203
4 | WIR | SPML-KCM-A-IR-7541 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44221
4 | WIR | SPML-KCM-A-IR-7542 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7543 | Pole | Light Pole | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7544 | Paving System | Interlock | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7545 | Pole | Light Pole | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7546 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7547 | Finishes | Wooden Grill | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7548 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR-7549 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7550 | Finishes | Wooden Grill | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7551 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7552 | Finishes | Wall Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7553 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR-7555 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44221
4 | WIR | SPML-KCM-A-IR-7556 | Finishes | Steel Ladder | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7557 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44181
4 | WIR | SPML-KCM-A-IR-7558 | Sealant | Expansion Joint Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44181
4 | WIR | SPML-KCM-A-IR-7567 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44200
4 | WIR | SPML-KCM-A-IR-7568 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44185
4 | WIR | SPML-KCM-A-IR-7569 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44185
4 | WIR | SPML-KCM-A-IR-7570 | Building Envelope | Expansion Joint | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44200
4 | WIR | SPML-KCM-A-IR-7571 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR-7572 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44187
4 | WIR | SPML-KCM-A-IR-7573 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44187
4 | WIR | SPML-KCM-A-IR-7574 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR-7576 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7577 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7578 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7579 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-A-IR-7582 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7583 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7584 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7585 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7586 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7587 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7588 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7589 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7590 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7591 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7592 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7596 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7597 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7598 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7599 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7602 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7603 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7604 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7605 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7606 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7607 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7608 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7609 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7610 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7611 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7612 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7613 | Finishes | Louvre | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44261
4 | WIR | SPML-KCM-A-IR-7614 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-A-IR-7615 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR-7616 | Paving System | Kerb Stone | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR-7617 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR-7618 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR-7620 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR-7625 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-A-IR-7627 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7632 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-A-IR-7633 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7634 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7635 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7636 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7637 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7639 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7641 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7642 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7644 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7645 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7646 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7647 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7648 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7649 | Finishes | Armour Coat | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7650 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7651 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7652 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7653 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7654 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7655 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7656 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7657 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7658 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7660 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7661 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7662 | Finishes | Floor Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7665 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7666 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7667 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7668 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7669 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7670 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7671 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7672 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7673 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7674 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7675 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7676 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7678 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7679 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7681 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7682 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7683 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-A-IR-7684 | Cladding | Column Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR-7685 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-A-IR-7686 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44199
4 | WIR | SPML-KCM-A-IR-7688 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44254
4 | WIR | SPML-KCM-A-IR-7689 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7690 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44178
4 | WIR | SPML-KCM-A-IR-7691 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44201
4 | WIR | SPML-KCM-A-IR-7692 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44201
4 | WIR | SPML-KCM-A-IR-7693 | Finishes | Aesthetic Finishes | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44201
4 | WIR | SPML-KCM-A-IR-7694 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44201
4 | WIR | SPML-KCM-A-IR-7695 | Sealant | Expansion Joint Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44201
4 | WIR | SPML-KCM-A-IR-7696 | Finishes | Aesthetic Finishes | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44201
4 | WIR | SPML-KCM-A-IR-7697 | Finishes | Aesthetic Finishes | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44201
4 | WIR | SPML-KCM-A-IR-7698 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44201
4 | WIR | SPML-KCM-A-IR-7699 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44201
4 | WIR | SPML-KCM-A-IR-7700 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44201
4 | WIR | SPML-KCM-A-IR-7701 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44205
4 | WIR | SPML-KCM-A-IR-7702 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44205
4 | WIR | SPML-KCM-A-IR-7703 | Finishes | Grating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44207
4 | WIR | SPML-KCM-A-IR-7712 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44216
4 | WIR | SPML-KCM-A-IR-7713 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-A-IR-7714 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44261
4 | WIR | SPML-KCM-HM-A-IR-6379 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44051
4 | WIR | SPML-KCM-HM-A-IR-6382 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44051
4 | WIR | SPML-KCM-ME-IR- 4213 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-ME-IR- 4214 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-ME-IR- 4215 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-ME-IR- 4216 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-ME-IR- 4217 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43706
4 | WIR | SPML-KCM-ME-IR- 4733 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-ME-IR- 4734 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-ME-IR- 4735 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-ME-IR- 4736 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-ME-IR- 4737 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-ME-IR- 4788 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-ME-IR- 4789 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-ME-IR- 4790 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-ME-IR- 4791 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-ME-IR- 4792 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-ME-IR- 4793 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-ME-IR- 4799 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-ME-IR- 4845 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-ME-IR- 4846 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-ME-IR- 4950 | Finishes | Grating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-ME-IR- 4951 | Manhole | Manhole | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-ME-IR- 5006 | Manhole | Manhole | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-ME-IR- 5050 | Car Park | Gate Barrier | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44152
4 | WIR | SPML-KCM-ME-IR- 5051 | Car Park | Gate Barrier | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44152
4 | WIR | SPML-KCM-ME-IR- 5052 | Car Park | Gate Barrier | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44152
4 | WIR | SPML-KCM-ME-IR- 5054 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43797
4 | WIR | SPML-KCM-ME-IR- 5067 | Finishes | Grating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-ME-IR- 5069 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43797
4 | WIR | SPML-KCM-ME-IR- 5137 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-ME-IR- 5152 | LandScaping | Irrigation System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-ME-IR- 5175 | Lift System | Travalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-ME-IR- 5176 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43815
4 | WIR | SPML-KCM-ME-IR- 5177 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43815
4 | WIR | SPML-KCM-ME-IR- 5178 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43815
4 | WIR | SPML-KCM-ME-IR- 5239 | LandScaping | Irrigation System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-ME-IR- 5240 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-ME-IR- 5281 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-ME-IR- 5386 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43878
4 | WIR | SPML-KCM-ME-IR- 5420 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-ME-IR- 5584 | Car Park | Gate Barrier | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44152
4 | WIR | SPML-KCM-ME-IR- 5637 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-ME-IR- 5638 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-ME-IR- 5639 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-ME-IR- 5640 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-ME-IR- 5641 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-ME-IR- 5642 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-ME-IR- 5643 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-ME-IR- 5644 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43871
4 | WIR | SPML-KCM-ME-IR- 5705 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43879
4 | WIR | SPML-KCM-ME-IR- 5717 | Rainwater Management System | Gutter Down Spout | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-ME-IR- 5771 | Lift System | Travalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43886
4 | WIR | SPML-KCM-ME-IR- 5811 | Lift System | Travalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-ME-IR- 5952 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44034
4 | WIR | SPML-KCM-ME-IR- 5953 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44034
4 | WIR | SPML-KCM-ME-IR- 5954 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44034
4 | WIR | SPML-KCM-ME-IR- 5955 | Lift System | Escalator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44034
4 | WIR | SPML-KCM-ME-IR- 5956 | FF&E | Utility Cabinet | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-ME-IR- 6332 | Sealant | Fire Sealant | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-ME-IR- 6377 | Waste Management | Garbage Compactor | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44142
4 | WIR | SPML-KCM-ME-IR- 6424 | ELV | CPMS | Al Forsan Central Mall | NA | Electrical | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-ME-IR- 6434 | Space Protection System | Bollards | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44136
4 | WIR | SPML-KCM-ME-IR- 6459 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44083
4 | WIR | SPML-KCM-ME-IR- 6460 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44083
4 | WIR | SPML-KCM-ME-IR- 6492 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44254
4 | WIR | SPML-KCM-ME-IR- 6652 | Loading Bay Equipment System | Overhead Door | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44096
4 | WIR | SPML-KCM-ME-IR- 6971 | ELV | CPMS | Al Forsan Central Mall | NA | Electrical | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-ME-IR-7507 | ELV | Parking Guidance | Al Forsan Central Mall | NA | Electrical | NULL | Global Admin | A | 44181
4 | WIR | SPML-KCM-ME-IR-7638 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-ME-IR-7640 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-ME-IR-7643 | LandScaping | Irrigation System | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44231
4 | WIR | SPML-KCM-ME-IR-7680 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-ME-IR-7724 | ELV | Parking Guidance | Al Forsan Central Mall | NA | Electrical | NULL | Global Admin | A | 44261
4 | WIR | SPML-KCM-ME-IR-7725 | ELV | Parking Guidance | Al Forsan Central Mall | NA | Electrical | NULL | Global Admin | A | 44261
4 | WIR | SPML-KCM-OT-IR-0002 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43220
4 | WIR | SPML-KCM-OT-IR-0003 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43159
4 | WIR | SPML-KCM-OT-IR-0004 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43162
4 | WIR | SPML-KCM-OT-IR-0005 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-OT-IR-0006 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43165
4 | WIR | SPML-KCM-OT-IR-0007 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43166
4 | WIR | SPML-KCM-OT-IR-0008 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43167
4 | WIR | SPML-KCM-OT-IR-0009 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43169
4 | WIR | SPML-KCM-OT-IR-0010 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43170
4 | WIR | SPML-KCM-OT-IR-0011 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43171
4 | WIR | SPML-KCM-OT-IR-0012 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43172
4 | WIR | SPML-KCM-OT-IR-0013 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43173
4 | WIR | SPML-KCM-OT-IR-0014 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43174
4 | WIR | SPML-KCM-OT-IR-0015 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43176
4 | WIR | SPML-KCM-OT-IR-0016 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43176
4 | WIR | SPML-KCM-OT-IR-0017 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43177
4 | WIR | SPML-KCM-OT-IR-0018 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43178
4 | WIR | SPML-KCM-OT-IR-0019 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43179
4 | WIR | SPML-KCM-OT-IR-0020 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43179
4 | WIR | SPML-KCM-OT-IR-0021 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43180
4 | WIR | SPML-KCM-OT-IR-0022 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43180
4 | WIR | SPML-KCM-OT-IR-0023 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43181
4 | WIR | SPML-KCM-OT-IR-0024 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43183
4 | WIR | SPML-KCM-OT-IR-0025 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43184
4 | WIR | SPML-KCM-OT-IR-0026 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43184
4 | WIR | SPML-KCM-OT-IR-0027 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43185
4 | WIR | SPML-KCM-OT-IR-0028 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43185
4 | WIR | SPML-KCM-OT-IR-0029 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43186
4 | WIR | SPML-KCM-OT-IR-0030 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43220
4 | WIR | SPML-KCM-OT-IR-0031 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43187
4 | WIR | SPML-KCM-OT-IR-0032 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43187
4 | WIR | SPML-KCM-OT-IR-0033 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43220
4 | WIR | SPML-KCM-OT-IR-0034 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43187
4 | WIR | SPML-KCM-OT-IR-0035 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43187
4 | WIR | SPML-KCM-OT-IR-0036 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43220
4 | WIR | SPML-KCM-OT-IR-0037 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43188
4 | WIR | SPML-KCM-OT-IR-0038 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43190
4 | WIR | SPML-KCM-OT-IR-0039 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43220
4 | WIR | SPML-KCM-OT-IR-0040 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43191
4 | WIR | SPML-KCM-OT-IR-0041 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43191
4 | WIR | SPML-KCM-OT-IR-0042 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43191
4 | WIR | SPML-KCM-OT-IR-0043 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43192
4 | WIR | SPML-KCM-OT-IR-0044 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43192
4 | WIR | SPML-KCM-OT-IR-0045 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43192
4 | WIR | SPML-KCM-OT-IR-0046 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43193
4 | WIR | SPML-KCM-OT-IR-0047 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43193
4 | WIR | SPML-KCM-OT-IR-0048 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43193
4 | WIR | SPML-KCM-OT-IR-0049 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43194
4 | WIR | SPML-KCM-OT-IR-0050 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43194
4 | WIR | SPML-KCM-OT-IR-0051 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43194
4 | WIR | SPML-KCM-OT-IR-0052 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43195
4 | WIR | SPML-KCM-OT-IR-0053 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43195
4 | WIR | SPML-KCM-OT-IR-0054 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43195
4 | WIR | SPML-KCM-OT-IR-0055 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43197
4 | WIR | SPML-KCM-OT-IR-0056 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43197
4 | WIR | SPML-KCM-OT-IR-0057 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43197
4 | WIR | SPML-KCM-OT-IR-0058 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43198
4 | WIR | SPML-KCM-OT-IR-0059 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43198
4 | WIR | SPML-KCM-OT-IR-0060 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43198
4 | WIR | SPML-KCM-OT-IR-0061 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43199
4 | WIR | SPML-KCM-OT-IR-0062 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43199
4 | WIR | SPML-KCM-OT-IR-0063 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43200
4 | WIR | SPML-KCM-OT-IR-0064 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43200
4 | WIR | SPML-KCM-OT-IR-0065 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43200
4 | WIR | SPML-KCM-OT-IR-0066 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43201
4 | WIR | SPML-KCM-OT-IR-0067 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43201
4 | WIR | SPML-KCM-OT-IR-0068 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43201
4 | WIR | SPML-KCM-OT-IR-0069 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43202
4 | WIR | SPML-KCM-OT-IR-0070 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43202
4 | WIR | SPML-KCM-OT-IR-0071 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43202
4 | WIR | SPML-KCM-OT-IR-0072 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43204
4 | WIR | SPML-KCM-OT-IR-0073 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43204
4 | WIR | SPML-KCM-OT-IR-0074 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43204
4 | WIR | SPML-KCM-OT-IR-0075 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43205
4 | WIR | SPML-KCM-OT-IR-0076 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43205
4 | WIR | SPML-KCM-OT-IR-0077 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43205
4 | WIR | SPML-KCM-OT-IR-0078 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43206
4 | WIR | SPML-KCM-OT-IR-0079 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43206
4 | WIR | SPML-KCM-OT-IR-0080 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43206
4 | WIR | SPML-KCM-OT-IR-0081 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43207
4 | WIR | SPML-KCM-OT-IR-0082 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43207
4 | WIR | SPML-KCM-OT-IR-0083 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43207
4 | WIR | SPML-KCM-OT-IR-0084 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43207
4 | WIR | SPML-KCM-OT-IR-0085 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43208
4 | WIR | SPML-KCM-OT-IR-0086 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43208
4 | WIR | SPML-KCM-OT-IR-0087 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43208
4 | WIR | SPML-KCM-OT-IR-0088 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43208
4 | WIR | SPML-KCM-OT-IR-0089 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43209
4 | WIR | SPML-KCM-OT-IR-0090 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43209
4 | WIR | SPML-KCM-OT-IR-0091 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43209
4 | WIR | SPML-KCM-OT-IR-0092 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43209
4 | WIR | SPML-KCM-OT-IR-0093 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43211
4 | WIR | SPML-KCM-OT-IR-0094 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43211
4 | WIR | SPML-KCM-OT-IR-0095 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43211
4 | WIR | SPML-KCM-OT-IR-0096 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43211
4 | WIR | SPML-KCM-OT-IR-0097 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43212
4 | WIR | SPML-KCM-OT-IR-0098 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43212
4 | WIR | SPML-KCM-OT-IR-0099 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43212
4 | WIR | SPML-KCM-OT-IR-0100 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43212
4 | WIR | SPML-KCM-OT-IR-0101 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43213
4 | WIR | SPML-KCM-OT-IR-0102 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43213
4 | WIR | SPML-KCM-OT-IR-0103 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43213
4 | WIR | SPML-KCM-OT-IR-0104 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43213
4 | WIR | SPML-KCM-OT-IR-0105 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43214
4 | WIR | SPML-KCM-OT-IR-0106 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43214
4 | WIR | SPML-KCM-OT-IR-0107 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43214
4 | WIR | SPML-KCM-OT-IR-0108 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43214
4 | WIR | SPML-KCM-OT-IR-0109 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43215
4 | WIR | SPML-KCM-OT-IR-0110 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43215
4 | WIR | SPML-KCM-OT-IR-0111 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43215
4 | WIR | SPML-KCM-OT-IR-0112 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43216
4 | WIR | SPML-KCM-OT-IR-0113 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43216
4 | WIR | SPML-KCM-OT-IR-0114 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43216
4 | WIR | SPML-KCM-OT-IR-0115 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43216
4 | WIR | SPML-KCM-OT-IR-0116 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-OT-IR-0117 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43218
4 | WIR | SPML-KCM-OT-IR-0118 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43218
4 | WIR | SPML-KCM-OT-IR-0119 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43219
4 | WIR | SPML-KCM-OT-IR-0120 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43219
4 | WIR | SPML-KCM-OT-IR-0121 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43219
4 | WIR | SPML-KCM-OT-IR-0122 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43219
4 | WIR | SPML-KCM-OT-IR-0123 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43220
4 | WIR | SPML-KCM-OT-IR-0124 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43220
4 | WIR | SPML-KCM-OT-IR-0125 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43220
4 | WIR | SPML-KCM-OT-IR-0126 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43221
4 | WIR | SPML-KCM-OT-IR-0127 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43221
4 | WIR | SPML-KCM-OT-IR-0128 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43221
4 | WIR | SPML-KCM-OT-IR-0129 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43222
4 | WIR | SPML-KCM-OT-IR-0130 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43222
4 | WIR | SPML-KCM-OT-IR-0131 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43222
4 | WIR | SPML-KCM-OT-IR-0132 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43223
4 | WIR | SPML-KCM-OT-IR-0133 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43223
4 | WIR | SPML-KCM-OT-IR-0134 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43223
4 | WIR | SPML-KCM-OT-IR-0135 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43225
4 | WIR | SPML-KCM-OT-IR-0136 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43225
4 | WIR | SPML-KCM-OT-IR-0137 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43225
4 | WIR | SPML-KCM-OT-IR-0138 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43226
4 | WIR | SPML-KCM-OT-IR-0139 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43226
4 | WIR | SPML-KCM-OT-IR-0140 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43226
4 | WIR | SPML-KCM-OT-IR-0141 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43227
4 | WIR | SPML-KCM-OT-IR-0142 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43227
4 | WIR | SPML-KCM-OT-IR-0143 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43227
4 | WIR | SPML-KCM-OT-IR-0144 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43228
4 | WIR | SPML-KCM-OT-IR-0145 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43228
4 | WIR | SPML-KCM-OT-IR-0146 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43228
4 | WIR | SPML-KCM-OT-IR-0147 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43229
4 | WIR | SPML-KCM-OT-IR-0148 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43229
4 | WIR | SPML-KCM-OT-IR-0149 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43229
4 | WIR | SPML-KCM-OT-IR-0150 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43230
4 | WIR | SPML-KCM-OT-IR-0151 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43230
4 | WIR | SPML-KCM-OT-IR-0152 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43230
4 | WIR | SPML-KCM-OT-IR-0153 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43232
4 | WIR | SPML-KCM-OT-IR-0154 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43232
4 | WIR | SPML-KCM-OT-IR-0155 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43232
4 | WIR | SPML-KCM-OT-IR-0156 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43232
4 | WIR | SPML-KCM-OT-IR-0157 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43233
4 | WIR | SPML-KCM-OT-IR-0158 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43233
4 | WIR | SPML-KCM-OT-IR-0159 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43233
4 | WIR | SPML-KCM-OT-IR-0160 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43234
4 | WIR | SPML-KCM-OT-IR-0161 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43234
4 | WIR | SPML-KCM-OT-IR-0162 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43234
4 | WIR | SPML-KCM-OT-IR-0163 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43234
4 | WIR | SPML-KCM-OT-IR-0164 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43235
4 | WIR | SPML-KCM-OT-IR-0165 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43235
4 | WIR | SPML-KCM-OT-IR-0166 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43235
4 | WIR | SPML-KCM-OT-IR-0167 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43235
4 | WIR | SPML-KCM-OT-IR-0168 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43236
4 | WIR | SPML-KCM-OT-IR-0169 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43236
4 | WIR | SPML-KCM-OT-IR-0170 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43236
4 | WIR | SPML-KCM-OT-IR-0171 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43236
4 | WIR | SPML-KCM-OT-IR-0172 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43237
4 | WIR | SPML-KCM-OT-IR-0173 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43237
4 | WIR | SPML-KCM-OT-IR-0174 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43237
4 | WIR | SPML-KCM-OT-IR-0175 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43237
4 | WIR | SPML-KCM-OT-IR-0176 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43239
4 | WIR | SPML-KCM-OT-IR-0177 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43239
4 | WIR | SPML-KCM-OT-IR-0178 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43240
4 | WIR | SPML-KCM-OT-IR-0179 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43240
4 | WIR | SPML-KCM-OT-IR-0180 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43241
4 | WIR | SPML-KCM-OT-IR-0181 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43241
4 | WIR | SPML-KCM-OT-IR-0182 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43241
4 | WIR | SPML-KCM-OT-IR-0183 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43241
4 | WIR | SPML-KCM-OT-IR-0185 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43242
4 | WIR | SPML-KCM-OT-IR-0186 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43242
4 | WIR | SPML-KCM-OT-IR-0187 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43243
4 | WIR | SPML-KCM-OT-IR-0188 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43243
4 | WIR | SPML-KCM-OT-IR-0189 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43243
4 | WIR | SPML-KCM-OT-IR-0190 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43243
4 | WIR | SPML-KCM-OT-IR-0191 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43244
4 | WIR | SPML-KCM-OT-IR-0192 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43244
4 | WIR | SPML-KCM-OT-IR-0193 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43244
4 | WIR | SPML-KCM-OT-IR-0194 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43246
4 | WIR | SPML-KCM-OT-IR-0195 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43246
4 | WIR | SPML-KCM-OT-IR-0196 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43247
4 | WIR | SPML-KCM-OT-IR-0197 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43248
4 | WIR | SPML-KCM-OT-IR-0198 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43248
4 | WIR | SPML-KCM-OT-IR-0199 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43249
4 | WIR | SPML-KCM-OT-IR-0200 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43250
4 | WIR | SPML-KCM-OT-IR-0201 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43251
4 | WIR | SPML-KCM-OT-IR-0202 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43252
4 | WIR | SPML-KCM-OT-IR-0203 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43253
4 | WIR | SPML-KCM-OT-IR-0204 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43254
4 | WIR | SPML-KCM-OT-IR-0205 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43254
4 | WIR | SPML-KCM-OT-IR-0206 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43255
4 | WIR | SPML-KCM-OT-IR-0207 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43256
4 | WIR | SPML-KCM-OT-IR-0208 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43257
4 | WIR | SPML-KCM-OT-IR-0209 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43257
4 | WIR | SPML-KCM-OT-IR-0210 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43258
4 | WIR | SPML-KCM-OT-IR-0211 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43260
4 | WIR | SPML-KCM-OT-IR-0213 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43261
4 | WIR | SPML-KCM-OT-IR-0214 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43262
4 | WIR | SPML-KCM-OT-IR-0215 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43263
4 | WIR | SPML-KCM-OT-IR-0216 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43264
4 | WIR | SPML-KCM-OT-IR-0217 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43265
4 | WIR | SPML-KCM-OT-IR-0218 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43265
4 | WIR | SPML-KCM-OT-IR-0219 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43265
4 | WIR | SPML-KCM-OT-IR-0220 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43269
4 | WIR | SPML-KCM-OT-IR-0221 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43269
4 | WIR | SPML-KCM-OT-IR-0222 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43270
4 | WIR | SPML-KCM-OT-IR-0223 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43271
4 | WIR | SPML-KCM-OT-IR-0224 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43271
4 | WIR | SPML-KCM-OT-IR-0225 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43272
4 | WIR | SPML-KCM-OT-IR-0226 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43274
4 | WIR | SPML-KCM-OT-IR-0227 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43274
4 | WIR | SPML-KCM-OT-IR-0228 | Foundation | Excavation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43276
4 | WIR | SPML-KCM-OT-IR-0229 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43275
4 | WIR | SPML-KCM-OT-IR-0230 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43276
4 | WIR | SPML-KCM-OT-IR-0231 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43276
4 | WIR | SPML-KCM-OT-IR-0232 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43277
4 | WIR | SPML-KCM-OT-IR-0233 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43278
4 | WIR | SPML-KCM-OT-IR-0234 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43278
4 | WIR | SPML-KCM-OT-IR-0235 | Foundation | Excavation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43279
4 | WIR | SPML-KCM-OT-IR-0236 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43279
4 | WIR | SPML-KCM-OT-IR-0237 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43279
4 | WIR | SPML-KCM-OT-IR-0238 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43281
4 | WIR | SPML-KCM-OT-IR-0239 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43282
4 | WIR | SPML-KCM-OT-IR-0240 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43282
4 | WIR | SPML-KCM-OT-IR-0241 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43285
4 | WIR | SPML-KCM-OT-IR-0242 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43286
4 | WIR | SPML-KCM-OT-IR-0243 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43289
4 | WIR | SPML-KCM-OT-IR-0244 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43291
4 | WIR | SPML-KCM-OT-IR-0245 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43294
4 | WIR | SPML-KCM-OT-IR-0246 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-OT-IR-0247 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43309
4 | WIR | SPML-KCM-OT-IR-0248 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-OT-IR-0249 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43295
4 | WIR | SPML-KCM-OT-IR-0250 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43300
4 | WIR | SPML-KCM-OT-IR-0251 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43302
4 | WIR | SPML-KCM-OT-IR-0252 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43302
4 | WIR | SPML-KCM-OT-IR-0253 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43302
4 | WIR | SPML-KCM-OT-IR-0254 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43303
4 | WIR | SPML-KCM-OT-IR-0255 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43303
4 | WIR | SPML-KCM-OT-IR-0256 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43303
4 | WIR | SPML-KCM-OT-IR-0257 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43303
4 | WIR | SPML-KCM-OT-IR-0258 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43304
4 | WIR | SPML-KCM-OT-IR-0259 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43305
4 | WIR | SPML-KCM-OT-IR-0260 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43305
4 | WIR | SPML-KCM-OT-IR-0261 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43307
4 | WIR | SPML-KCM-OT-IR-0262 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43307
4 | WIR | SPML-KCM-OT-IR-0263 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44144
4 | WIR | SPML-KCM-OT-IR-0264 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43306
4 | WIR | SPML-KCM-OT-IR-0265 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43306
4 | WIR | SPML-KCM-OT-IR-0266 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43306
4 | WIR | SPML-KCM-OT-IR-0267 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43309
4 | WIR | SPML-KCM-OT-IR-0268 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43309
4 | WIR | SPML-KCM-OT-IR-0269 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43309
4 | WIR | SPML-KCM-OT-IR-0270 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43309
4 | WIR | SPML-KCM-OT-IR-0271 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43310
4 | WIR | SPML-KCM-OT-IR-0272 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43310
4 | WIR | SPML-KCM-OT-IR-0273 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43312
4 | WIR | SPML-KCM-OT-IR-0274 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43312
4 | WIR | SPML-KCM-OT-IR-0275 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43312
4 | WIR | SPML-KCM-OT-IR-0276 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43311
4 | WIR | SPML-KCM-OT-IR-0277 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43311
4 | WIR | SPML-KCM-OT-IR-0278 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43311
4 | WIR | SPML-KCM-OT-IR-0279 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43313
4 | WIR | SPML-KCM-OT-IR-0280 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43313
4 | WIR | SPML-KCM-OT-IR-0336 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43324
4 | WIR | SPML-KCM-OT-IR-0386 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43332
4 | WIR | SPML-KCM-OT-IR-0397 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-OT-IR-0401 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43335
4 | WIR | SPML-KCM-OT-IR-0402 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-OT-IR-0406 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-OT-IR-0411 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-OT-IR-0412 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-OT-IR-0422 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43338
4 | WIR | SPML-KCM-OT-IR-0423 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43338
4 | WIR | SPML-KCM-OT-IR-0424 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43338
4 | WIR | SPML-KCM-OT-IR-0425 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43338
4 | WIR | SPML-KCM-OT-IR-0432 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43339
4 | WIR | SPML-KCM-OT-IR-0433 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43339
4 | WIR | SPML-KCM-OT-IR-0448 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-OT-IR-0449 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-OT-IR-0470 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-OT-IR-0473 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43342
4 | WIR | SPML-KCM-OT-IR-0474 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43342
4 | WIR | SPML-KCM-OT-IR-0485 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-OT-IR-0526 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-OT-IR-0539 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-OT-IR-0546 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43349
4 | WIR | SPML-KCM-OT-IR-0547 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43349
4 | WIR | SPML-KCM-OT-IR-0568 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44143
4 | WIR | SPML-KCM-OT-IR-0575 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-OT-IR-0594 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-OT-IR-0605 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-OT-IR-0627 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-OT-IR-0637 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43359
4 | WIR | SPML-KCM-OT-IR-0651 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-OT-IR-0658 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-OT-IR-0668 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43362
4 | WIR | SPML-KCM-OT-IR-0703 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43365
4 | WIR | SPML-KCM-OT-IR-0709 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-OT-IR-0725 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-OT-IR-0741 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-OT-IR-0742 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-OT-IR-0743 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-OT-IR-0782 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-OT-IR-0783 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-OT-IR-0800 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43374
4 | WIR | SPML-KCM-OT-IR-0801 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43374
4 | WIR | SPML-KCM-OT-IR-0836 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-OT-IR-0837 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-OT-IR-0841 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43379
4 | WIR | SPML-KCM-OT-IR-0842 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43379
4 | WIR | SPML-KCM-OT-IR-0864 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-OT-IR-0875 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-OT-IR-0876 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-OT-IR-0903 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43384
4 | WIR | SPML-KCM-OT-IR-0933 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-OT-IR-1035 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-OT-IR-1178 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-OT-IR-1325 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-OT-IR-7229 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-OT-IR-7230 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-OT-IR-7233 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44143
4 | WIR | SPML-KCM-OT-IR-7400 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-OT-IR-7401 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-OT-IR-7402 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-OT-IR-7413 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-OT-IR-7415 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-OT-IR-7416 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-OT-IR-7418 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-OT-IR-7419 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-OT-IR-7420 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-OT-IR-7421 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-PT-IR-0418 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR- 2214 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2273 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2274 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 2275 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | C | 43503
4 | WIR | SPML-KCM-S-IR- 2276 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43476
4 | WIR | SPML-KCM-S-IR- 2277 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43477
4 | WIR | SPML-KCM-S-IR- 2278 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43477
4 | WIR | SPML-KCM-S-IR- 2279 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43479
4 | WIR | SPML-KCM-S-IR- 2280 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR- 2281 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43477
4 | WIR | SPML-KCM-S-IR- 2282 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43477
4 | WIR | SPML-KCM-S-IR- 2283 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43477
4 | WIR | SPML-KCM-S-IR- 2284 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43526
4 | WIR | SPML-KCM-S-IR- 2285 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR- 2286 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43493
4 | WIR | SPML-KCM-S-IR- 2287 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR- 2297 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43477
4 | WIR | SPML-KCM-S-IR- 2298 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43477
4 | WIR | SPML-KCM-S-IR- 2299 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR- 2300 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR- 2301 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR- 2308 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2309 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2310 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2311 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2312 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2313 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2314 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2315 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2316 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2317 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2318 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2319 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2320 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2321 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2322 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2323 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR- 2324 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43492
4 | WIR | SPML-KCM-S-IR- 2325 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43481
4 | WIR | SPML-KCM-S-IR- 2326 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43517
4 | WIR | SPML-KCM-S-IR- 2327 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR- 2328 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43481
4 | WIR | SPML-KCM-S-IR- 2329 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43481
4 | WIR | SPML-KCM-S-IR- 2330 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43481
4 | WIR | SPML-KCM-S-IR- 2331 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43492
4 | WIR | SPML-KCM-S-IR- 2332 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43482
4 | WIR | SPML-KCM-S-IR- 2333 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-S-IR- 2334 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR- 2335 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR- 2336 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-S-IR- 2337 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-S-IR- 2338 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR- 2339 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR- 2340 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR- 2341 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR- 2343 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-S-IR- 2357 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR- 2358 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2359 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2360 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2361 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2362 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2363 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43527
4 | WIR | SPML-KCM-S-IR- 2364 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2365 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2366 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43491
4 | WIR | SPML-KCM-S-IR- 2367 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2368 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2369 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2370 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43487
4 | WIR | SPML-KCM-S-IR- 2371 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2372 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43487
4 | WIR | SPML-KCM-S-IR- 2373 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43487
4 | WIR | SPML-KCM-S-IR- 2374 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR- 2375 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR- 2376 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43487
4 | WIR | SPML-KCM-S-IR- 2377 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43487
4 | WIR | SPML-KCM-S-IR- 2378 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43487
4 | WIR | SPML-KCM-S-IR- 2379 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43487
4 | WIR | SPML-KCM-S-IR- 2380 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43487
4 | WIR | SPML-KCM-S-IR- 2381 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43491
4 | WIR | SPML-KCM-S-IR- 2397 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43957
4 | WIR | SPML-KCM-S-IR- 2398 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43489
4 | WIR | SPML-KCM-S-IR- 2399 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 2400 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2401 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2402 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43492
4 | WIR | SPML-KCM-S-IR- 2403 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43492
4 | WIR | SPML-KCM-S-IR- 2404 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2405 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2406 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 2407 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43492
4 | WIR | SPML-KCM-S-IR- 2408 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43492
4 | WIR | SPML-KCM-S-IR- 2409 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43493
4 | WIR | SPML-KCM-S-IR- 2410 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2411 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43506
4 | WIR | SPML-KCM-S-IR- 2412 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43493
4 | WIR | SPML-KCM-S-IR- 2413 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43493
4 | WIR | SPML-KCM-S-IR- 2414 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43498
4 | WIR | SPML-KCM-S-IR- 2415 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2416 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2417 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43501
4 | WIR | SPML-KCM-S-IR- 2418 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43497
4 | WIR | SPML-KCM-S-IR- 2419 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43506
4 | WIR | SPML-KCM-S-IR- 2420 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43504
4 | WIR | SPML-KCM-S-IR- 2421 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2422 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2423 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2424 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2425 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2426 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2427 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR- 2452 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43500
4 | WIR | SPML-KCM-S-IR- 2455 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43498
4 | WIR | SPML-KCM-S-IR- 2456 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43516
4 | WIR | SPML-KCM-S-IR- 2457 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43499
4 | WIR | SPML-KCM-S-IR- 2496 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 2517 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2518 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2519 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43505
4 | WIR | SPML-KCM-S-IR- 2520 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43508
4 | WIR | SPML-KCM-S-IR- 2564 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR- 2583 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43527
4 | WIR | SPML-KCM-S-IR- 2584 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR- 2585 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2586 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR- 2587 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR- 2588 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR- 2589 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR- 2590 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR- 2591 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR- 2592 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43517
4 | WIR | SPML-KCM-S-IR- 2593 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR- 2594 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2595 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR- 2596 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43511
4 | WIR | SPML-KCM-S-IR- 2597 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR- 2598 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR- 2599 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR- 2600 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR- 2601 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR- 2602 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43510
4 | WIR | SPML-KCM-S-IR- 2603 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43510
4 | WIR | SPML-KCM-S-IR- 2604 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43510
4 | WIR | SPML-KCM-S-IR- 2605 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43510
4 | WIR | SPML-KCM-S-IR- 2606 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-S-IR- 2607 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR- 2608 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR- 2609 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43530
4 | WIR | SPML-KCM-S-IR- 2610 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43510
4 | WIR | SPML-KCM-S-IR- 2611 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR- 2612 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-S-IR- 2613 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43510
4 | WIR | SPML-KCM-S-IR- 2614 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43510
4 | WIR | SPML-KCM-S-IR- 2615 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR- 2617 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43516
4 | WIR | SPML-KCM-S-IR- 2618 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR- 2619 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43533
4 | WIR | SPML-KCM-S-IR- 2635 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43516
4 | WIR | SPML-KCM-S-IR- 2636 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43514
4 | WIR | SPML-KCM-S-IR- 2637 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43518
4 | WIR | SPML-KCM-S-IR- 2638 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-S-IR- 2639 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43514
4 | WIR | SPML-KCM-S-IR- 2640 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43514
4 | WIR | SPML-KCM-S-IR- 2641 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-S-IR- 2665 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR- 2666 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR- 2671 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43747
4 | WIR | SPML-KCM-S-IR- 2672 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43517
4 | WIR | SPML-KCM-S-IR- 2673 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43516
4 | WIR | SPML-KCM-S-IR- 2674 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43516
4 | WIR | SPML-KCM-S-IR- 2675 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43516
4 | WIR | SPML-KCM-S-IR- 2676 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR- 2681 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2682 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43519
4 | WIR | SPML-KCM-S-IR- 2683 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR- 2684 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43517
4 | WIR | SPML-KCM-S-IR- 2685 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43517
4 | WIR | SPML-KCM-S-IR- 2686 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43517
4 | WIR | SPML-KCM-S-IR- 2687 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2688 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2689 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43521
4 | WIR | SPML-KCM-S-IR- 2690 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43530
4 | WIR | SPML-KCM-S-IR- 2691 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR- 2692 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43519
4 | WIR | SPML-KCM-S-IR- 2693 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-S-IR- 2694 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43519
4 | WIR | SPML-KCM-S-IR- 2695 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-S-IR- 2696 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-S-IR- 2702 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43881
4 | WIR | SPML-KCM-S-IR- 2703 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43531
4 | WIR | SPML-KCM-S-IR- 2704 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2705 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2706 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2707 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR- 2708 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR- 2709 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR- 2710 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR- 2711 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR- 2712 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR- 2718 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43747
4 | WIR | SPML-KCM-S-IR- 2720 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43521
4 | WIR | SPML-KCM-S-IR- 2721 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2722 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2723 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2724 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2725 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2726 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2727 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR- 2728 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR- 2730 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR- 2731 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 2732 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43783
4 | WIR | SPML-KCM-S-IR- 2733 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43522
4 | WIR | SPML-KCM-S-IR- 2734 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2737 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2738 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2740 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2741 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-S-IR- 2742 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2743 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2744 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR- 2745 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-S-IR- 2763 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43526
4 | WIR | SPML-KCM-S-IR- 2764 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-S-IR- 2765 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43527
4 | WIR | SPML-KCM-S-IR- 2766 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43545
4 | WIR | SPML-KCM-S-IR- 2767 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43527
4 | WIR | SPML-KCM-S-IR- 2769 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43550
4 | WIR | SPML-KCM-S-IR- 2771 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43550
4 | WIR | SPML-KCM-S-IR- 2772 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43550
4 | WIR | SPML-KCM-S-IR- 2773 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43550
4 | WIR | SPML-KCM-S-IR- 2774 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43569
4 | WIR | SPML-KCM-S-IR- 2775 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43530
4 | WIR | SPML-KCM-S-IR- 2776 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43527
4 | WIR | SPML-KCM-S-IR- 2777 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43533
4 | WIR | SPML-KCM-S-IR- 2778 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2779 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43530
4 | WIR | SPML-KCM-S-IR- 2780 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR- 2781 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 2782 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43528
4 | WIR | SPML-KCM-S-IR- 2783 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43532
4 | WIR | SPML-KCM-S-IR- 2794 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR- 2796 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43550
4 | WIR | SPML-KCM-S-IR- 2798 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43545
4 | WIR | SPML-KCM-S-IR- 2799 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43533
4 | WIR | SPML-KCM-S-IR- 2801 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43544
4 | WIR | SPML-KCM-S-IR- 2804 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43747
4 | WIR | SPML-KCM-S-IR- 2805 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43530
4 | WIR | SPML-KCM-S-IR- 2806 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 2807 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43531
4 | WIR | SPML-KCM-S-IR- 2808 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43544
4 | WIR | SPML-KCM-S-IR- 2809 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43531
4 | WIR | SPML-KCM-S-IR- 2810 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2811 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43530
4 | WIR | SPML-KCM-S-IR- 2812 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43533
4 | WIR | SPML-KCM-S-IR- 2813 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43533
4 | WIR | SPML-KCM-S-IR- 2814 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-S-IR- 2816 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43533
4 | WIR | SPML-KCM-S-IR- 2817 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2818 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43533
4 | WIR | SPML-KCM-S-IR- 2819 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43531
4 | WIR | SPML-KCM-S-IR- 2820 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-S-IR- 2821 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2825 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43534
4 | WIR | SPML-KCM-S-IR- 2826 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43747
4 | WIR | SPML-KCM-S-IR- 2827 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43534
4 | WIR | SPML-KCM-S-IR- 2828 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43534
4 | WIR | SPML-KCM-S-IR- 2829 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43748
4 | WIR | SPML-KCM-S-IR- 2830 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43545
4 | WIR | SPML-KCM-S-IR- 2831 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43544
4 | WIR | SPML-KCM-S-IR- 2832 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43534
4 | WIR | SPML-KCM-S-IR- 2833 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-S-IR- 2834 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43534
4 | WIR | SPML-KCM-S-IR- 2835 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43534
4 | WIR | SPML-KCM-S-IR- 2836 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43538
4 | WIR | SPML-KCM-S-IR- 2837 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43535
4 | WIR | SPML-KCM-S-IR- 2838 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43535
4 | WIR | SPML-KCM-S-IR- 2839 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 2840 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2841 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2842 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43542
4 | WIR | SPML-KCM-S-IR- 2843 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2844 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43545
4 | WIR | SPML-KCM-S-IR- 2845 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2846 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43543
4 | WIR | SPML-KCM-S-IR- 2847 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 2848 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2849 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2850 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2851 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 2852 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2853 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2854 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2855 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2856 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2857 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2858 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2859 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR- 2860 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43592
4 | WIR | SPML-KCM-S-IR- 2861 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 2862 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43538
4 | WIR | SPML-KCM-S-IR- 2863 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43538
4 | WIR | SPML-KCM-S-IR- 2864 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43538
4 | WIR | SPML-KCM-S-IR- 2865 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43538
4 | WIR | SPML-KCM-S-IR- 2866 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-S-IR- 2867 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43538
4 | WIR | SPML-KCM-S-IR- 2868 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2869 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-S-IR- 2870 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43538
4 | WIR | SPML-KCM-S-IR- 2871 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43538
4 | WIR | SPML-KCM-S-IR- 2872 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43538
4 | WIR | SPML-KCM-S-IR- 2873 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2874 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2875 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2876 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2877 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43538
4 | WIR | SPML-KCM-S-IR- 2878 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2879 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 2880 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-S-IR- 2881 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43540
4 | WIR | SPML-KCM-S-IR- 2882 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 2883 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43540
4 | WIR | SPML-KCM-S-IR- 2885 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2886 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43540
4 | WIR | SPML-KCM-S-IR- 2887 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43540
4 | WIR | SPML-KCM-S-IR- 2888 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43540
4 | WIR | SPML-KCM-S-IR- 2889 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43542
4 | WIR | SPML-KCM-S-IR- 2890 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43541
4 | WIR | SPML-KCM-S-IR- 2891 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 2892 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43592
4 | WIR | SPML-KCM-S-IR- 2893 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43541
4 | WIR | SPML-KCM-S-IR- 2894 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43541
4 | WIR | SPML-KCM-S-IR- 2895 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43541
4 | WIR | SPML-KCM-S-IR- 2897 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43542
4 | WIR | SPML-KCM-S-IR- 2898 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2900 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43548
4 | WIR | SPML-KCM-S-IR- 2901 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43542
4 | WIR | SPML-KCM-S-IR- 2902 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43542
4 | WIR | SPML-KCM-S-IR- 2903 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-S-IR- 2904 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43548
4 | WIR | SPML-KCM-S-IR- 2905 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43548
4 | WIR | SPML-KCM-S-IR- 2906 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43542
4 | WIR | SPML-KCM-S-IR- 2907 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43543
4 | WIR | SPML-KCM-S-IR- 2908 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2909 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43545
4 | WIR | SPML-KCM-S-IR- 2910 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43543
4 | WIR | SPML-KCM-S-IR- 2911 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43543
4 | WIR | SPML-KCM-S-IR- 2912 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43543
4 | WIR | SPML-KCM-S-IR- 2913 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2914 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43544
4 | WIR | SPML-KCM-S-IR- 2915 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43544
4 | WIR | SPML-KCM-S-IR- 2919 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 2920 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43544
4 | WIR | SPML-KCM-S-IR- 2921 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43544
4 | WIR | SPML-KCM-S-IR- 2922 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43544
4 | WIR | SPML-KCM-S-IR- 2923 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43548
4 | WIR | SPML-KCM-S-IR- 2924 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43545
4 | WIR | SPML-KCM-S-IR- 2925 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-S-IR- 2926 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2927 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44151
4 | WIR | SPML-KCM-S-IR- 2928 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2929 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2930 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2931 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR- 2932 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43548
4 | WIR | SPML-KCM-S-IR- 2933 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2934 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 2935 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2937 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43548
4 | WIR | SPML-KCM-S-IR- 2938 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43548
4 | WIR | SPML-KCM-S-IR- 2939 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-S-IR- 2940 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44151
4 | WIR | SPML-KCM-S-IR- 2941 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43553
4 | WIR | SPML-KCM-S-IR- 2943 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43548
4 | WIR | SPML-KCM-S-IR- 2945 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43550
4 | WIR | SPML-KCM-S-IR- 2946 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43550
4 | WIR | SPML-KCM-S-IR- 2947 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-S-IR- 2948 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2949 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 2950 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 2951 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-S-IR- 2952 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-S-IR- 2953 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2954 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2955 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2956 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2957 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2958 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2959 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2960 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2961 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2962 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2963 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2964 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 2965 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR- 2968 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43550
4 | WIR | SPML-KCM-S-IR- 2969 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-S-IR- 2970 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43748
4 | WIR | SPML-KCM-S-IR- 2971 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-S-IR- 2973 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43748
4 | WIR | SPML-KCM-S-IR- 2974 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-S-IR- 2975 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-S-IR- 2976 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 2978 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-S-IR- 2979 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-S-IR- 2980 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43547
4 | WIR | SPML-KCM-S-IR- 2981 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 2982 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43551
4 | WIR | SPML-KCM-S-IR- 2983 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43570
4 | WIR | SPML-KCM-S-IR- 2984 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-S-IR- 2988 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43552
4 | WIR | SPML-KCM-S-IR- 2989 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 2990 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43552
4 | WIR | SPML-KCM-S-IR- 2991 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43573
4 | WIR | SPML-KCM-S-IR- 2993 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43552
4 | WIR | SPML-KCM-S-IR- 2994 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43552
4 | WIR | SPML-KCM-S-IR- 2997 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 2999 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 3000 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 3001 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 3002 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 3003 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43574
4 | WIR | SPML-KCM-S-IR- 3004 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 3005 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43558
4 | WIR | SPML-KCM-S-IR- 3006 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR- 3007 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43558
4 | WIR | SPML-KCM-S-IR- 3008 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 3009 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-S-IR- 3010 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43554
4 | WIR | SPML-KCM-S-IR- 3011 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-S-IR- 3012 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43561
4 | WIR | SPML-KCM-S-IR- 3013 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 3018 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-S-IR- 3019 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43555
4 | WIR | SPML-KCM-S-IR- 3020 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-S-IR- 3021 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43556
4 | WIR | SPML-KCM-S-IR- 3022 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 3023 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-S-IR- 3024 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43556
4 | WIR | SPML-KCM-S-IR- 3025 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-S-IR- 3026 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-S-IR- 3027 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-S-IR- 3028 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-S-IR- 3031 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-S-IR- 3032 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43561
4 | WIR | SPML-KCM-S-IR- 3033 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43563
4 | WIR | SPML-KCM-S-IR- 3034 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43557
4 | WIR | SPML-KCM-S-IR- 3038 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43558
4 | WIR | SPML-KCM-S-IR- 3039 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43558
4 | WIR | SPML-KCM-S-IR- 3040 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-S-IR- 3041 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43561
4 | WIR | SPML-KCM-S-IR- 3043 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43558
4 | WIR | SPML-KCM-S-IR- 3044 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43564
4 | WIR | SPML-KCM-S-IR- 3045 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43559
4 | WIR | SPML-KCM-S-IR- 3046 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-S-IR- 3047 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43559
4 | WIR | SPML-KCM-S-IR- 3048 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43559
4 | WIR | SPML-KCM-S-IR- 3049 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43561
4 | WIR | SPML-KCM-S-IR- 3052 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-S-IR- 3053 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-S-IR- 3054 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43565
4 | WIR | SPML-KCM-S-IR- 3055 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 3056 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43561
4 | WIR | SPML-KCM-S-IR- 3057 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43561
4 | WIR | SPML-KCM-S-IR- 3062 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-S-IR- 3064 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-S-IR- 3065 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-S-IR- 3066 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-S-IR- 3067 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43566
4 | WIR | SPML-KCM-S-IR- 3068 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43562
4 | WIR | SPML-KCM-S-IR- 3071 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 3072 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43563
4 | WIR | SPML-KCM-S-IR- 3073 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43569
4 | WIR | SPML-KCM-S-IR- 3074 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43563
4 | WIR | SPML-KCM-S-IR- 3075 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR- 3076 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR- 3077 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43563
4 | WIR | SPML-KCM-S-IR- 3078 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43566
4 | WIR | SPML-KCM-S-IR- 3079 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43563
4 | WIR | SPML-KCM-S-IR- 3080 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43565
4 | WIR | SPML-KCM-S-IR- 3081 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43563
4 | WIR | SPML-KCM-S-IR- 3087 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43564
4 | WIR | SPML-KCM-S-IR- 3088 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43564
4 | WIR | SPML-KCM-S-IR- 3089 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43836
4 | WIR | SPML-KCM-S-IR- 3091 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-S-IR- 3092 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-S-IR- 3093 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43564
4 | WIR | SPML-KCM-S-IR- 3094 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43564
4 | WIR | SPML-KCM-S-IR- 3095 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-S-IR- 3098 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43565
4 | WIR | SPML-KCM-S-IR- 3099 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43582
4 | WIR | SPML-KCM-S-IR- 3100 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 3102 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43565
4 | WIR | SPML-KCM-S-IR- 3105 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43566
4 | WIR | SPML-KCM-S-IR- 3106 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43566
4 | WIR | SPML-KCM-S-IR- 3107 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43570
4 | WIR | SPML-KCM-S-IR- 3110 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43565
4 | WIR | SPML-KCM-S-IR- 3111 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43566
4 | WIR | SPML-KCM-S-IR- 3112 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-S-IR- 3113 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-S-IR- 3114 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43569
4 | WIR | SPML-KCM-S-IR- 3122 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43570
4 | WIR | SPML-KCM-S-IR- 3123 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43570
4 | WIR | SPML-KCM-S-IR- 3124 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43570
4 | WIR | SPML-KCM-S-IR- 3125 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43771
4 | WIR | SPML-KCM-S-IR- 3126 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-S-IR- 3127 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-S-IR- 3128 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43571
4 | WIR | SPML-KCM-S-IR- 3129 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43572
4 | WIR | SPML-KCM-S-IR- 3130 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43570
4 | WIR | SPML-KCM-S-IR- 3132 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR- 3133 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43571
4 | WIR | SPML-KCM-S-IR- 3137 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43575
4 | WIR | SPML-KCM-S-IR- 3138 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43571
4 | WIR | SPML-KCM-S-IR- 3139 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43572
4 | WIR | SPML-KCM-S-IR- 3140 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43571
4 | WIR | SPML-KCM-S-IR- 3141 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43572
4 | WIR | SPML-KCM-S-IR- 3142 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR- 3144 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43571
4 | WIR | SPML-KCM-S-IR- 3146 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-S-IR- 3147 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-S-IR- 3148 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43572
4 | WIR | SPML-KCM-S-IR- 3149 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43572
4 | WIR | SPML-KCM-S-IR- 3150 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43750
4 | WIR | SPML-KCM-S-IR- 3151 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43572
4 | WIR | SPML-KCM-S-IR- 3153 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43573
4 | WIR | SPML-KCM-S-IR- 3154 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43574
4 | WIR | SPML-KCM-S-IR- 3155 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43574
4 | WIR | SPML-KCM-S-IR- 3156 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43574
4 | WIR | SPML-KCM-S-IR- 3159 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43573
4 | WIR | SPML-KCM-S-IR- 3160 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43573
4 | WIR | SPML-KCM-S-IR- 3162 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43573
4 | WIR | SPML-KCM-S-IR- 3163 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43573
4 | WIR | SPML-KCM-S-IR- 3164 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43577
4 | WIR | SPML-KCM-S-IR- 3165 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43576
4 | WIR | SPML-KCM-S-IR- 3166 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43573
4 | WIR | SPML-KCM-S-IR- 3167 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43573
4 | WIR | SPML-KCM-S-IR- 3168 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43573
4 | WIR | SPML-KCM-S-IR- 3169 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR- 3170 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR- 3171 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43573
4 | WIR | SPML-KCM-S-IR- 3172 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43575
4 | WIR | SPML-KCM-S-IR- 3173 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR- 3174 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43575
4 | WIR | SPML-KCM-S-IR- 3175 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | C | 43575
4 | WIR | SPML-KCM-S-IR- 3176 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR- 3177 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR- 3178 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43575
4 | WIR | SPML-KCM-S-IR- 3180 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43618
4 | WIR | SPML-KCM-S-IR- 3182 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43564
4 | WIR | SPML-KCM-S-IR- 3183 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43575
4 | WIR | SPML-KCM-S-IR- 3184 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR- 3185 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43639
4 | WIR | SPML-KCM-S-IR- 3186 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43575
4 | WIR | SPML-KCM-S-IR- 3187 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43575
4 | WIR | SPML-KCM-S-IR- 3188 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43576
4 | WIR | SPML-KCM-S-IR- 3189 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43576
4 | WIR | SPML-KCM-S-IR- 3193 | Structural System | Tranformer Channel | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 3195 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43577
4 | WIR | SPML-KCM-S-IR- 3196 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43579
4 | WIR | SPML-KCM-S-IR- 3197 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43577
4 | WIR | SPML-KCM-S-IR- 3198 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-S-IR- 3199 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR- 3200 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43580
4 | WIR | SPML-KCM-S-IR- 3201 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 3202 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43579
4 | WIR | SPML-KCM-S-IR- 3203 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43577
4 | WIR | SPML-KCM-S-IR- 3204 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43579
4 | WIR | SPML-KCM-S-IR- 3205 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3206 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3207 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3208 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3209 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3210 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3211 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3212 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3213 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3214 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43579
4 | WIR | SPML-KCM-S-IR- 3215 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-S-IR- 3216 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43628
4 | WIR | SPML-KCM-S-IR- 3217 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3218 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3219 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43578
4 | WIR | SPML-KCM-S-IR- 3220 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43578
4 | WIR | SPML-KCM-S-IR- 3221 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43578
4 | WIR | SPML-KCM-S-IR- 3224 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43580
4 | WIR | SPML-KCM-S-IR- 3225 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43580
4 | WIR | SPML-KCM-S-IR- 3226 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43605
4 | WIR | SPML-KCM-S-IR- 3227 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43580
4 | WIR | SPML-KCM-S-IR- 3228 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 3229 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43605
4 | WIR | SPML-KCM-S-IR- 3230 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43580
4 | WIR | SPML-KCM-S-IR- 3232 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43610
4 | WIR | SPML-KCM-S-IR- 3233 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43580
4 | WIR | SPML-KCM-S-IR- 3234 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43753
4 | WIR | SPML-KCM-S-IR- 3235 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43580
4 | WIR | SPML-KCM-S-IR- 3236 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43648
4 | WIR | SPML-KCM-S-IR- 3237 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-S-IR- 3238 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43582
4 | WIR | SPML-KCM-S-IR- 3239 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43771
4 | WIR | SPML-KCM-S-IR- 3240 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43582
4 | WIR | SPML-KCM-S-IR- 3241 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-S-IR- 3243 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43774
4 | WIR | SPML-KCM-S-IR- 3250 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43582
4 | WIR | SPML-KCM-S-IR- 3251 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43605
4 | WIR | SPML-KCM-S-IR- 3252 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43582
4 | WIR | SPML-KCM-S-IR- 3253 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-S-IR- 3254 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43583
4 | WIR | SPML-KCM-S-IR- 3255 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-S-IR- 3256 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43583
4 | WIR | SPML-KCM-S-IR- 3257 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43583
4 | WIR | SPML-KCM-S-IR- 3258 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43605
4 | WIR | SPML-KCM-S-IR- 3259 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-S-IR- 3260 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43626
4 | WIR | SPML-KCM-S-IR- 3261 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43586
4 | WIR | SPML-KCM-S-IR- 3262 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43615
4 | WIR | SPML-KCM-S-IR- 3263 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43605
4 | WIR | SPML-KCM-S-IR- 3264 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-S-IR- 3265 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-S-IR- 3266 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-S-IR- 3267 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43605
4 | WIR | SPML-KCM-S-IR- 3268 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-S-IR- 3269 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-S-IR- 3270 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-S-IR- 3271 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43585
4 | WIR | SPML-KCM-S-IR- 3273 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-S-IR- 3274 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43584
4 | WIR | SPML-KCM-S-IR- 3275 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43585
4 | WIR | SPML-KCM-S-IR- 3276 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43585
4 | WIR | SPML-KCM-S-IR- 3277 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43962
4 | WIR | SPML-KCM-S-IR- 3280 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43585
4 | WIR | SPML-KCM-S-IR- 3281 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43753
4 | WIR | SPML-KCM-S-IR- 3282 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43758
4 | WIR | SPML-KCM-S-IR- 3283 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43588
4 | WIR | SPML-KCM-S-IR- 3284 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43585
4 | WIR | SPML-KCM-S-IR- 3285 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43586
4 | WIR | SPML-KCM-S-IR- 3286 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43753
4 | WIR | SPML-KCM-S-IR- 3287 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-S-IR- 3288 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 3289 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43586
4 | WIR | SPML-KCM-S-IR- 3290 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43586
4 | WIR | SPML-KCM-S-IR- 3291 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43586
4 | WIR | SPML-KCM-S-IR- 3292 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43587
4 | WIR | SPML-KCM-S-IR- 3293 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43587
4 | WIR | SPML-KCM-S-IR- 3294 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43587
4 | WIR | SPML-KCM-S-IR- 3295 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43604
4 | WIR | SPML-KCM-S-IR- 3298 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43586
4 | WIR | SPML-KCM-S-IR- 3299 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43587
4 | WIR | SPML-KCM-S-IR- 3302 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43587
4 | WIR | SPML-KCM-S-IR- 3304 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43587
4 | WIR | SPML-KCM-S-IR- 3305 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-S-IR- 3306 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43589
4 | WIR | SPML-KCM-S-IR- 3307 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43586
4 | WIR | SPML-KCM-S-IR- 3309 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43589
4 | WIR | SPML-KCM-S-IR- 3313 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43589
4 | WIR | SPML-KCM-S-IR- 3314 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-S-IR- 3315 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-S-IR- 3318 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-S-IR- 3319 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-S-IR- 3320 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43715
4 | WIR | SPML-KCM-S-IR- 3321 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 3322 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-S-IR- 3323 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 3324 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 3325 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 3326 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43592
4 | WIR | SPML-KCM-S-IR- 3327 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-S-IR- 3328 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43590
4 | WIR | SPML-KCM-S-IR- 3329 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 3330 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43591
4 | WIR | SPML-KCM-S-IR- 3331 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | C | 43591
4 | WIR | SPML-KCM-S-IR- 3333 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 3334 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43593
4 | WIR | SPML-KCM-S-IR- 3335 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43592
4 | WIR | SPML-KCM-S-IR- 3336 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43592
4 | WIR | SPML-KCM-S-IR- 3341 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43753
4 | WIR | SPML-KCM-S-IR- 3347 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 3348 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43594
4 | WIR | SPML-KCM-S-IR- 3349 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 3350 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-S-IR- 3351 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43944
4 | WIR | SPML-KCM-S-IR- 3352 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | C | 43596
4 | WIR | SPML-KCM-S-IR- 3353 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 3354 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 3355 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43597
4 | WIR | SPML-KCM-S-IR- 3356 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43597
4 | WIR | SPML-KCM-S-IR- 3357 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43597
4 | WIR | SPML-KCM-S-IR- 3358 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43597
4 | WIR | SPML-KCM-S-IR- 3360 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43626
4 | WIR | SPML-KCM-S-IR- 3365 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43599
4 | WIR | SPML-KCM-S-IR- 3366 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43599
4 | WIR | SPML-KCM-S-IR- 3367 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43599
4 | WIR | SPML-KCM-S-IR- 3368 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43599
4 | WIR | SPML-KCM-S-IR- 3369 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43599
4 | WIR | SPML-KCM-S-IR- 3376 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43604
4 | WIR | SPML-KCM-S-IR- 3377 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43599
4 | WIR | SPML-KCM-S-IR- 3378 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 3379 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 3380 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43599
4 | WIR | SPML-KCM-S-IR- 3383 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 3386 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR- 3387 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43600
4 | WIR | SPML-KCM-S-IR- 3388 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43552
4 | WIR | SPML-KCM-S-IR- 3394 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43775
4 | WIR | SPML-KCM-S-IR- 3395 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43603
4 | WIR | SPML-KCM-S-IR- 3396 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43603
4 | WIR | SPML-KCM-S-IR- 3397 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43604
4 | WIR | SPML-KCM-S-IR- 3400 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 3401 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43615
4 | WIR | SPML-KCM-S-IR- 3402 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43628
4 | WIR | SPML-KCM-S-IR- 3405 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 3409 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43628
4 | WIR | SPML-KCM-S-IR- 3410 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 3411 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 3412 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-S-IR- 3413 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43606
4 | WIR | SPML-KCM-S-IR- 3414 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43606
4 | WIR | SPML-KCM-S-IR- 3415 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43606
4 | WIR | SPML-KCM-S-IR- 3418 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-S-IR- 3420 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43606
4 | WIR | SPML-KCM-S-IR- 3421 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43607
4 | WIR | SPML-KCM-S-IR- 3422 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43628
4 | WIR | SPML-KCM-S-IR- 3423 | Walls | Plaster Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43611
4 | WIR | SPML-KCM-S-IR- 3427 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43610
4 | WIR | SPML-KCM-S-IR- 3428 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44151
4 | WIR | SPML-KCM-S-IR- 3429 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43611
4 | WIR | SPML-KCM-S-IR- 3430 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43608
4 | WIR | SPML-KCM-S-IR- 3431 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43610
4 | WIR | SPML-KCM-S-IR- 3435 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43610
4 | WIR | SPML-KCM-S-IR- 3436 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-S-IR- 3437 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43611
4 | WIR | SPML-KCM-S-IR- 3438 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43611
4 | WIR | SPML-KCM-S-IR- 3439 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43614
4 | WIR | SPML-KCM-S-IR- 3440 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-S-IR- 3441 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-S-IR- 3442 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43758
4 | WIR | SPML-KCM-S-IR- 3443 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-S-IR- 3444 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43612
4 | WIR | SPML-KCM-S-IR- 3445 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43612
4 | WIR | SPML-KCM-S-IR- 3446 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43612
4 | WIR | SPML-KCM-S-IR- 3447 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43612
4 | WIR | SPML-KCM-S-IR- 3448 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43758
4 | WIR | SPML-KCM-S-IR- 3449 | Concrete Works | Substation Foundation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-S-IR- 3450 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 3454 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43614
4 | WIR | SPML-KCM-S-IR- 3458 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43614
4 | WIR | SPML-KCM-S-IR- 3459 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43758
4 | WIR | SPML-KCM-S-IR- 3460 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43617
4 | WIR | SPML-KCM-S-IR- 3462 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43758
4 | WIR | SPML-KCM-S-IR- 3464 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43615
4 | WIR | SPML-KCM-S-IR- 3469 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43753
4 | WIR | SPML-KCM-S-IR- 3470 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43617
4 | WIR | SPML-KCM-S-IR- 3471 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43759
4 | WIR | SPML-KCM-S-IR- 3472 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43759
4 | WIR | SPML-KCM-S-IR- 3473 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43759
4 | WIR | SPML-KCM-S-IR- 3474 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43628
4 | WIR | SPML-KCM-S-IR- 3476 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-S-IR- 3477 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43626
4 | WIR | SPML-KCM-S-IR- 3478 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43624
4 | WIR | SPML-KCM-S-IR- 3479 | Concrete Works | Retaining Wall | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43660
4 | WIR | SPML-KCM-S-IR- 3480 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43759
4 | WIR | SPML-KCM-S-IR- 3481 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43759
4 | WIR | SPML-KCM-S-IR- 3485 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43636
4 | WIR | SPML-KCM-S-IR- 3486 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43951
4 | WIR | SPML-KCM-S-IR- 3489 | Concrete Works | Retaining Wall | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43650
4 | WIR | SPML-KCM-S-IR- 3493 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 3494 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43628
4 | WIR | SPML-KCM-S-IR- 3496 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43951
4 | WIR | SPML-KCM-S-IR- 3497 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 3498 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43626
4 | WIR | SPML-KCM-S-IR- 3499 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43631
4 | WIR | SPML-KCM-S-IR- 3503 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR- 3505 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 3506 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 3507 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 3508 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43631
4 | WIR | SPML-KCM-S-IR- 3509 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 3510 | Concrete Works | Retaining Wall | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 3511 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43627
4 | WIR | SPML-KCM-S-IR- 3512 | Concrete Works | Retaining Wall | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43762
4 | WIR | SPML-KCM-S-IR- 3513 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43761
4 | WIR | SPML-KCM-S-IR- 3514 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43634
4 | WIR | SPML-KCM-S-IR- 3515 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43761
4 | WIR | SPML-KCM-S-IR- 3516 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43761
4 | WIR | SPML-KCM-S-IR- 3517 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43761
4 | WIR | SPML-KCM-S-IR- 3519 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-S-IR- 3520 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-S-IR- 3521 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR- 3522 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43761
4 | WIR | SPML-KCM-S-IR- 3523 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43629
4 | WIR | SPML-KCM-S-IR- 3526 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43761
4 | WIR | SPML-KCM-S-IR- 3527 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43762
4 | WIR | SPML-KCM-S-IR- 3538 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43762
4 | WIR | SPML-KCM-S-IR- 3539 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43953
4 | WIR | SPML-KCM-S-IR- 3540 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-S-IR- 3541 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43638
4 | WIR | SPML-KCM-S-IR- 3542 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43962
4 | WIR | SPML-KCM-S-IR- 3544 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43702
4 | WIR | SPML-KCM-S-IR- 3545 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43762
4 | WIR | SPML-KCM-S-IR- 3546 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43631
4 | WIR | SPML-KCM-S-IR- 3547 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-S-IR- 3551 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43764
4 | WIR | SPML-KCM-S-IR- 3553 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43632
4 | WIR | SPML-KCM-S-IR- 3554 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43639
4 | WIR | SPML-KCM-S-IR- 3558 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43634
4 | WIR | SPML-KCM-S-IR- 3559 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43683
4 | WIR | SPML-KCM-S-IR- 3560 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43634
4 | WIR | SPML-KCM-S-IR- 3561 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43638
4 | WIR | SPML-KCM-S-IR- 3562 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43634
4 | WIR | SPML-KCM-S-IR- 3563 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43634
4 | WIR | SPML-KCM-S-IR- 3564 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43762
4 | WIR | SPML-KCM-S-IR- 3567 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-S-IR- 3568 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-S-IR- 3574 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43764
4 | WIR | SPML-KCM-S-IR- 3575 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43638
4 | WIR | SPML-KCM-S-IR- 3585 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43764
4 | WIR | SPML-KCM-S-IR- 3586 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43764
4 | WIR | SPML-KCM-S-IR- 3587 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43733
4 | WIR | SPML-KCM-S-IR- 3588 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43636
4 | WIR | SPML-KCM-S-IR- 3589 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43636
4 | WIR | SPML-KCM-S-IR- 3590 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43636
4 | WIR | SPML-KCM-S-IR- 3591 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43636
4 | WIR | SPML-KCM-S-IR- 3592 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43764
4 | WIR | SPML-KCM-S-IR- 3598 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-S-IR- 3601 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-S-IR- 3603 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43765
4 | WIR | SPML-KCM-S-IR- 3604 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43656
4 | WIR | SPML-KCM-S-IR- 3606 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43765
4 | WIR | SPML-KCM-S-IR- 3607 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43765
4 | WIR | SPML-KCM-S-IR- 3608 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43765
4 | WIR | SPML-KCM-S-IR- 3619 | Finishes | Painting | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-S-IR- 3620 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43647
4 | WIR | SPML-KCM-S-IR- 3621 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43655
4 | WIR | SPML-KCM-S-IR- 3623 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43647
4 | WIR | SPML-KCM-S-IR- 3626 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43765
4 | WIR | SPML-KCM-S-IR- 3627 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43646
4 | WIR | SPML-KCM-S-IR- 3646 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43647
4 | WIR | SPML-KCM-S-IR- 3652 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43647
4 | WIR | SPML-KCM-S-IR- 3653 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43647
4 | WIR | SPML-KCM-S-IR- 3654 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-S-IR- 3657 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-S-IR- 3661 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43648
4 | WIR | SPML-KCM-S-IR- 3663 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR- 3664 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-S-IR- 3665 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-S-IR- 3666 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-S-IR- 3670 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43731
4 | WIR | SPML-KCM-S-IR- 3671 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43641
4 | WIR | SPML-KCM-S-IR- 3672 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43683
4 | WIR | SPML-KCM-S-IR- 3678 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-S-IR- 3679 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43641
4 | WIR | SPML-KCM-S-IR- 3680 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-S-IR- 3681 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43641
4 | WIR | SPML-KCM-S-IR- 3683 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 3685 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-S-IR- 3686 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43662
4 | WIR | SPML-KCM-S-IR- 3687 | Finishes | Putty Works | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44041
4 | WIR | SPML-KCM-S-IR- 3688 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43702
4 | WIR | SPML-KCM-S-IR- 3689 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-S-IR- 3690 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43684
4 | WIR | SPML-KCM-S-IR- 3693 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43650
4 | WIR | SPML-KCM-S-IR- 3695 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43642
4 | WIR | SPML-KCM-S-IR- 3696 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-S-IR- 3700 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43992
4 | WIR | SPML-KCM-S-IR- 3715 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43653
4 | WIR | SPML-KCM-S-IR- 3716 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43767
4 | WIR | SPML-KCM-S-IR- 3725 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43654
4 | WIR | SPML-KCM-S-IR- 3732 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43654
4 | WIR | SPML-KCM-S-IR- 3733 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43654
4 | WIR | SPML-KCM-S-IR- 3734 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43677
4 | WIR | SPML-KCM-S-IR- 3740 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43660
4 | WIR | SPML-KCM-S-IR- 3742 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR- 3750 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43657
4 | WIR | SPML-KCM-S-IR- 3755 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43657
4 | WIR | SPML-KCM-S-IR- 3762 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43656
4 | WIR | SPML-KCM-S-IR- 3763 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43657
4 | WIR | SPML-KCM-S-IR- 3764 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43657
4 | WIR | SPML-KCM-S-IR- 3765 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43701
4 | WIR | SPML-KCM-S-IR- 3766 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43657
4 | WIR | SPML-KCM-S-IR- 3769 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43657
4 | WIR | SPML-KCM-S-IR- 3770 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43657
4 | WIR | SPML-KCM-S-IR- 3772 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43668
4 | WIR | SPML-KCM-S-IR- 3775 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3776 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43731
4 | WIR | SPML-KCM-S-IR- 3777 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43661
4 | WIR | SPML-KCM-S-IR- 3786 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43663
4 | WIR | SPML-KCM-S-IR- 3791 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43659
4 | WIR | SPML-KCM-S-IR- 3793 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-S-IR- 3797 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43666
4 | WIR | SPML-KCM-S-IR- 3798 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43660
4 | WIR | SPML-KCM-S-IR- 3799 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43660
4 | WIR | SPML-KCM-S-IR- 3802 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43663
4 | WIR | SPML-KCM-S-IR- 3803 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-S-IR- 3804 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3805 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3807 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43666
4 | WIR | SPML-KCM-S-IR- 3815 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43662
4 | WIR | SPML-KCM-S-IR- 3816 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43662
4 | WIR | SPML-KCM-S-IR- 3817 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-S-IR- 3818 | Concrete Works | Substation Foundation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43662
4 | WIR | SPML-KCM-S-IR- 3834 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-S-IR- 3846 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43675
4 | WIR | SPML-KCM-S-IR- 3847 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43684
4 | WIR | SPML-KCM-S-IR- 3848 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43666
4 | WIR | SPML-KCM-S-IR- 3862 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3863 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43667
4 | WIR | SPML-KCM-S-IR- 3878 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43667
4 | WIR | SPML-KCM-S-IR- 3884 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-S-IR- 3885 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-S-IR- 3886 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43664
4 | WIR | SPML-KCM-S-IR- 3887 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-S-IR- 3890 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43676
4 | WIR | SPML-KCM-S-IR- 3892 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-S-IR- 3893 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3894 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43768
4 | WIR | SPML-KCM-S-IR- 3895 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43669
4 | WIR | SPML-KCM-S-IR- 3902 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3903 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3904 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3912 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-S-IR- 3913 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43668
4 | WIR | SPML-KCM-S-IR- 3916 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43684
4 | WIR | SPML-KCM-S-IR- 3919 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3920 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-S-IR- 3927 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3928 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3929 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43702
4 | WIR | SPML-KCM-S-IR- 3930 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-S-IR- 3932 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43667
4 | WIR | SPML-KCM-S-IR- 3933 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43674
4 | WIR | SPML-KCM-S-IR- 3934 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43670
4 | WIR | SPML-KCM-S-IR- 3945 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR- 3947 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43676
4 | WIR | SPML-KCM-S-IR- 3955 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-S-IR- 3956 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-S-IR- 3958 | Foundation | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-S-IR- 3959 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-S-IR- 3960 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43673
4 | WIR | SPML-KCM-S-IR- 3961 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44151
4 | WIR | SPML-KCM-S-IR- 3969 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43678
4 | WIR | SPML-KCM-S-IR- 3970 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43674
4 | WIR | SPML-KCM-S-IR- 3971 | Finishes | Painting | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43674
4 | WIR | SPML-KCM-S-IR- 3972 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43732
4 | WIR | SPML-KCM-S-IR- 3973 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43675
4 | WIR | SPML-KCM-S-IR- 3979 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3985 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3986 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43769
4 | WIR | SPML-KCM-S-IR- 3987 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-S-IR- 4002 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43694
4 | WIR | SPML-KCM-S-IR- 4019 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-S-IR- 4020 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-S-IR- 4023 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-S-IR- 4026 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-S-IR- 4028 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR- 4032 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43680
4 | WIR | SPML-KCM-S-IR- 4033 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43730
4 | WIR | SPML-KCM-S-IR- 4034 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-S-IR- 4038 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43684
4 | WIR | SPML-KCM-S-IR- 4051 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43683
4 | WIR | SPML-KCM-S-IR- 4052 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43683
4 | WIR | SPML-KCM-S-IR- 4064 | Foundation | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43684
4 | WIR | SPML-KCM-S-IR- 4065 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43684
4 | WIR | SPML-KCM-S-IR- 4067 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-S-IR- 4070 | Finishes | Painting | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 4083 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43723
4 | WIR | SPML-KCM-S-IR- 4090 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-S-IR- 4091 | Foundation | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-S-IR- 4092 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43835
4 | WIR | SPML-KCM-S-IR- 4094 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43702
4 | WIR | SPML-KCM-S-IR- 4107 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43695
4 | WIR | SPML-KCM-S-IR- 4111 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43695
4 | WIR | SPML-KCM-S-IR- 4124 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-S-IR- 4142 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 4175 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-S-IR- 4176 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43730
4 | WIR | SPML-KCM-S-IR- 4177 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-S-IR- 4178 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43740
4 | WIR | SPML-KCM-S-IR- 4179 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43737
4 | WIR | SPML-KCM-S-IR- 4180 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-S-IR- 4184 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-S-IR- 4185 | Foundation | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-S-IR- 4194 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43703
4 | WIR | SPML-KCM-S-IR- 4195 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43730
4 | WIR | SPML-KCM-S-IR- 4196 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-S-IR- 4197 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43737
4 | WIR | SPML-KCM-S-IR- 4198 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-S-IR- 4203 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43704
4 | WIR | SPML-KCM-S-IR- 4204 | Foundation | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43772
4 | WIR | SPML-KCM-S-IR- 4205 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43722
4 | WIR | SPML-KCM-S-IR- 4208 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 4211 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43722
4 | WIR | SPML-KCM-S-IR- 4212 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 4219 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-S-IR- 4224 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43773
4 | WIR | SPML-KCM-S-IR- 4229 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 4232 | Foundation | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43709
4 | WIR | SPML-KCM-S-IR- 4233 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43709
4 | WIR | SPML-KCM-S-IR- 4242 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43709
4 | WIR | SPML-KCM-S-IR- 4247 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 4248 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43710
4 | WIR | SPML-KCM-S-IR- 4256 | Finishes | Acrylic Coating | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43712
4 | WIR | SPML-KCM-S-IR- 4257 | Foundation | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-S-IR- 4258 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-S-IR- 4262 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43773
4 | WIR | SPML-KCM-S-IR- 4265 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43740
4 | WIR | SPML-KCM-S-IR- 4270 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43773
4 | WIR | SPML-KCM-S-IR- 4271 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-S-IR- 4272 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43740
4 | WIR | SPML-KCM-S-IR- 4275 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43773
4 | WIR | SPML-KCM-S-IR- 4276 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43773
4 | WIR | SPML-KCM-S-IR- 4277 | Foundation | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43713
4 | WIR | SPML-KCM-S-IR- 4278 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43713
4 | WIR | SPML-KCM-S-IR- 4299 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43773
4 | WIR | SPML-KCM-S-IR- 4300 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43773
4 | WIR | SPML-KCM-S-IR- 4301 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-S-IR- 4310 | Foundation | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43715
4 | WIR | SPML-KCM-S-IR- 4311 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43715
4 | WIR | SPML-KCM-S-IR- 4323 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43722
4 | WIR | SPML-KCM-S-IR- 4383 | Car Park | Car Park Shade | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR- 4420 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 4429 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43737
4 | WIR | SPML-KCM-S-IR- 4448 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43729
4 | WIR | SPML-KCM-S-IR- 4455 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43731
4 | WIR | SPML-KCM-S-IR- 4462 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43726
4 | WIR | SPML-KCM-S-IR- 4485 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR- 4495 | Finishes | Painting | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43739
4 | WIR | SPML-KCM-S-IR- 4502 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43740
4 | WIR | SPML-KCM-S-IR- 4503 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43740
4 | WIR | SPML-KCM-S-IR- 4504 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-S-IR- 4511 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR- 4513 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 4540 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43737
4 | WIR | SPML-KCM-S-IR- 4563 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43739
4 | WIR | SPML-KCM-S-IR- 4564 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43739
4 | WIR | SPML-KCM-S-IR- 4565 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43739
4 | WIR | SPML-KCM-S-IR- 4575 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43740
4 | WIR | SPML-KCM-S-IR- 4576 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43740
4 | WIR | SPML-KCM-S-IR- 4622 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43743
4 | WIR | SPML-KCM-S-IR- 4640 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43744
4 | WIR | SPML-KCM-S-IR- 4641 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43744
4 | WIR | SPML-KCM-S-IR- 4642 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-S-IR- 4643 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43747
4 | WIR | SPML-KCM-S-IR- 4644 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43744
4 | WIR | SPML-KCM-S-IR- 4645 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43744
4 | WIR | SPML-KCM-S-IR- 4646 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43747
4 | WIR | SPML-KCM-S-IR- 4647 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43744
4 | WIR | SPML-KCM-S-IR- 4648 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43744
4 | WIR | SPML-KCM-S-IR- 4649 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43744
4 | WIR | SPML-KCM-S-IR- 4650 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43744
4 | WIR | SPML-KCM-S-IR- 4651 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43834
4 | WIR | SPML-KCM-S-IR- 4661 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-S-IR- 4662 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-S-IR- 4663 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-S-IR- 4691 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 4692 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 4732 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR- 4765 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43757
4 | WIR | SPML-KCM-S-IR- 4778 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 4794 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 4795 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 4796 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 4797 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 4798 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43760
4 | WIR | SPML-KCM-S-IR- 4843 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43766
4 | WIR | SPML-KCM-S-IR- 4851 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 4852 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR- 4857 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43771
4 | WIR | SPML-KCM-S-IR- 4888 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43620
4 | WIR | SPML-KCM-S-IR- 4905 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 4935 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-S-IR- 4949 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | C | 43780
4 | WIR | SPML-KCM-S-IR- 4959 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 4961 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-S-IR- 4963 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44007
4 | WIR | SPML-KCM-S-IR- 4965 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44147
4 | WIR | SPML-KCM-S-IR- 4987 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43829
4 | WIR | SPML-KCM-S-IR- 4988 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 4995 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43997
4 | WIR | SPML-KCM-S-IR- 4996 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43789
4 | WIR | SPML-KCM-S-IR- 5005 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 43788
4 | WIR | SPML-KCM-S-IR- 5032 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43940
4 | WIR | SPML-KCM-S-IR- 5033 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43962
4 | WIR | SPML-KCM-S-IR- 5042 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43998
4 | WIR | SPML-KCM-S-IR- 5095 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-S-IR- 5104 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5107 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 5109 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5127 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44174
4 | WIR | SPML-KCM-S-IR- 5141 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43809
4 | WIR | SPML-KCM-S-IR- 5145 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 5146 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43810
4 | WIR | SPML-KCM-S-IR- 5151 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43810
4 | WIR | SPML-KCM-S-IR- 5153 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43962
4 | WIR | SPML-KCM-S-IR- 5154 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-S-IR- 5157 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43811
4 | WIR | SPML-KCM-S-IR- 5158 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR- 5160 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44048
4 | WIR | SPML-KCM-S-IR- 5164 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43852
4 | WIR | SPML-KCM-S-IR- 5165 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43852
4 | WIR | SPML-KCM-S-IR- 5166 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43852
4 | WIR | SPML-KCM-S-IR- 5172 | Finishes | Gypsum Wall | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 5183 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-S-IR- 5209 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-S-IR- 5216 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43962
4 | WIR | SPML-KCM-S-IR- 5220 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-S-IR- 5224 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-S-IR- 5236 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 5237 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5260 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-S-IR- 5267 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-S-IR- 5269 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43992
4 | WIR | SPML-KCM-S-IR- 5271 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-S-IR- 5280 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43982
4 | WIR | SPML-KCM-S-IR- 5292 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR- 5293 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 5305 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43837
4 | WIR | SPML-KCM-S-IR- 5325 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-S-IR- 5330 | Walls | Block Work | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43841
4 | WIR | SPML-KCM-S-IR- 5347 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-S-IR- 5359 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44006
4 | WIR | SPML-KCM-S-IR- 5360 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44006
4 | WIR | SPML-KCM-S-IR- 5361 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43948
4 | WIR | SPML-KCM-S-IR- 5362 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-S-IR- 5390 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-S-IR- 5399 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43846
4 | WIR | SPML-KCM-S-IR- 5400 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43846
4 | WIR | SPML-KCM-S-IR- 5407 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-S-IR- 5408 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-S-IR- 5412 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-S-IR- 5434 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44159
4 | WIR | SPML-KCM-S-IR- 5452 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-S-IR- 5465 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44137
4 | WIR | SPML-KCM-S-IR- 5475 | Concrete Works | OTS Wall | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-S-IR- 5496 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43857
4 | WIR | SPML-KCM-S-IR- 5539 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43860
4 | WIR | SPML-KCM-S-IR- 5543 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43860
4 | WIR | SPML-KCM-S-IR- 5551 | Space Protection System | Bollards | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-S-IR- 5553 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5557 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5559 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5560 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5566 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-S-IR- 5567 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44233
4 | WIR | SPML-KCM-S-IR- 5568 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR- 5569 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43985
4 | WIR | SPML-KCM-S-IR- 5570 | Finishes | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 5571 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43985
4 | WIR | SPML-KCM-S-IR- 5572 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-S-IR- 5573 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-S-IR- 5587 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5589 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5592 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-S-IR- 5595 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44205
4 | WIR | SPML-KCM-S-IR- 5596 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 5597 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44233
4 | WIR | SPML-KCM-S-IR- 5598 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-S-IR- 5605 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5606 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5609 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43906
4 | WIR | SPML-KCM-S-IR- 5613 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR- 5614 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44177
4 | WIR | SPML-KCM-S-IR- 5633 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-S-IR- 5646 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR- 5656 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5667 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-S-IR- 5668 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 5691 | Space Protection System | Bollards | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43997
4 | WIR | SPML-KCM-S-IR- 5708 | Space Protection System | Bollards | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43997
4 | WIR | SPML-KCM-S-IR- 5767 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-S-IR- 5792 | Finishes | Epoxy | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44088
4 | WIR | SPML-KCM-S-IR- 5793 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-S-IR- 5794 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43936
4 | WIR | SPML-KCM-S-IR- 5795 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-S-IR- 5804 | Space Protection System | Bollards | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-S-IR- 5806 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-S-IR- 5807 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-S-IR- 5808 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-S-IR- 5809 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-S-IR- 5860 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-S-IR- 5870 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-S-IR- 5881 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR- 5889 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR- 5902 | Finishes | Glazing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-S-IR- 5903 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43950
4 | WIR | SPML-KCM-S-IR- 5925 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-S-IR- 5926 | Structural System | Roofing Purlins | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 5962 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43901
4 | WIR | SPML-KCM-S-IR- 6115 | Finishes | Epoxy | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44047
4 | WIR | SPML-KCM-S-IR- 6147 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR- 6243 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44051
4 | WIR | SPML-KCM-S-IR- 6260 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44125
4 | WIR | SPML-KCM-S-IR- 6267 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR- 6282 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR- 6288 | Car Park | Car Park Shade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-S-IR- 6310 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR- 6311 | Floor | Floor Screed | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-S-IR- 6397 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44079
4 | WIR | SPML-KCM-S-IR- 6398 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-S-IR- 6416 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-S-IR- 6420 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44060
4 | WIR | SPML-KCM-S-IR- 6421 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44254
4 | WIR | SPML-KCM-S-IR- 6422 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-S-IR- 6423 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43690
4 | WIR | SPML-KCM-S-IR- 6433 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR- 6440 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-S-IR- 6444 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44174
4 | WIR | SPML-KCM-S-IR- 6474 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44067
4 | WIR | SPML-KCM-S-IR- 6480 | Finishes | Carbon Fibre | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44254
4 | WIR | SPML-KCM-S-IR- 6482 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 6487 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44073
4 | WIR | SPML-KCM-S-IR- 6524 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-S-IR- 6525 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-S-IR- 6531 | FF&E | Totem | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44254
4 | WIR | SPML-KCM-S-IR- 6533 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44163
4 | WIR | SPML-KCM-S-IR- 6535 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44079
4 | WIR | SPML-KCM-S-IR- 6659 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR- 6660 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | C | 44093
4 | WIR | SPML-KCM-S-IR- 6679 | Signages | Wayfinding Signages | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44104
4 | WIR | SPML-KCM-S-IR- 6694 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44116
4 | WIR | SPML-KCM-S-IR- 6695 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43849
4 | WIR | SPML-KCM-S-IR- 6697 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-S-IR- 6698 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44129
4 | WIR | SPML-KCM-S-IR- 6699 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-S-IR- 6706 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44059
4 | WIR | SPML-KCM-S-IR- 6707 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44129
4 | WIR | SPML-KCM-S-IR- 6709 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 6719 | Finishes | Aqua Panel | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44058
4 | WIR | SPML-KCM-S-IR- 6726 | Fire Fighting System | Deluge System | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44132
4 | WIR | SPML-KCM-S-IR- 6753 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44124
4 | WIR | SPML-KCM-S-IR- 6820 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-S-IR- 6883 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44137
4 | WIR | SPML-KCM-S-IR- 6884 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44111
4 | WIR | SPML-KCM-S-IR- 6895 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44128
4 | WIR | SPML-KCM-S-IR- 6900 | Finishes | Aluminum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44132
4 | WIR | SPML-KCM-S-IR- 6901 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR- 6914 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-S-IR- 6917 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44105
4 | WIR | SPML-KCM-S-IR- 6934 | Finishes | Ceiling Tiles | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-S-IR- 6944 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44189
4 | WIR | SPML-KCM-S-IR- 6945 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 6946 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 6947 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR- 6948 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 6949 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 6950 | Pole | Flag Pole | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44170
4 | WIR | SPML-KCM-S-IR- 6963 | Finishes | Painting | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 6964 | Finishes | Painting | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR- 6965 | Finishes | Painting | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-0281 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43313
4 | WIR | SPML-KCM-S-IR-0282 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43313
4 | WIR | SPML-KCM-S-IR-0283 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43313
4 | WIR | SPML-KCM-S-IR-0284 | Foundation | Excavation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43314
4 | WIR | SPML-KCM-S-IR-0285 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43316
4 | WIR | SPML-KCM-S-IR-0286 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43316
4 | WIR | SPML-KCM-S-IR-0287 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43316
4 | WIR | SPML-KCM-S-IR-0288 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44143
4 | WIR | SPML-KCM-S-IR-0289 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43316
4 | WIR | SPML-KCM-S-IR-0290 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43316
4 | WIR | SPML-KCM-S-IR-0291 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43316
4 | WIR | SPML-KCM-S-IR-0292 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43316
4 | WIR | SPML-KCM-S-IR-0293 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43318
4 | WIR | SPML-KCM-S-IR-0294 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43318
4 | WIR | SPML-KCM-S-IR-0295 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43318
4 | WIR | SPML-KCM-S-IR-0296 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43318
4 | WIR | SPML-KCM-S-IR-0297 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43318
4 | WIR | SPML-KCM-S-IR-0298 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43318
4 | WIR | SPML-KCM-S-IR-0299 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43318
4 | WIR | SPML-KCM-S-IR-0300 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43318
4 | WIR | SPML-KCM-S-IR-0301 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43318
4 | WIR | SPML-KCM-S-IR-0302 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43318
4 | WIR | SPML-KCM-S-IR-0303 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0304 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43323
4 | WIR | SPML-KCM-S-IR-0305 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-0306 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43319
4 | WIR | SPML-KCM-S-IR-0307 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43319
4 | WIR | SPML-KCM-S-IR-0308 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43319
4 | WIR | SPML-KCM-S-IR-0309 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43320
4 | WIR | SPML-KCM-S-IR-0310 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43320
4 | WIR | SPML-KCM-S-IR-0311 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43320
4 | WIR | SPML-KCM-S-IR-0312 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0313 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0314 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0315 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-0316 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0317 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0318 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0319 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43323
4 | WIR | SPML-KCM-S-IR-0320 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0321 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0322 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0323 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0324 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43321
4 | WIR | SPML-KCM-S-IR-0325 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43323
4 | WIR | SPML-KCM-S-IR-0326 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43323
4 | WIR | SPML-KCM-S-IR-0327 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43323
4 | WIR | SPML-KCM-S-IR-0328 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43323
4 | WIR | SPML-KCM-S-IR-0329 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43323
4 | WIR | SPML-KCM-S-IR-0330 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43323
4 | WIR | SPML-KCM-S-IR-0331 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-0332 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43323
4 | WIR | SPML-KCM-S-IR-0333 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43325
4 | WIR | SPML-KCM-S-IR-0334 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43323
4 | WIR | SPML-KCM-S-IR-0335 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43325
4 | WIR | SPML-KCM-S-IR-0337 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43324
4 | WIR | SPML-KCM-S-IR-0338 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43325
4 | WIR | SPML-KCM-S-IR-0339 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43325
4 | WIR | SPML-KCM-S-IR-0340 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43325
4 | WIR | SPML-KCM-S-IR-0341 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43325
4 | WIR | SPML-KCM-S-IR-0342 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43325
4 | WIR | SPML-KCM-S-IR-0343 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43325
4 | WIR | SPML-KCM-S-IR-0344 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43325
4 | WIR | SPML-KCM-S-IR-0345 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43325
4 | WIR | SPML-KCM-S-IR-0346 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43325
4 | WIR | SPML-KCM-S-IR-0347 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43326
4 | WIR | SPML-KCM-S-IR-0348 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43326
4 | WIR | SPML-KCM-S-IR-0349 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-0350 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43326
4 | WIR | SPML-KCM-S-IR-0351 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43326
4 | WIR | SPML-KCM-S-IR-0352 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43328
4 | WIR | SPML-KCM-S-IR-0353 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43327
4 | WIR | SPML-KCM-S-IR-0354 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43327
4 | WIR | SPML-KCM-S-IR-0355 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43327
4 | WIR | SPML-KCM-S-IR-0356 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43327
4 | WIR | SPML-KCM-S-IR-0357 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43327
4 | WIR | SPML-KCM-S-IR-0358 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-0359 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43327
4 | WIR | SPML-KCM-S-IR-0360 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43327
4 | WIR | SPML-KCM-S-IR-0361 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43327
4 | WIR | SPML-KCM-S-IR-0362 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0363 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0364 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0365 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0366 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0367 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43328
4 | WIR | SPML-KCM-S-IR-0368 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43328
4 | WIR | SPML-KCM-S-IR-0369 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43328
4 | WIR | SPML-KCM-S-IR-0370 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43328
4 | WIR | SPML-KCM-S-IR-0371 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43328
4 | WIR | SPML-KCM-S-IR-0372 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43328
4 | WIR | SPML-KCM-S-IR-0373 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43328
4 | WIR | SPML-KCM-S-IR-0374 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43328
4 | WIR | SPML-KCM-S-IR-0375 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43328
4 | WIR | SPML-KCM-S-IR-0376 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0377 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0378 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0379 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0380 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0381 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0382 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43330
4 | WIR | SPML-KCM-S-IR-0383 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43331
4 | WIR | SPML-KCM-S-IR-0384 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43331
4 | WIR | SPML-KCM-S-IR-0385 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43331
4 | WIR | SPML-KCM-S-IR-0387 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43332
4 | WIR | SPML-KCM-S-IR-0388 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43332
4 | WIR | SPML-KCM-S-IR-0389 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43332
4 | WIR | SPML-KCM-S-IR-0390 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43332
4 | WIR | SPML-KCM-S-IR-0391 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43335
4 | WIR | SPML-KCM-S-IR-0392 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43332
4 | WIR | SPML-KCM-S-IR-0393 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43332
4 | WIR | SPML-KCM-S-IR-0394 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43332
4 | WIR | SPML-KCM-S-IR-0395 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43332
4 | WIR | SPML-KCM-S-IR-0396 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43332
4 | WIR | SPML-KCM-S-IR-0398 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43335
4 | WIR | SPML-KCM-S-IR-0399 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43335
4 | WIR | SPML-KCM-S-IR-0400 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0403 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0404 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0405 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0407 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0408 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0409 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0410 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0413 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0414 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0415 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0416 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0417 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0419 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0420 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43337
4 | WIR | SPML-KCM-S-IR-0421 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43338
4 | WIR | SPML-KCM-S-IR-0426 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43338
4 | WIR | SPML-KCM-S-IR-0427 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43338
4 | WIR | SPML-KCM-S-IR-0428 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43338
4 | WIR | SPML-KCM-S-IR-0429 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43338
4 | WIR | SPML-KCM-S-IR-0430 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43338
4 | WIR | SPML-KCM-S-IR-0431 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43338
4 | WIR | SPML-KCM-S-IR-0434 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43339
4 | WIR | SPML-KCM-S-IR-0435 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43339
4 | WIR | SPML-KCM-S-IR-0436 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43339
4 | WIR | SPML-KCM-S-IR-0437 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43339
4 | WIR | SPML-KCM-S-IR-0438 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43339
4 | WIR | SPML-KCM-S-IR-0439 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43339
4 | WIR | SPML-KCM-S-IR-0440 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43339
4 | WIR | SPML-KCM-S-IR-0441 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43339
4 | WIR | SPML-KCM-S-IR-0442 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43339
4 | WIR | SPML-KCM-S-IR-0443 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0444 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0445 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-S-IR-0446 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0447 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0450 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0451 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0452 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43342
4 | WIR | SPML-KCM-S-IR-0453 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43342
4 | WIR | SPML-KCM-S-IR-0454 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43342
4 | WIR | SPML-KCM-S-IR-0455 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-S-IR-0456 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0457 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0458 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0459 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0460 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-S-IR-0461 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0462 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0463 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0464 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43340
4 | WIR | SPML-KCM-S-IR-0465 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-S-IR-0466 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0467 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-S-IR-0468 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-S-IR-0469 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-S-IR-0471 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-S-IR-0472 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0475 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-S-IR-0476 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-S-IR-0477 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43341
4 | WIR | SPML-KCM-S-IR-0478 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43342
4 | WIR | SPML-KCM-S-IR-0479 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43342
4 | WIR | SPML-KCM-S-IR-0480 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43342
4 | WIR | SPML-KCM-S-IR-0481 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0482 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0483 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0484 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0486 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0487 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0488 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0489 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0490 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0491 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0492 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0493 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0494 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0495 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43344
4 | WIR | SPML-KCM-S-IR-0496 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0497 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0498 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0499 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0500 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0501 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0502 | Foundation | Excavation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0503 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0504 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-S-IR-0505 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0506 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0507 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-S-IR-0508 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0509 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0510 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0511 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0512 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0513 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0514 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0515 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0516 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43345
4 | WIR | SPML-KCM-S-IR-0517 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-S-IR-0518 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-S-IR-0519 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-S-IR-0520 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-S-IR-0521 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-S-IR-0522 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-S-IR-0523 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-S-IR-0524 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-S-IR-0525 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43346
4 | WIR | SPML-KCM-S-IR-0527 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43347
4 | WIR | SPML-KCM-S-IR-0528 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43347
4 | WIR | SPML-KCM-S-IR-0529 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43347
4 | WIR | SPML-KCM-S-IR-0530 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43347
4 | WIR | SPML-KCM-S-IR-0531 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43347
4 | WIR | SPML-KCM-S-IR-0532 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-S-IR-0533 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-S-IR-0534 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43347
4 | WIR | SPML-KCM-S-IR-0535 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43347
4 | WIR | SPML-KCM-S-IR-0536 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43347
4 | WIR | SPML-KCM-S-IR-0537 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43347
4 | WIR | SPML-KCM-S-IR-0538 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0540 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0541 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43347
4 | WIR | SPML-KCM-S-IR-0542 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0543 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0544 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0545 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0548 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0549 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0550 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0551 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0552 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0553 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0554 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0555 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43349
4 | WIR | SPML-KCM-S-IR-0556 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43348
4 | WIR | SPML-KCM-S-IR-0557 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43349
4 | WIR | SPML-KCM-S-IR-0558 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43349
4 | WIR | SPML-KCM-S-IR-0559 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43351
4 | WIR | SPML-KCM-S-IR-0560 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43349
4 | WIR | SPML-KCM-S-IR-0561 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43349
4 | WIR | SPML-KCM-S-IR-0562 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43349
4 | WIR | SPML-KCM-S-IR-0563 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43349
4 | WIR | SPML-KCM-S-IR-0564 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43349
4 | WIR | SPML-KCM-S-IR-0565 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43351
4 | WIR | SPML-KCM-S-IR-0566 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43351
4 | WIR | SPML-KCM-S-IR-0567 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43351
4 | WIR | SPML-KCM-S-IR-0569 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-0570 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43351
4 | WIR | SPML-KCM-S-IR-0571 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-0572 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43352
4 | WIR | SPML-KCM-S-IR-0573 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-0574 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43351
4 | WIR | SPML-KCM-S-IR-0576 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43351
4 | WIR | SPML-KCM-S-IR-0577 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43351
4 | WIR | SPML-KCM-S-IR-0578 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43351
4 | WIR | SPML-KCM-S-IR-0579 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43352
4 | WIR | SPML-KCM-S-IR-0580 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43352
4 | WIR | SPML-KCM-S-IR-0581 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43352
4 | WIR | SPML-KCM-S-IR-0582 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43352
4 | WIR | SPML-KCM-S-IR-0583 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43352
4 | WIR | SPML-KCM-S-IR-0584 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43352
4 | WIR | SPML-KCM-S-IR-0585 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-S-IR-0586 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43352
4 | WIR | SPML-KCM-S-IR-0587 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43352
4 | WIR | SPML-KCM-S-IR-0588 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43352
4 | WIR | SPML-KCM-S-IR-0589 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43352
4 | WIR | SPML-KCM-S-IR-0590 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-S-IR-0591 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-S-IR-0592 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-S-IR-0593 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-S-IR-0595 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-S-IR-0596 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-S-IR-0597 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-S-IR-0598 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-S-IR-0599 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-S-IR-0600 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43353
4 | WIR | SPML-KCM-S-IR-0601 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43358
4 | WIR | SPML-KCM-S-IR-0602 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43358
4 | WIR | SPML-KCM-S-IR-0603 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-S-IR-0604 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-S-IR-0606 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-S-IR-0607 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-S-IR-0608 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-S-IR-0609 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-S-IR-0610 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-S-IR-0611 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-S-IR-0612 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-S-IR-0613 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43354
4 | WIR | SPML-KCM-S-IR-0614 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0615 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0616 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0617 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0618 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0619 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0620 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0621 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0622 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0623 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0624 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0625 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43358
4 | WIR | SPML-KCM-S-IR-0626 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43358
4 | WIR | SPML-KCM-S-IR-0628 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-0629 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0630 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0631 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0632 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0633 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0634 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43355
4 | WIR | SPML-KCM-S-IR-0635 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43358
4 | WIR | SPML-KCM-S-IR-0636 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-0638 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43358
4 | WIR | SPML-KCM-S-IR-0639 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43358
4 | WIR | SPML-KCM-S-IR-0640 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43358
4 | WIR | SPML-KCM-S-IR-0641 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0642 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0643 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0644 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0645 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0646 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0647 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0648 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0649 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0650 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0652 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0653 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0654 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0655 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0656 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0657 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43360
4 | WIR | SPML-KCM-S-IR-0659 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0660 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0661 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0662 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0663 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0664 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-0665 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43378
4 | WIR | SPML-KCM-S-IR-0666 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0667 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0669 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43362
4 | WIR | SPML-KCM-S-IR-0670 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0671 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0672 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0673 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43362
4 | WIR | SPML-KCM-S-IR-0674 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43362
4 | WIR | SPML-KCM-S-IR-0675 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43362
4 | WIR | SPML-KCM-S-IR-0676 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43362
4 | WIR | SPML-KCM-S-IR-0677 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43362
4 | WIR | SPML-KCM-S-IR-0678 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0679 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0680 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0681 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0682 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0683 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43361
4 | WIR | SPML-KCM-S-IR-0684 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43362
4 | WIR | SPML-KCM-S-IR-0685 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43362
4 | WIR | SPML-KCM-S-IR-0686 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43362
4 | WIR | SPML-KCM-S-IR-0687 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43365
4 | WIR | SPML-KCM-S-IR-0688 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0689 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0690 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0691 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0692 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0693 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0694 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0695 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0696 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0697 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0698 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0699 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0700 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0701 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0702 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43363
4 | WIR | SPML-KCM-S-IR-0704 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43365
4 | WIR | SPML-KCM-S-IR-0705 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43365
4 | WIR | SPML-KCM-S-IR-0706 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43365
4 | WIR | SPML-KCM-S-IR-0707 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0708 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0710 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0711 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0712 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0713 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0714 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0715 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0716 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0717 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0718 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0719 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43366
4 | WIR | SPML-KCM-S-IR-0720 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0721 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0722 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0723 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0724 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0726 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0727 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0728 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0729 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0730 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0731 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0732 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-S-IR-0733 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0734 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0735 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43369
4 | WIR | SPML-KCM-S-IR-0736 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0737 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0738 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43367
4 | WIR | SPML-KCM-S-IR-0739 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-S-IR-0740 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-S-IR-0744 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-S-IR-0745 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-S-IR-0746 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-S-IR-0747 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-S-IR-0748 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43368
4 | WIR | SPML-KCM-S-IR-0749 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-S-IR-0750 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-S-IR-0751 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-S-IR-0752 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43368
4 | WIR | SPML-KCM-S-IR-0753 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43369
4 | WIR | SPML-KCM-S-IR-0754 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43369
4 | WIR | SPML-KCM-S-IR-0755 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43369
4 | WIR | SPML-KCM-S-IR-0756 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0757 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-S-IR-0758 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43369
4 | WIR | SPML-KCM-S-IR-0759 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43370
4 | WIR | SPML-KCM-S-IR-0760 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43369
4 | WIR | SPML-KCM-S-IR-0761 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43369
4 | WIR | SPML-KCM-S-IR-0762 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43369
4 | WIR | SPML-KCM-S-IR-0763 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43369
4 | WIR | SPML-KCM-S-IR-0764 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43369
4 | WIR | SPML-KCM-S-IR-0765 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43370
4 | WIR | SPML-KCM-S-IR-0766 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43370
4 | WIR | SPML-KCM-S-IR-0767 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43371
4 | WIR | SPML-KCM-S-IR-0768 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43370
4 | WIR | SPML-KCM-S-IR-0769 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43386
4 | WIR | SPML-KCM-S-IR-0770 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43370
4 | WIR | SPML-KCM-S-IR-0771 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43370
4 | WIR | SPML-KCM-S-IR-0772 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-S-IR-0773 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-S-IR-0774 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-S-IR-0775 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-S-IR-0776 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-S-IR-0777 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-S-IR-0778 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-S-IR-0779 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-S-IR-0780 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-S-IR-0781 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43372
4 | WIR | SPML-KCM-S-IR-0784 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43373
4 | WIR | SPML-KCM-S-IR-0785 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43373
4 | WIR | SPML-KCM-S-IR-0786 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43373
4 | WIR | SPML-KCM-S-IR-0787 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43373
4 | WIR | SPML-KCM-S-IR-0788 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43373
4 | WIR | SPML-KCM-S-IR-0789 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43373
4 | WIR | SPML-KCM-S-IR-0790 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43370
4 | WIR | SPML-KCM-S-IR-0791 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43373
4 | WIR | SPML-KCM-S-IR-0792 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43374
4 | WIR | SPML-KCM-S-IR-0793 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43373
4 | WIR | SPML-KCM-S-IR-0794 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR-0795 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43379
4 | WIR | SPML-KCM-S-IR-0796 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43374
4 | WIR | SPML-KCM-S-IR-0797 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43374
4 | WIR | SPML-KCM-S-IR-0798 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43374
4 | WIR | SPML-KCM-S-IR-0799 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43374
4 | WIR | SPML-KCM-S-IR-0802 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43375
4 | WIR | SPML-KCM-S-IR-0803 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43375
4 | WIR | SPML-KCM-S-IR-0804 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43375
4 | WIR | SPML-KCM-S-IR-0805 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43375
4 | WIR | SPML-KCM-S-IR-0806 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0807 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0808 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0809 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0810 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43375
4 | WIR | SPML-KCM-S-IR-0811 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0812 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0813 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0814 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0815 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0816 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0817 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0818 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0819 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0820 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0821 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0822 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0823 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43376
4 | WIR | SPML-KCM-S-IR-0824 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43377
4 | WIR | SPML-KCM-S-IR-0825 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0826 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0827 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0828 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0829 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0830 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0831 | Foundation | Excavation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0832 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0833 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0834 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0835 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0838 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0839 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0840 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43377
4 | WIR | SPML-KCM-S-IR-0843 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43379
4 | WIR | SPML-KCM-S-IR-0844 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43379
4 | WIR | SPML-KCM-S-IR-0845 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43379
4 | WIR | SPML-KCM-S-IR-0846 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43379
4 | WIR | SPML-KCM-S-IR-0847 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0848 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43389
4 | WIR | SPML-KCM-S-IR-0849 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43389
4 | WIR | SPML-KCM-S-IR-0850 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43389
4 | WIR | SPML-KCM-S-IR-0851 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0852 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0853 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0854 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0855 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-S-IR-0856 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-S-IR-0857 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0858 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0859 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0860 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0861 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0862 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0863 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0865 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0866 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0867 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-S-IR-0868 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43380
4 | WIR | SPML-KCM-S-IR-0869 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-0870 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-S-IR-0871 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-S-IR-0872 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-S-IR-0873 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-S-IR-0874 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-S-IR-0877 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0878 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0879 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0880 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-S-IR-0881 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-S-IR-0882 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43381
4 | WIR | SPML-KCM-S-IR-0883 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0884 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0885 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0886 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0887 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0888 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43383
4 | WIR | SPML-KCM-S-IR-0889 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43383
4 | WIR | SPML-KCM-S-IR-0890 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0891 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0892 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0893 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0894 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0895 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0896 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43383
4 | WIR | SPML-KCM-S-IR-0897 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43383
4 | WIR | SPML-KCM-S-IR-0898 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43383
4 | WIR | SPML-KCM-S-IR-0899 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43383
4 | WIR | SPML-KCM-S-IR-0900 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43383
4 | WIR | SPML-KCM-S-IR-0901 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43383
4 | WIR | SPML-KCM-S-IR-0902 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43383
4 | WIR | SPML-KCM-S-IR-0904 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43384
4 | WIR | SPML-KCM-S-IR-0905 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43383
4 | WIR | SPML-KCM-S-IR-0906 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43383
4 | WIR | SPML-KCM-S-IR-0907 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43384
4 | WIR | SPML-KCM-S-IR-0908 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-0909 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43386
4 | WIR | SPML-KCM-S-IR-0910 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43384
4 | WIR | SPML-KCM-S-IR-0911 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43384
4 | WIR | SPML-KCM-S-IR-0912 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0913 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-S-IR-0914 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43384
4 | WIR | SPML-KCM-S-IR-0915 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0916 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43384
4 | WIR | SPML-KCM-S-IR-0917 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43384
4 | WIR | SPML-KCM-S-IR-0918 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43384
4 | WIR | SPML-KCM-S-IR-0919 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43384
4 | WIR | SPML-KCM-S-IR-0920 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43382
4 | WIR | SPML-KCM-S-IR-0921 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43384
4 | WIR | SPML-KCM-S-IR-0922 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43386
4 | WIR | SPML-KCM-S-IR-0923 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43386
4 | WIR | SPML-KCM-S-IR-0924 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43386
4 | WIR | SPML-KCM-S-IR-0925 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43386
4 | WIR | SPML-KCM-S-IR-0926 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43386
4 | WIR | SPML-KCM-S-IR-0927 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43386
4 | WIR | SPML-KCM-S-IR-0928 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43386
4 | WIR | SPML-KCM-S-IR-0929 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43386
4 | WIR | SPML-KCM-S-IR-0930 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0931 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0932 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0934 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0935 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0936 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0937 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0938 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0939 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0940 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0941 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-0942 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43482
4 | WIR | SPML-KCM-S-IR-0943 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0944 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43387
4 | WIR | SPML-KCM-S-IR-0945 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43369
4 | WIR | SPML-KCM-S-IR-0946 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0947 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0948 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0949 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0950 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0951 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0952 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-0953 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43414
4 | WIR | SPML-KCM-S-IR-0954 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0955 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0956 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0957 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0958 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0959 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0960 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0961 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0962 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0963 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0964 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-0965 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43389
4 | WIR | SPML-KCM-S-IR-0966 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43388
4 | WIR | SPML-KCM-S-IR-0967 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0968 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-0969 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43389
4 | WIR | SPML-KCM-S-IR-0970 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43389
4 | WIR | SPML-KCM-S-IR-0971 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43389
4 | WIR | SPML-KCM-S-IR-0972 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0973 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43389
4 | WIR | SPML-KCM-S-IR-0974 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0975 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43389
4 | WIR | SPML-KCM-S-IR-0976 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43389
4 | WIR | SPML-KCM-S-IR-0977 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0978 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0979 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0980 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-0981 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0982 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43286
4 | WIR | SPML-KCM-S-IR-0983 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0984 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0985 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0986 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0987 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0988 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0989 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0990 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0991 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-0992 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43389
4 | WIR | SPML-KCM-S-IR-0993 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-S-IR-0994 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0995 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43379
4 | WIR | SPML-KCM-S-IR-0996 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0997 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0998 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-0999 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-1000 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1001 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1002 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1003 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1004 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1005 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1006 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1007 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1008 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1009 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1010 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1011 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1012 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1013 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1014 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1015 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43390
4 | WIR | SPML-KCM-S-IR-1016 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1017 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1018 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43391
4 | WIR | SPML-KCM-S-IR-1019 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1020 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1021 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1022 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1023 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1024 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1025 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1026 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1027 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1028 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1029 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1030 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1031 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR-1032 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR-1033 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-S-IR-1034 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1036 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1037 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1038 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1039 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1040 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1041 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1042 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1043 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1044 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1045 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1046 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43393
4 | WIR | SPML-KCM-S-IR-1047 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1048 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1049 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1050 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1051 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1052 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1053 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1054 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1055 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1056 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1057 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1058 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR-1059 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1060 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1061 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43399
4 | WIR | SPML-KCM-S-IR-1062 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1063 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1064 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1065 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1066 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1067 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1068 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1069 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43395
4 | WIR | SPML-KCM-S-IR-1070 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1071 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1072 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43394
4 | WIR | SPML-KCM-S-IR-1073 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1074 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1075 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1076 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1077 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1078 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1079 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1080 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1081 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1082 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1083 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1084 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43396
4 | WIR | SPML-KCM-S-IR-1085 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43379
4 | WIR | SPML-KCM-S-IR-1086 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1087 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1088 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1089 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1090 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1091 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1092 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1093 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1094 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1095 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1096 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1097 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1098 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1099 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1100 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1101 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1102 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1103 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-1104 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1105 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43397
4 | WIR | SPML-KCM-S-IR-1106 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1107 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1108 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1109 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1110 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1111 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1112 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1113 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1114 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1115 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1116 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1117 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1118 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1119 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1120 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1121 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1122 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1123 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1124 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1125 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43398
4 | WIR | SPML-KCM-S-IR-1126 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1127 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1128 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1129 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1130 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1131 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1132 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1133 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1134 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1135 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1136 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1137 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1138 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1139 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1140 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1141 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1142 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1143 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1144 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1145 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1146 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-S-IR-1147 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1148 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1149 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43379
4 | WIR | SPML-KCM-S-IR-1150 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1151 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1152 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1153 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1154 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1155 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1156 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1157 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1158 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1159 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1160 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1161 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43400
4 | WIR | SPML-KCM-S-IR-1162 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1163 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43399
4 | WIR | SPML-KCM-S-IR-1164 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43401
4 | WIR | SPML-KCM-S-IR-1165 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1166 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1167 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1168 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43422
4 | WIR | SPML-KCM-S-IR-1169 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1170 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1171 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1172 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1173 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1174 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1175 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1176 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1177 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43439
4 | WIR | SPML-KCM-S-IR-1179 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1180 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43439
4 | WIR | SPML-KCM-S-IR-1181 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1182 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1183 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1184 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1185 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1186 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1187 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1188 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1189 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1190 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43608
4 | WIR | SPML-KCM-S-IR-1191 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1192 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1193 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1194 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1195 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1196 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1197 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1198 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1199 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1200 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1201 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1202 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1203 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43405
4 | WIR | SPML-KCM-S-IR-1204 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1205 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1206 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1207 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1208 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1209 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1210 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1211 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1212 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1213 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1214 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1215 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43405
4 | WIR | SPML-KCM-S-IR-1216 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43405
4 | WIR | SPML-KCM-S-IR-1217 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1218 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1219 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1220 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1221 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1222 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1223 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43406
4 | WIR | SPML-KCM-S-IR-1224 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1225 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1226 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43404
4 | WIR | SPML-KCM-S-IR-1227 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1228 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1229 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1230 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1231 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1232 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1233 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1234 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1235 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1236 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1237 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1238 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43606
4 | WIR | SPML-KCM-S-IR-1239 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1240 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43403
4 | WIR | SPML-KCM-S-IR-1241 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-1242 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43405
4 | WIR | SPML-KCM-S-IR-1243 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43405
4 | WIR | SPML-KCM-S-IR-1244 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1245 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1246 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1247 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1248 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1249 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1250 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1251 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1252 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43405
4 | WIR | SPML-KCM-S-IR-1253 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1254 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1255 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1256 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43405
4 | WIR | SPML-KCM-S-IR-1257 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1258 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43405
4 | WIR | SPML-KCM-S-IR-1259 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43405
4 | WIR | SPML-KCM-S-IR-1260 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43405
4 | WIR | SPML-KCM-S-IR-1261 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43405
4 | WIR | SPML-KCM-S-IR-1262 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1263 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1264 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1265 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1266 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1267 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1268 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1269 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1270 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1271 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1272 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1273 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1274 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1275 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1276 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43406
4 | WIR | SPML-KCM-S-IR-1277 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1278 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1279 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1280 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1281 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1282 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1283 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1284 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1285 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1286 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1287 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43407
4 | WIR | SPML-KCM-S-IR-1288 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1289 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-S-IR-1290 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1291 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43606
4 | WIR | SPML-KCM-S-IR-1292 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1293 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-1294 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1295 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1296 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1297 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1298 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1299 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1300 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1301 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1302 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1303 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1304 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR-1305 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR-1306 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1307 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1308 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1309 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1310 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1311 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1312 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1313 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1314 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1315 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1316 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1317 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1318 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1319 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1320 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43471
4 | WIR | SPML-KCM-S-IR-1321 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1322 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1323 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1324 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43408
4 | WIR | SPML-KCM-S-IR-1326 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1327 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-1328 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-1329 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1330 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1331 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1332 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43412
4 | WIR | SPML-KCM-S-IR-1333 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-S-IR-1334 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1335 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1336 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1337 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-S-IR-1338 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1339 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1340 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1341 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1342 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1343 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1344 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1345 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1346 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1347 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1348 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1349 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1350 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1351 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1352 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1353 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1354 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1355 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1356 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1357 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1358 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43409
4 | WIR | SPML-KCM-S-IR-1359 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1360 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1361 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1362 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1363 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1364 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1365 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1366 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1367 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1368 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1369 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1370 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1371 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43410
4 | WIR | SPML-KCM-S-IR-1372 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1373 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1374 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1375 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1376 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1377 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1378 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1379 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1380 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1381 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1382 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1383 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1384 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1385 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1386 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1387 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1388 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1389 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1390 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1391 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1392 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1393 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1394 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1395 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1396 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1397 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1398 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1399 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1400 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1401 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1402 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1403 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1404 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1405 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1406 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1407 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1408 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43411
4 | WIR | SPML-KCM-S-IR-1409 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1410 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1411 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1412 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1413 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1414 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1415 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR-1416 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1417 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1418 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-S-IR-1419 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-S-IR-1420 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1421 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1422 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1423 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1424 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1425 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1426 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43626
4 | WIR | SPML-KCM-S-IR-1427 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1428 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR-1429 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR-1430 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1431 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1432 | Foundation | Excavation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1433 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1434 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1435 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1436 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1437 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1438 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1439 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1440 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1441 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43414
4 | WIR | SPML-KCM-S-IR-1442 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43414
4 | WIR | SPML-KCM-S-IR-1443 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43414
4 | WIR | SPML-KCM-S-IR-1444 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1445 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1446 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43413
4 | WIR | SPML-KCM-S-IR-1447 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43414
4 | WIR | SPML-KCM-S-IR-1448 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43414
4 | WIR | SPML-KCM-S-IR-1449 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43482
4 | WIR | SPML-KCM-S-IR-1450 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43414
4 | WIR | SPML-KCM-S-IR-1451 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1452 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1453 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43414
4 | WIR | SPML-KCM-S-IR-1454 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1455 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1456 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1457 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43420
4 | WIR | SPML-KCM-S-IR-1458 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43416
4 | WIR | SPML-KCM-S-IR-1459 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43416
4 | WIR | SPML-KCM-S-IR-1460 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1461 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1462 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1463 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1464 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1465 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1466 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1467 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1468 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1469 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1470 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1471 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1472 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43416
4 | WIR | SPML-KCM-S-IR-1473 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43415
4 | WIR | SPML-KCM-S-IR-1474 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43416
4 | WIR | SPML-KCM-S-IR-1475 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-S-IR-1476 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43416
4 | WIR | SPML-KCM-S-IR-1477 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43416
4 | WIR | SPML-KCM-S-IR-1478 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43416
4 | WIR | SPML-KCM-S-IR-1479 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1480 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1481 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43416
4 | WIR | SPML-KCM-S-IR-1482 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1483 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43420
4 | WIR | SPML-KCM-S-IR-1484 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1485 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1486 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1487 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43416
4 | WIR | SPML-KCM-S-IR-1488 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1489 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43416
4 | WIR | SPML-KCM-S-IR-1490 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43416
4 | WIR | SPML-KCM-S-IR-1491 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1492 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1493 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1494 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1495 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1496 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1497 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1498 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1499 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1500 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1501 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1502 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1503 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1504 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1505 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1506 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1507 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1508 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1509 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1510 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1511 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1512 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1513 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1514 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43417
4 | WIR | SPML-KCM-S-IR-1515 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1516 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1517 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1518 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1519 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1520 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1521 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1522 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1523 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1524 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1525 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1526 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1527 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1528 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1529 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1530 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1531 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1532 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1533 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1534 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1535 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1536 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1537 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1538 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1539 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1540 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1541 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1542 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1543 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44247
4 | WIR | SPML-KCM-S-IR-1544 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1545 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1546 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1547 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1548 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1549 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1550 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-1551 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1552 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1553 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1554 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1555 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1556 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1557 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1558 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1559 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1560 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43627
4 | WIR | SPML-KCM-S-IR-1561 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1562 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43418
4 | WIR | SPML-KCM-S-IR-1563 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1564 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1565 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1566 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1567 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-1568 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1569 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1570 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1571 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1572 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1573 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1574 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1575 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1576 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1577 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1578 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1579 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43482
4 | WIR | SPML-KCM-S-IR-1580 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43419
4 | WIR | SPML-KCM-S-IR-1581 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1582 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1583 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1584 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1585 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1586 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1587 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR-1588 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1589 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1590 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1591 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1592 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1593 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1594 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1595 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1596 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1597 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1598 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1599 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1600 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1601 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1602 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1603 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1604 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1605 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1606 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1607 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-1608 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43627
4 | WIR | SPML-KCM-S-IR-1609 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1610 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1611 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1612 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1613 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1614 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1615 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1616 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1617 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1618 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1619 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1620 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1621 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1622 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1623 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1624 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1625 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43421
4 | WIR | SPML-KCM-S-IR-1626 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-1627 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1628 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1629 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1630 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1631 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1632 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1633 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1634 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1635 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1636 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1637 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1638 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1639 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1640 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1641 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1642 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1643 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1644 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1645 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1646 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43423
4 | WIR | SPML-KCM-S-IR-1647 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43626
4 | WIR | SPML-KCM-S-IR-1648 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-1649 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1650 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-1651 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1652 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43225
4 | WIR | SPML-KCM-S-IR-1653 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1654 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1655 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1656 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1657 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1658 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1659 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43471
4 | WIR | SPML-KCM-S-IR-1660 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1661 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1662 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1663 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1664 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1665 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1666 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43424
4 | WIR | SPML-KCM-S-IR-1667 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1668 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43627
4 | WIR | SPML-KCM-S-IR-1669 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-S-IR-1670 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-S-IR-1671 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1672 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1673 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1674 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1675 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1676 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1677 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1678 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1679 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1680 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1681 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1682 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1683 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1684 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1685 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1686 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1687 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1688 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR-1689 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1690 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1691 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1692 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1693 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1694 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1695 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1696 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1697 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1698 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1699 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1700 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1701 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1702 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43425
4 | WIR | SPML-KCM-S-IR-1703 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1704 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1705 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1706 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1707 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1708 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR-1709 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1710 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1711 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1712 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1713 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1714 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1715 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1716 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1717 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1718 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1719 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1720 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43426
4 | WIR | SPML-KCM-S-IR-1721 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1722 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1723 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1724 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1725 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1726 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1727 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1728 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1729 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43428
4 | WIR | SPML-KCM-S-IR-1730 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1731 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1732 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1733 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1734 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1735 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1736 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1737 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1738 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1739 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1740 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1741 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1742 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1743 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1744 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1745 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1746 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1747 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1748 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1749 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1750 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1751 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1752 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1753 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1754 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1755 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1756 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1757 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1758 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43429
4 | WIR | SPML-KCM-S-IR-1759 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1760 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1761 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1762 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-1763 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1764 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1765 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1766 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1767 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1768 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-1769 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1770 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1771 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1772 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1773 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1774 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1775 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1776 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1777 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1778 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1779 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1780 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1781 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1782 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1783 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1784 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1785 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1786 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1787 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1788 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1789 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1790 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1791 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1792 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43430
4 | WIR | SPML-KCM-S-IR-1793 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43412
4 | WIR | SPML-KCM-S-IR-1794 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1795 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1796 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43402
4 | WIR | SPML-KCM-S-IR-1797 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1798 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1799 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1800 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1801 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1802 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43431
4 | WIR | SPML-KCM-S-IR-1803 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43452
4 | WIR | SPML-KCM-S-IR-1804 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1805 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1806 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1807 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1808 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1809 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1810 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1811 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1812 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1813 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1814 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1815 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR-1816 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1817 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1818 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1819 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1820 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1821 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1822 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1823 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1824 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43432
4 | WIR | SPML-KCM-S-IR-1825 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43439
4 | WIR | SPML-KCM-S-IR-1826 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1827 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1828 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43441
4 | WIR | SPML-KCM-S-IR-1829 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1830 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1831 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43443
4 | WIR | SPML-KCM-S-IR-1832 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1833 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1834 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1835 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1836 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1837 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1838 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1839 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1840 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1841 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1842 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43433
4 | WIR | SPML-KCM-S-IR-1843 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43441
4 | WIR | SPML-KCM-S-IR-1844 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-1845 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43412
4 | WIR | SPML-KCM-S-IR-1846 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR-1847 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1848 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1849 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1850 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1851 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43445
4 | WIR | SPML-KCM-S-IR-1852 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1853 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1854 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43445
4 | WIR | SPML-KCM-S-IR-1855 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1856 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1857 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1858 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1859 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1860 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1861 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1862 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1863 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1864 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1865 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1866 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1867 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1868 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1869 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1870 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1871 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1872 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1873 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1874 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1875 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1876 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1877 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1878 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1879 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR-1880 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1881 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1882 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1883 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1884 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1885 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1886 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1887 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1888 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1889 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1890 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1891 | Building Envelope | Water Proofing | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR-1892 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43486
4 | WIR | SPML-KCM-S-IR-1893 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1894 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1895 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR-1896 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43441
4 | WIR | SPML-KCM-S-IR-1897 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43473
4 | WIR | SPML-KCM-S-IR-1898 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1899 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1900 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1901 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR-1902 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1903 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43437
4 | WIR | SPML-KCM-S-IR-1904 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1905 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1906 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1907 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1908 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1909 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1910 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1911 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43628
4 | WIR | SPML-KCM-S-IR-1912 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1913 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1914 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1915 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1916 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1917 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1918 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1919 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43445
4 | WIR | SPML-KCM-S-IR-1920 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43445
4 | WIR | SPML-KCM-S-IR-1921 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-1922 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43441
4 | WIR | SPML-KCM-S-IR-1923 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43439
4 | WIR | SPML-KCM-S-IR-1924 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43439
4 | WIR | SPML-KCM-S-IR-1925 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-1926 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43439
4 | WIR | SPML-KCM-S-IR-1927 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR-1928 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43439
4 | WIR | SPML-KCM-S-IR-1929 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43439
4 | WIR | SPML-KCM-S-IR-1930 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43439
4 | WIR | SPML-KCM-S-IR-1931 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-1932 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-1933 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43452
4 | WIR | SPML-KCM-S-IR-1934 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43439
4 | WIR | SPML-KCM-S-IR-1935 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43443
4 | WIR | SPML-KCM-S-IR-1936 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-1937 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-S-IR-1938 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43745
4 | WIR | SPML-KCM-S-IR-1939 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1940 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1941 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1942 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1943 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1944 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-1945 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1946 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1947 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-1948 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1949 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1950 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1951 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1952 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1953 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1954 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1955 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1956 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-1957 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-1958 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-1959 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1960 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1961 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1962 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1963 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1964 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1965 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1966 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-1967 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-1968 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-1969 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-1970 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR-1971 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR-1972 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1973 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-1974 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1975 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1976 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1977 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-1978 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1979 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1980 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1981 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43440
4 | WIR | SPML-KCM-S-IR-1982 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1983 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43474
4 | WIR | SPML-KCM-S-IR-1984 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1985 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1986 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1987 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1988 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-1989 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-1990 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1991 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-1992 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-S-IR-1993 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43448
4 | WIR | SPML-KCM-S-IR-1994 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43443
4 | WIR | SPML-KCM-S-IR-1995 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1996 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43442
4 | WIR | SPML-KCM-S-IR-1997 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-1998 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43443
4 | WIR | SPML-KCM-S-IR-1999 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43443
4 | WIR | SPML-KCM-S-IR-2000 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2001 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2002 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2003 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43445
4 | WIR | SPML-KCM-S-IR-2004 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2005 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2006 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2007 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2008 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2009 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2010 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-2011 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-2012 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2013 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2014 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43445
4 | WIR | SPML-KCM-S-IR-2015 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR-2016 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2017 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43445
4 | WIR | SPML-KCM-S-IR-2018 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43445
4 | WIR | SPML-KCM-S-IR-2019 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43445
4 | WIR | SPML-KCM-S-IR-2020 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2021 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2022 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2023 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2024 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2025 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2026 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2027 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2028 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR-2029 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43438
4 | WIR | SPML-KCM-S-IR-2030 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43453
4 | WIR | SPML-KCM-S-IR-2031 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43453
4 | WIR | SPML-KCM-S-IR-2032 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-2033 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43446
4 | WIR | SPML-KCM-S-IR-2034 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43627
4 | WIR | SPML-KCM-S-IR-2035 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-2036 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-2037 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43445
4 | WIR | SPML-KCM-S-IR-2038 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43444
4 | WIR | SPML-KCM-S-IR-2039 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2040 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43455
4 | WIR | SPML-KCM-S-IR-2041 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2042 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2043 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2044 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43505
4 | WIR | SPML-KCM-S-IR-2045 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR-2046 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2047 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2048 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2049 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43447
4 | WIR | SPML-KCM-S-IR-2050 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-2051 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-2052 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43452
4 | WIR | SPML-KCM-S-IR-2053 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43592
4 | WIR | SPML-KCM-S-IR-2054 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-2055 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43449
4 | WIR | SPML-KCM-S-IR-2056 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43454
4 | WIR | SPML-KCM-S-IR-2057 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43457
4 | WIR | SPML-KCM-S-IR-2058 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43454
4 | WIR | SPML-KCM-S-IR-2059 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43454
4 | WIR | SPML-KCM-S-IR-2060 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43454
4 | WIR | SPML-KCM-S-IR-2061 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43454
4 | WIR | SPML-KCM-S-IR-2062 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-2063 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-2064 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-2065 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43450
4 | WIR | SPML-KCM-S-IR-2066 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43453
4 | WIR | SPML-KCM-S-IR-2067 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2068 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43453
4 | WIR | SPML-KCM-S-IR-2069 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-2070 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-2071 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-2072 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43451
4 | WIR | SPML-KCM-S-IR-2073 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43493
4 | WIR | SPML-KCM-S-IR-2074 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43493
4 | WIR | SPML-KCM-S-IR-2075 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43452
4 | WIR | SPML-KCM-S-IR-2076 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43452
4 | WIR | SPML-KCM-S-IR-2077 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43452
4 | WIR | SPML-KCM-S-IR-2078 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43452
4 | WIR | SPML-KCM-S-IR-2079 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43452
4 | WIR | SPML-KCM-S-IR-2080 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43452
4 | WIR | SPML-KCM-S-IR-2081 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43452
4 | WIR | SPML-KCM-S-IR-2082 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43452
4 | WIR | SPML-KCM-S-IR-2083 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43453
4 | WIR | SPML-KCM-S-IR-2084 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-S-IR-2085 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43517
4 | WIR | SPML-KCM-S-IR-2086 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2087 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43453
4 | WIR | SPML-KCM-S-IR-2088 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43453
4 | WIR | SPML-KCM-S-IR-2089 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43453
4 | WIR | SPML-KCM-S-IR-2090 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43453
4 | WIR | SPML-KCM-S-IR-2091 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43453
4 | WIR | SPML-KCM-S-IR-2092 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR-2093 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-S-IR-2094 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43454
4 | WIR | SPML-KCM-S-IR-2095 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43454
4 | WIR | SPML-KCM-S-IR-2096 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43711
4 | WIR | SPML-KCM-S-IR-2097 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43454
4 | WIR | SPML-KCM-S-IR-2098 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43163
4 | WIR | SPML-KCM-S-IR-2099 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2100 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2101 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43460
4 | WIR | SPML-KCM-S-IR-2102 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43454
4 | WIR | SPML-KCM-S-IR-2103 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43456
4 | WIR | SPML-KCM-S-IR-2104 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43474
4 | WIR | SPML-KCM-S-IR-2105 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43456
4 | WIR | SPML-KCM-S-IR-2106 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43752
4 | WIR | SPML-KCM-S-IR-2107 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43753
4 | WIR | SPML-KCM-S-IR-2108 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2109 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43457
4 | WIR | SPML-KCM-S-IR-2110 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43457
4 | WIR | SPML-KCM-S-IR-2111 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43457
4 | WIR | SPML-KCM-S-IR-2112 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43457
4 | WIR | SPML-KCM-S-IR-2113 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43457
4 | WIR | SPML-KCM-S-IR-2114 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43751
4 | WIR | SPML-KCM-S-IR-2115 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-S-IR-2116 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43474
4 | WIR | SPML-KCM-S-IR-2117 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-S-IR-2118 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43456
4 | WIR | SPML-KCM-S-IR-2119 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43461
4 | WIR | SPML-KCM-S-IR-2120 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-S-IR-2121 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43458
4 | WIR | SPML-KCM-S-IR-2122 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43459
4 | WIR | SPML-KCM-S-IR-2123 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43458
4 | WIR | SPML-KCM-S-IR-2124 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43459
4 | WIR | SPML-KCM-S-IR-2125 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43459
4 | WIR | SPML-KCM-S-IR-2126 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-S-IR-2127 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2128 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43465
4 | WIR | SPML-KCM-S-IR-2129 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43471
4 | WIR | SPML-KCM-S-IR-2130 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43459
4 | WIR | SPML-KCM-S-IR-2131 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43459
4 | WIR | SPML-KCM-S-IR-2132 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43493
4 | WIR | SPML-KCM-S-IR-2133 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-2134 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43458
4 | WIR | SPML-KCM-S-IR-2135 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43256
4 | WIR | SPML-KCM-S-IR-2136 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43461
4 | WIR | SPML-KCM-S-IR-2137 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43462
4 | WIR | SPML-KCM-S-IR-2138 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43460
4 | WIR | SPML-KCM-S-IR-2139 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43460
4 | WIR | SPML-KCM-S-IR-2140 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43460
4 | WIR | SPML-KCM-S-IR-2141 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43592
4 | WIR | SPML-KCM-S-IR-2142 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43460
4 | WIR | SPML-KCM-S-IR-2143 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43460
4 | WIR | SPML-KCM-S-IR-2144 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2145 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43460
4 | WIR | SPML-KCM-S-IR-2146 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43460
4 | WIR | SPML-KCM-S-IR-2147 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2148 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43463
4 | WIR | SPML-KCM-S-IR-2149 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43461
4 | WIR | SPML-KCM-S-IR-2150 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43461
4 | WIR | SPML-KCM-S-IR-2151 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43492
4 | WIR | SPML-KCM-S-IR-2152 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43461
4 | WIR | SPML-KCM-S-IR-2153 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43461
4 | WIR | SPML-KCM-S-IR-2154 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43463
4 | WIR | SPML-KCM-S-IR-2155 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43463
4 | WIR | SPML-KCM-S-IR-2156 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43463
4 | WIR | SPML-KCM-S-IR-2157 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43463
4 | WIR | SPML-KCM-S-IR-2158 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43463
4 | WIR | SPML-KCM-S-IR-2159 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43463
4 | WIR | SPML-KCM-S-IR-2160 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43463
4 | WIR | SPML-KCM-S-IR-2161 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43463
4 | WIR | SPML-KCM-S-IR-2162 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43463
4 | WIR | SPML-KCM-S-IR-2163 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2164 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43464
4 | WIR | SPML-KCM-S-IR-2165 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43469
4 | WIR | SPML-KCM-S-IR-2166 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2167 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43464
4 | WIR | SPML-KCM-S-IR-2168 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR-2169 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43464
4 | WIR | SPML-KCM-S-IR-2170 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43464
4 | WIR | SPML-KCM-S-IR-2171 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43464
4 | WIR | SPML-KCM-S-IR-2172 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43464
4 | WIR | SPML-KCM-S-IR-2173 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43465
4 | WIR | SPML-KCM-S-IR-2174 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43464
4 | WIR | SPML-KCM-S-IR-2175 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43493
4 | WIR | SPML-KCM-S-IR-2176 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43465
4 | WIR | SPML-KCM-S-IR-2177 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43467
4 | WIR | SPML-KCM-S-IR-2178 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43467
4 | WIR | SPML-KCM-S-IR-2179 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43464
4 | WIR | SPML-KCM-S-IR-2180 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43467
4 | WIR | SPML-KCM-S-IR-2181 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43467
4 | WIR | SPML-KCM-S-IR-2182 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2183 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2184 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43465
4 | WIR | SPML-KCM-S-IR-2185 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43465
4 | WIR | SPML-KCM-S-IR-2186 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-S-IR-2187 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43468
4 | WIR | SPML-KCM-S-IR-2188 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43468
4 | WIR | SPML-KCM-S-IR-2189 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43468
4 | WIR | SPML-KCM-S-IR-2190 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43468
4 | WIR | SPML-KCM-S-IR-2191 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2192 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2193 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43527
4 | WIR | SPML-KCM-S-IR-2194 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43516
4 | WIR | SPML-KCM-S-IR-2195 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43716
4 | WIR | SPML-KCM-S-IR-2196 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2197 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2198 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2199 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2200 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2201 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2202 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2203 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2204 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43471
4 | WIR | SPML-KCM-S-IR-2205 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2206 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2207 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43716
4 | WIR | SPML-KCM-S-IR-2208 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2209 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43475
4 | WIR | SPML-KCM-S-IR-2210 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-S-IR-2211 | Foundation | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43465
4 | WIR | SPML-KCM-S-IR-2212 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43465
4 | WIR | SPML-KCM-S-IR-2213 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43465
4 | WIR | SPML-KCM-S-IR-2214 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | C | 43471
4 | WIR | SPML-KCM-S-IR-2215 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2216 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2217 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2218 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2219 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2220 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2221 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43471
4 | WIR | SPML-KCM-S-IR-2222 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR-2223 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2224 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2225 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2226 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2227 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2228 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2229 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43470
4 | WIR | SPML-KCM-S-IR-2230 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2231 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2232 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-2233 | Foundation | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-2234 | Concrete Works | Retaining Wall | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-2235 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43465
4 | WIR | SPML-KCM-S-IR-2236 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2237 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2238 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2239 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43473
4 | WIR | SPML-KCM-S-IR-2240 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43473
4 | WIR | SPML-KCM-S-IR-2241 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2242 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2243 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2244 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2245 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2246 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2247 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2248 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR-2249 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43473
4 | WIR | SPML-KCM-S-IR-2250 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44235
4 | WIR | SPML-KCM-S-IR-2251 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43492
4 | WIR | SPML-KCM-S-IR-2252 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43492
4 | WIR | SPML-KCM-S-IR-2253 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43471
4 | WIR | SPML-KCM-S-IR-2254 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43472
4 | WIR | SPML-KCM-S-IR-2255 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43473
4 | WIR | SPML-KCM-S-IR-2256 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR-2257 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2258 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43473
4 | WIR | SPML-KCM-S-IR-2259 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43473
4 | WIR | SPML-KCM-S-IR-2260 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43473
4 | WIR | SPML-KCM-S-IR-2261 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43474
4 | WIR | SPML-KCM-S-IR-2262 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR-2263 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR-2264 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43596
4 | WIR | SPML-KCM-S-IR-2265 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43496
4 | WIR | SPML-KCM-S-IR-2266 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43496
4 | WIR | SPML-KCM-S-IR-2267 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43496
4 | WIR | SPML-KCM-S-IR-2268 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43474
4 | WIR | SPML-KCM-S-IR-2269 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43465
4 | WIR | SPML-KCM-S-IR-2270 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43474
4 | WIR | SPML-KCM-S-IR-2271 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-2272 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43477
4 | WIR | SPML-KCM-S-IR-2288 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR-2289 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR-2290 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR-2291 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR-2292 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR-2293 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR-2294 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2295 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43478
4 | WIR | SPML-KCM-S-IR-2296 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-2302 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43479
4 | WIR | SPML-KCM-S-IR-2303 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR-2304 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR-2305 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR-2306 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43480
4 | WIR | SPML-KCM-S-IR-2307 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-S-IR-2342 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43482
4 | WIR | SPML-KCM-S-IR-2344 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR-2345 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR-2346 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR-2347 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43485
4 | WIR | SPML-KCM-S-IR-2348 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43485
4 | WIR | SPML-KCM-S-IR-2349 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43484
4 | WIR | SPML-KCM-S-IR-2350 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2351 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43591
4 | WIR | SPML-KCM-S-IR-2352 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43485
4 | WIR | SPML-KCM-S-IR-2353 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2354 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43485
4 | WIR | SPML-KCM-S-IR-2355 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43485
4 | WIR | SPML-KCM-S-IR-2356 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43485
4 | WIR | SPML-KCM-S-IR-2382 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43491
4 | WIR | SPML-KCM-S-IR-2383 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-2384 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-2385 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2386 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-2387 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43489
4 | WIR | SPML-KCM-S-IR-2388 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-2389 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-2390 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-2391 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-2392 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-2393 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-2394 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-2395 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43488
4 | WIR | SPML-KCM-S-IR-2396 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43476
4 | WIR | SPML-KCM-S-IR-2429 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43498
4 | WIR | SPML-KCM-S-IR-2430 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2431 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR-2432 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2433 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43494
4 | WIR | SPML-KCM-S-IR-2434 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43498
4 | WIR | SPML-KCM-S-IR-2435 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR-2436 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43495
4 | WIR | SPML-KCM-S-IR-2437 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43495
4 | WIR | SPML-KCM-S-IR-2438 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43495
4 | WIR | SPML-KCM-S-IR-2439 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43496
4 | WIR | SPML-KCM-S-IR-2440 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-2441 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR-2442 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2443 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43496
4 | WIR | SPML-KCM-S-IR-2444 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43496
4 | WIR | SPML-KCM-S-IR-2445 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-S-IR-2446 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2447 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43496
4 | WIR | SPML-KCM-S-IR-2448 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43496
4 | WIR | SPML-KCM-S-IR-2449 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR-2450 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-2451 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43501
4 | WIR | SPML-KCM-S-IR-2453 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43498
4 | WIR | SPML-KCM-S-IR-2454 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43522
4 | WIR | SPML-KCM-S-IR-2458 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43465
4 | WIR | SPML-KCM-S-IR-2459 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-2460 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2461 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43531
4 | WIR | SPML-KCM-S-IR-2462 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43499
4 | WIR | SPML-KCM-S-IR-2463 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43499
4 | WIR | SPML-KCM-S-IR-2464 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43499
4 | WIR | SPML-KCM-S-IR-2465 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43499
4 | WIR | SPML-KCM-S-IR-2466 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2467 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2468 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2469 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43532
4 | WIR | SPML-KCM-S-IR-2470 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43500
4 | WIR | SPML-KCM-S-IR-2471 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-2472 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43516
4 | WIR | SPML-KCM-S-IR-2473 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43500
4 | WIR | SPML-KCM-S-IR-2474 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43500
4 | WIR | SPML-KCM-S-IR-2475 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2476 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43500
4 | WIR | SPML-KCM-S-IR-2477 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-2478 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43500
4 | WIR | SPML-KCM-S-IR-2479 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43500
4 | WIR | SPML-KCM-S-IR-2480 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43500
4 | WIR | SPML-KCM-S-IR-2481 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43500
4 | WIR | SPML-KCM-S-IR-2482 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43502
4 | WIR | SPML-KCM-S-IR-2483 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2484 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-S-IR-2485 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43501
4 | WIR | SPML-KCM-S-IR-2486 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43501
4 | WIR | SPML-KCM-S-IR-2487 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43501
4 | WIR | SPML-KCM-S-IR-2488 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43501
4 | WIR | SPML-KCM-S-IR-2489 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43505
4 | WIR | SPML-KCM-S-IR-2490 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43502
4 | WIR | SPML-KCM-S-IR-2491 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2492 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43505
4 | WIR | SPML-KCM-S-IR-2493 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43522
4 | WIR | SPML-KCM-S-IR-2494 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR-2495 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR-2497 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43502
4 | WIR | SPML-KCM-S-IR-2498 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43502
4 | WIR | SPML-KCM-S-IR-2499 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43502
4 | WIR | SPML-KCM-S-IR-2500 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43533
4 | WIR | SPML-KCM-S-IR-2501 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43516
4 | WIR | SPML-KCM-S-IR-2502 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43502
4 | WIR | SPML-KCM-S-IR-2503 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43508
4 | WIR | SPML-KCM-S-IR-2504 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43502
4 | WIR | SPML-KCM-S-IR-2505 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43502
4 | WIR | SPML-KCM-S-IR-2506 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2507 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43505
4 | WIR | SPML-KCM-S-IR-2508 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43531
4 | WIR | SPML-KCM-S-IR-2509 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR-2510 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-2511 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2512 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43505
4 | WIR | SPML-KCM-S-IR-2513 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43510
4 | WIR | SPML-KCM-S-IR-2514 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43503
4 | WIR | SPML-KCM-S-IR-2515 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR-2516 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-2521 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43505
4 | WIR | SPML-KCM-S-IR-2522 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-S-IR-2523 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-S-IR-2524 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43510
4 | WIR | SPML-KCM-S-IR-2525 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43506
4 | WIR | SPML-KCM-S-IR-2526 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43505
4 | WIR | SPML-KCM-S-IR-2527 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR-2528 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43508
4 | WIR | SPML-KCM-S-IR-2529 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43506
4 | WIR | SPML-KCM-S-IR-2530 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44115
4 | WIR | SPML-KCM-S-IR-2531 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43523
4 | WIR | SPML-KCM-S-IR-2532 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43506
4 | WIR | SPML-KCM-S-IR-2533 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43506
4 | WIR | SPML-KCM-S-IR-2534 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43506
4 | WIR | SPML-KCM-S-IR-2535 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR-2536 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43506
4 | WIR | SPML-KCM-S-IR-2539 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-S-IR-2540 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-S-IR-2541 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43527
4 | WIR | SPML-KCM-S-IR-2542 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43502
4 | WIR | SPML-KCM-S-IR-2543 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43510
4 | WIR | SPML-KCM-S-IR-2544 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR-2545 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-S-IR-2547 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-S-IR-2548 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2549 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-S-IR-2550 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43495
4 | WIR | SPML-KCM-S-IR-2551 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43495
4 | WIR | SPML-KCM-S-IR-2552 | Concrete Works | Core Wall | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-2553 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-2554 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43495
4 | WIR | SPML-KCM-S-IR-2555 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2556 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-2557 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR-2558 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43533
4 | WIR | SPML-KCM-S-IR-2559 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-S-IR-2560 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-S-IR-2561 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-S-IR-2562 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR-2563 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-S-IR-2565 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR-2566 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-S-IR-2567 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43507
4 | WIR | SPML-KCM-S-IR-2568 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR-2569 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR-2570 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43546
4 | WIR | SPML-KCM-S-IR-2571 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR-2572 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43508
4 | WIR | SPML-KCM-S-IR-2573 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR-2574 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR-2575 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43549
4 | WIR | SPML-KCM-S-IR-2576 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43509
4 | WIR | SPML-KCM-S-IR-2577 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43511
4 | WIR | SPML-KCM-S-IR-2578 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43511
4 | WIR | SPML-KCM-S-IR-2579 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2580 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR-2581 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2582 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2621 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR-2622 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2623 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2624 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2625 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2626 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43514
4 | WIR | SPML-KCM-S-IR-2627 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR-2628 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR-2629 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43512
4 | WIR | SPML-KCM-S-IR-2630 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2631 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2632 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2633 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2634 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43514
4 | WIR | SPML-KCM-S-IR-2645 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2646 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2647 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2648 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-2649 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2650 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43513
4 | WIR | SPML-KCM-S-IR-2651 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2652 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43514
4 | WIR | SPML-KCM-S-IR-2653 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43514
4 | WIR | SPML-KCM-S-IR-2654 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43517
4 | WIR | SPML-KCM-S-IR-2655 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43516
4 | WIR | SPML-KCM-S-IR-2656 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-S-IR-2657 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-S-IR-2658 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2659 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43514
4 | WIR | SPML-KCM-S-IR-2660 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2661 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2662 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2663 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43746
4 | WIR | SPML-KCM-S-IR-2664 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43515
4 | WIR | SPML-KCM-S-IR-2668 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43520
4 | WIR | SPML-KCM-S-IR-2669 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43530
4 | WIR | SPML-KCM-S-IR-2670 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43516
4 | WIR | SPML-KCM-S-IR-2749 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43527
4 | WIR | SPML-KCM-S-IR-2750 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-S-IR-2751 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-S-IR-2752 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43524
4 | WIR | SPML-KCM-S-IR-2753 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43526
4 | WIR | SPML-KCM-S-IR-2754 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2755 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43526
4 | WIR | SPML-KCM-S-IR-2756 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR-2757 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR-2758 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43536
4 | WIR | SPML-KCM-S-IR-2759 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43533
4 | WIR | SPML-KCM-S-IR-2760 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43626
4 | WIR | SPML-KCM-S-IR-2761 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44114
4 | WIR | SPML-KCM-S-IR-2762 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43558
4 | WIR | SPML-KCM-S-IR-2786 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR-2787 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR-2788 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR-2789 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR-2790 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43528
4 | WIR | SPML-KCM-S-IR-2791 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43530
4 | WIR | SPML-KCM-S-IR-2792 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43544
4 | WIR | SPML-KCM-S-IR-2803 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 43713
4 | WIR | SPML-KCM-S-IR-3175 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43577
4 | WIR | SPML-KCM-S-IR-3243 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | D | 43583
4 | WIR | SPML-KCM-S-IR-3398 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43755
4 | WIR | SPML-KCM-S-IR-3466 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43618
4 | WIR | SPML-KCM-S-IR-6979 | Finishes | Painting | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44124
4 | WIR | SPML-KCM-S-IR-7071 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44124
4 | WIR | SPML-KCM-S-IR-7114 | Finishes | Epoxy | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44123
4 | WIR | SPML-KCM-S-IR-7115 | Finishes | Epoxy | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44123
4 | WIR | SPML-KCM-S-IR-7116 | Finishes | Epoxy | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44123
4 | WIR | SPML-KCM-S-IR-7118 | Finishes | Epoxy | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-S-IR-7119 | Finishes | Epoxy | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44123
4 | WIR | SPML-KCM-S-IR-7120 | Finishes | Epoxy | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44126
4 | WIR | SPML-KCM-S-IR-7144 | Finishes | Painting | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44124
4 | WIR | SPML-KCM-S-IR-7148 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-S-IR-7152 | Finishes | Louvre | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44160
4 | WIR | SPML-KCM-S-IR-7176 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-7198 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-7215 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7228 | Foundation | Excavation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44143
4 | WIR | SPML-KCM-S-IR-7231 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-S-IR-7232 | Foundation | Soil Compaction | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44158
4 | WIR | SPML-KCM-S-IR-7234 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-S-IR-7235 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44144
4 | WIR | SPML-KCM-S-IR-7237 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44164
4 | WIR | SPML-KCM-S-IR-7239 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44146
4 | WIR | SPML-KCM-S-IR-7240 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-7241 | Expansion | Expansion Joint | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44234
4 | WIR | SPML-KCM-S-IR-7242 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7251 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-S-IR-7252 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-S-IR-7263 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-S-IR-7264 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7265 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7268 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7269 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7271 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7272 | Concrete Works | Column | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7273 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7274 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7275 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7280 | Structural System | Steel Structure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7281 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7282 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7283 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7288 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44150
4 | WIR | SPML-KCM-S-IR-7289 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7290 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7301 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-7322 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7324 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44175
4 | WIR | SPML-KCM-S-IR-7325 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44150
4 | WIR | SPML-KCM-S-IR-7326 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44150
4 | WIR | SPML-KCM-S-IR-7327 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44145
4 | WIR | SPML-KCM-S-IR-7329 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44149
4 | WIR | SPML-KCM-S-IR-7330 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7338 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7339 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7344 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7359 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7363 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7364 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-S-IR-7365 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7366 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-S-IR-7367 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-S-IR-7368 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7376 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7377 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-S-IR-7378 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44153
4 | WIR | SPML-KCM-S-IR-7380 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7381 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7382 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7383 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7384 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7385 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7386 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7388 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7389 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7390 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7392 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7393 | FF&E | Planter Box | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7396 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7398 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-7404 | Foundation | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7405 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7406 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7407 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7408 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7409 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7410 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-7411 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-7412 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-7414 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-7417 | Foundation | Piling | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44154
4 | WIR | SPML-KCM-S-IR-7422 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7423 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-7424 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-7425 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7426 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7427 | Concrete Works | Floor Screed | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7429 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44172
4 | WIR | SPML-KCM-S-IR-7430 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
4 | WIR | SPML-KCM-S-IR-7432 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7433 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7434 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7439 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7440 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7441 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7442 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7443 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44157
4 | WIR | SPML-KCM-S-IR-7444 | FF&E | Totem | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44240
4 | WIR | SPML-KCM-S-IR-7452 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-S-IR-7456 | Concrete Works | Retaining Wall | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-S-IR-7463 | Roofing and Glazing System | Top Hat & Halter | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-S-IR-7464 | Cladding | Facade | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-S-IR-7483 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-S-IR-7488 | Concrete Works | Blinding Concrete | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-S-IR-7495 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44161
4 | WIR | SPML-KCM-S-IR-7517 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44165
4 | WIR | SPML-KCM-S-IR-7575 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-7580 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-7581 | Concrete Works | Post Tensioned Slab | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-7593 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-7594 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-7595 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-7600 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-7601 | Concrete Works | Shuttering | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44191
4 | WIR | SPML-KCM-S-IR-7618 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR-7619 | Concrete Works | Surface Preparation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR-7626 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44192
4 | WIR | SPML-KCM-S-IR-7628 | NCR & Exception | NCR Closure | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-S-IR-7659 | Lift System | Elevator | Al Forsan Central Mall | NA | Mechanical | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-S-IR-7663 | Space Protection System | Bollards | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-S-IR-7664 | Concrete Works | Reinforcement | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44193
4 | WIR | SPML-KCM-SPID-IR-5000 | Finishes | Colum Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43166
4 | WIR | SPML-KCM-SPID-IR-5001 | Finishes | Colum Cladding | Al Forsan Central Mall | NA | Architectural | NULL | Global Admin | D | 43166
4 | WIR | SPML-KCM-ST-IR-0000 | Foundation | Excavation | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 43134
4 | WIR | SPML-KCM-ST-IR-0001 | Concrete Works | Water Proofing | Al Forsan Central Mall | NA | Structural | NULL | Global Admin | A | 44156
5 | TS | SPML-KCM-CA-MSS-0014 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43135
5 | TS | SPML-KCM-CA-MSS-0016 | Foundation | Excavation | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43117
5 | TS | SPML-KCM-CA-MSS-0019 | Foundation | Shuttering | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43155
5 | TS | SPML-KCM-CA-MSS-0045 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43297
5 | TS | SPML-KCM-CA-MSS-0046 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | C | 43320
5 | TS | SPML-KCM-CA-MSS-0046 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43353
5 | TS | SPML-KCM-CA-MSS-0052 | Walls | Block Work | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43486
5 | TS | SPML-KCM-CA-MSS-0055 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43223
5 | TS | SPML-KCM-CA-OM-001 | Car Park | Car Park Shade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43885
5 | TS | SPML-KCM-CA-OM-002 | Lift System | Escalators | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44157
5 | TS | SPML-KCM-CA-OM-003 | Lift System | Elevator | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44157
5 | TS | SPML-KCM-CA-OM-004 | Finishes | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-CA-OM-005 | Doors & Windows | Roller Shutter | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44224
5 | TS | SPML-KCM-CA-OM-006 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44130
5 | TS | SPML-KCM-CA-OM-007 | Waste Management | Garbage Compactor | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44153
5 | TS | SPML-KCM-CA-OM-008 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44195
5 | TS | SPML-KCM-CA-OM-009 | Loading Bay Equipment System | Dock Leveller | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44195
5 | TS | SPML-KCM-CA-OM-010 | Doors & Windows | Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44195
5 | TS | SPML-KCM-CA-OM-011 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44156
5 | TS | SPML-KCM-CA-OM-012 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
5 | TS | SPML-KCM-CA-OM-013 | ELV | CPMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44153
5 | TS | SPML-KCM-CA-OM-015 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-CA-OM-017 | Doors & Windows | Wooden Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
5 | TS | SPML-KCM-CA-OM-018 | Doors & Windows | Sliding Door | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44192
5 | TS | SPML-KCM-CA-OM-019 | Finishes | Carpet | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-CA-OM-020 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
5 | TS | SPML-KCM-CA-OM-021 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44185
5 | TS | SPML-KCM-CA-OM-022 | Cladding | Column Cladding | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44186
5 | TS | SPML-KCM-CA-OM-023 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44189
5 | TS | SPML-KCM-CA-OM-024 | Finishes | Baffle Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44193
5 | TS | SPML-KCM-CA-OM-025 | Finishes | Stone Carpet | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44194
5 | TS | SPML-KCM-CA-OM-026 | Finishes | Mirror | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44194
5 | TS | SPML-KCM-CA-OM-027 | Finishes | Aqua Panel | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44196
5 | TS | SPML-KCM-CA-OM-028 | Finishes | FOH Light | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-OM-029 | Doors & Windows | Steel Doors | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44200
5 | TS | SPML-KCM-CA-OM-030 | FF&E | Planter Box | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44212
5 | TS | SPML-KCM-CA-PQ-0008 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43177
5 | TS | SPML-KCM-CA-PQ-0011 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44090
5 | TS | SPML-KCM-CA-PQ-0054 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43197
5 | TS | SPML-KCM-CA-PQ-0059 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43197
5 | TS | SPML-KCM-CA-PQ-0068 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43213
5 | TS | SPML-KCM-CA-PQ-0086 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43243
5 | TS | SPML-KCM-CA-PQ-0094 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43282
5 | TS | SPML-KCM-CA-PQ-0111 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43281
5 | TS | SPML-KCM-CA-PQ-0116 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43284
5 | TS | SPML-KCM-CA-PQ-0117 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43284
5 | TS | SPML-KCM-CA-PQ-0118 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43293
5 | TS | SPML-KCM-CA-PQ-0124 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43289
5 | TS | SPML-KCM-CA-PQ-0125 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43289
5 | TS | SPML-KCM-CA-PQ-0126 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43335
5 | TS | SPML-KCM-CA-PQ-0135 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43298
5 | TS | SPML-KCM-CA-PQ-0137 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43302
5 | TS | SPML-KCM-CA-PQ-0143 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43311
5 | TS | SPML-KCM-CA-PQ-0144 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43311
5 | TS | SPML-KCM-CA-PQ-0146 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43313
5 | TS | SPML-KCM-CA-PQ-0148 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43316
5 | TS | SPML-KCM-CA-PQ-0153 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43331
5 | TS | SPML-KCM-CA-PQ-0154 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43320
5 | TS | SPML-KCM-CA-PQ-0165 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43328
5 | TS | SPML-KCM-CA-PQ-0180 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0181 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43341
5 | TS | SPML-KCM-CA-PQ-0184 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43341
5 | TS | SPML-KCM-CA-PQ-0186 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0192 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44233
5 | TS | SPML-KCM-CA-PQ-0194 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43353
5 | TS | SPML-KCM-CA-PQ-0197 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43355
5 | TS | SPML-KCM-CA-PQ-0203 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43358
5 | TS | SPML-KCM-CA-PQ-0207 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43361
5 | TS | SPML-KCM-CA-PQ-0220 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43373
5 | TS | SPML-KCM-CA-PQ-0223 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44233
5 | TS | SPML-KCM-CA-PQ-0243 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43388
5 | TS | SPML-KCM-CA-PQ-0247 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43391
5 | TS | SPML-KCM-CA-PQ-0248 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43391
5 | TS | SPML-KCM-CA-PQ-0256 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44122
5 | TS | SPML-KCM-CA-PQ-0340 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43397
5 | TS | SPML-KCM-CA-PQ-0347 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43447
5 | TS | SPML-KCM-CA-PQ-0348 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43449
5 | TS | SPML-KCM-CA-PQ-0349 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0352 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43451
5 | TS | SPML-KCM-CA-PQ-0365 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43464
5 | TS | SPML-KCM-CA-PQ-0366 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43457
5 | TS | SPML-KCM-CA-PQ-0367 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43458
5 | TS | SPML-KCM-CA-PQ-0374 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43460
5 | TS | SPML-KCM-CA-PQ-0381 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43464
5 | TS | SPML-KCM-CA-PQ-0385 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43465
5 | TS | SPML-KCM-CA-PQ-0390 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43468
5 | TS | SPML-KCM-CA-PQ-0401 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43477
5 | TS | SPML-KCM-CA-PQ-0418 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43484
5 | TS | SPML-KCM-CA-PQ-0422 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0428 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43489
5 | TS | SPML-KCM-CA-PQ-0433 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43492
5 | TS | SPML-KCM-CA-PQ-0439 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43494
5 | TS | SPML-KCM-CA-PQ-0440 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43494
5 | TS | SPML-KCM-CA-PQ-0441 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43494
5 | TS | SPML-KCM-CA-PQ-0451 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44145
5 | TS | SPML-KCM-CA-PQ-0457 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43502
5 | TS | SPML-KCM-CA-PQ-0474 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44126
5 | TS | SPML-KCM-CA-PQ-0475 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43523
5 | TS | SPML-KCM-CA-PQ-0478 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0480 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0486 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0493 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0494 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0497 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0499 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43534
5 | TS | SPML-KCM-CA-PQ-0544 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43540
5 | TS | SPML-KCM-CA-PQ-0546 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0550 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0572 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0575 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44142
5 | TS | SPML-KCM-CA-PQ-0582 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0617 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0639 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43589
5 | TS | SPML-KCM-CA-PQ-0641 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43582
5 | TS | SPML-KCM-CA-PQ-0643 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43585
5 | TS | SPML-KCM-CA-PQ-0644 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43585
5 | TS | SPML-KCM-CA-PQ-0658 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44174
5 | TS | SPML-KCM-CA-PQ-0665 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43599
5 | TS | SPML-KCM-CA-PQ-0668 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43615
5 | TS | SPML-KCM-CA-PQ-0671 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43603
5 | TS | SPML-KCM-CA-PQ-0700 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43624
5 | TS | SPML-KCM-CA-PQ-0701 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43624
5 | TS | SPML-KCM-CA-PQ-0707 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0720 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43635
5 | TS | SPML-KCM-CA-PQ-0744 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43649
5 | TS | SPML-KCM-CA-PQ-0745 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43648
5 | TS | SPML-KCM-CA-PQ-0752 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43654
5 | TS | SPML-KCM-CA-PQ-0753 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43654
5 | TS | SPML-KCM-CA-PQ-0754 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43631
5 | TS | SPML-KCM-CA-PQ-0766 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43694
5 | TS | SPML-KCM-CA-PQ-0781 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43674
5 | TS | SPML-KCM-CA-PQ-0782 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43682
5 | TS | SPML-KCM-CA-PQ-0793 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43680
5 | TS | SPML-KCM-CA-PQ-0810 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43694
5 | TS | SPML-KCM-CA-PQ-0819 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43701
5 | TS | SPML-KCM-CA-PQ-0838 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43725
5 | TS | SPML-KCM-CA-PQ-0862 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43740
5 | TS | SPML-KCM-CA-PQ-0885 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43754
5 | TS | SPML-KCM-CA-PQ-0918 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-CA-PQ-0926 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43789
5 | TS | SPML-KCM-CA-PQ-0932 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43796
5 | TS | SPML-KCM-CA-PQ-0940 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43806
5 | TS | SPML-KCM-CA-PQ-0941 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43806
5 | TS | SPML-KCM-CA-PQ-0942 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43806
5 | TS | SPML-KCM-CA-PQ-0997 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43904
5 | TS | SPML-KCM-CA-PQ-1049 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44004
5 | TS | SPML-KCM-CA-PQ-1068 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44055
5 | TS | SPML-KCM-CA-PQ-1147 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44163
5 | TS | SPML-KCM-CA-PQ-1161 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44202
5 | TS | SPML-KCM-CA-PQ-1162 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44202
5 | TS | SPML-KCM-CA-PQ-1163 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44202
5 | TS | SPML-KCM-CA-PQ-1177 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44233
5 | TS | SPML-KCM-CA-PQ-1180 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44233
5 | TS | SPML-KCM-CA-TR-003 | Foundation | Excavation | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43093
5 | TS | SPML-KCM-CA-TR-0043 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43167
5 | TS | SPML-KCM-CA-TR-0051 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43178
5 | TS | SPML-KCM-CA-TR-0053 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43185
5 | TS | SPML-KCM-CA-TR-0057 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43190
5 | TS | SPML-KCM-CA-TR-0058 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43194
5 | TS | SPML-KCM-CA-TR-0061 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43202
5 | TS | SPML-KCM-CA-TR-0062 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44234
5 | TS | SPML-KCM-CA-TR-0063 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43206
5 | TS | SPML-KCM-CA-TR-0066 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43213
5 | TS | SPML-KCM-CA-TR-0067 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43213
5 | TS | SPML-KCM-CA-TR-0069 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43215
5 | TS | SPML-KCM-CA-TR-0071 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43216
5 | TS | SPML-KCM-CA-TR-0076 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43222
5 | TS | SPML-KCM-CA-TR-0077 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43225
5 | TS | SPML-KCM-CA-TR-0078 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43226
5 | TS | SPML-KCM-CA-TR-0079 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43226
5 | TS | SPML-KCM-CA-TR-0080 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43234
5 | TS | SPML-KCM-CA-TR-0082 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43235
5 | TS | SPML-KCM-CA-TR-0083 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43235
5 | TS | SPML-KCM-CA-TR-0084 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43241
5 | TS | SPML-KCM-CA-TR-0088 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43248
5 | TS | SPML-KCM-CA-TR-0089 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43248
5 | TS | SPML-KCM-CA-TR-0091 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43250
5 | TS | SPML-KCM-CA-TR-0095 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43258
5 | TS | SPML-KCM-CA-TR-0096 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43258
5 | TS | SPML-KCM-CA-TR-0102 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43274
5 | TS | SPML-KCM-CA-TR-0103 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43274
5 | TS | SPML-KCM-CA-TR-0106 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43281
5 | TS | SPML-KCM-CA-TR-0119 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43285
5 | TS | SPML-KCM-CA-TR-0127 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43295
5 | TS | SPML-KCM-CA-TR-0128 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43295
5 | TS | SPML-KCM-CA-TR-0133 | Foundation | Excavation | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0134 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43304
5 | TS | SPML-KCM-CA-TR-0138 | Foundation | Soil Compaction | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43304
5 | TS | SPML-KCM-CA-TR-0140 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43309
5 | TS | SPML-KCM-CA-TR-0145 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43311
5 | TS | SPML-KCM-CA-TR-0151 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43319
5 | TS | SPML-KCM-CA-TR-0155 | Foundation | Soil Compaction | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43320
5 | TS | SPML-KCM-CA-TR-0156 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43300
5 | TS | SPML-KCM-CA-TR-0157 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43325
5 | TS | SPML-KCM-CA-TR-0159 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43325
5 | TS | SPML-KCM-CA-TR-0160 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43325
5 | TS | SPML-KCM-CA-TR-0169 | Foundation | Soil Compaction | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43335
5 | TS | SPML-KCM-CA-TR-0170 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43335
5 | TS | SPML-KCM-CA-TR-0172 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43335
5 | TS | SPML-KCM-CA-TR-0173 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43335
5 | TS | SPML-KCM-CA-TR-0175 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43337
5 | TS | SPML-KCM-CA-TR-0176 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43337
5 | TS | SPML-KCM-CA-TR-0179 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43348
5 | TS | SPML-KCM-CA-TR-0182 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43341
5 | TS | SPML-KCM-CA-TR-0183 | Foundation | Soil Compaction | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43342
5 | TS | SPML-KCM-CA-TR-0189 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43348
5 | TS | SPML-KCM-CA-TR-0190 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43348
5 | TS | SPML-KCM-CA-TR-0193 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43352
5 | TS | SPML-KCM-CA-TR-0196 | Foundation | Soil Compaction | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43358
5 | TS | SPML-KCM-CA-TR-0205 | Foundation | Soil Compaction | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43359
5 | TS | SPML-KCM-CA-TR-0210 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43366
5 | TS | SPML-KCM-CA-TR-0211 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43366
5 | TS | SPML-KCM-CA-TR-0212 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43366
5 | TS | SPML-KCM-CA-TR-0213 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43366
5 | TS | SPML-KCM-CA-TR-0214 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43368
5 | TS | SPML-KCM-CA-TR-0215 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43368
5 | TS | SPML-KCM-CA-TR-0216 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43368
5 | TS | SPML-KCM-CA-TR-0217 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43368
5 | TS | SPML-KCM-CA-TR-0230 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43381
5 | TS | SPML-KCM-CA-TR-0231 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43381
5 | TS | SPML-KCM-CA-TR-0232 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43382
5 | TS | SPML-KCM-CA-TR-0233 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43381
5 | TS | SPML-KCM-CA-TR-0234 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43381
5 | TS | SPML-KCM-CA-TR-0235 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43381
5 | TS | SPML-KCM-CA-TR-0236 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43382
5 | TS | SPML-KCM-CA-TR-0237 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43382
5 | TS | SPML-KCM-CA-TR-0238 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43382
5 | TS | SPML-KCM-CA-TR-0241 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43386
5 | TS | SPML-KCM-CA-TR-0242 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43386
5 | TS | SPML-KCM-CA-TR-0257 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43398
5 | TS | SPML-KCM-CA-TR-0258 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43398
5 | TS | SPML-KCM-CA-TR-0259 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43398
5 | TS | SPML-KCM-CA-TR-0260 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43407
5 | TS | SPML-KCM-CA-TR-0261 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43398
5 | TS | SPML-KCM-CA-TR-0262 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43398
5 | TS | SPML-KCM-CA-TR-0263 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43398
5 | TS | SPML-KCM-CA-TR-0266 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43400
5 | TS | SPML-KCM-CA-TR-0267 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43400
5 | TS | SPML-KCM-CA-TR-0268 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43400
5 | TS | SPML-KCM-CA-TR-0269 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43400
5 | TS | SPML-KCM-CA-TR-0273 | Foundation | Soil Compaction | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43408
5 | TS | SPML-KCM-CA-TR-0276 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43410
5 | TS | SPML-KCM-CA-TR-0277 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43410
5 | TS | SPML-KCM-CA-TR-0278 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43410
5 | TS | SPML-KCM-CA-TR-0291 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43416
5 | TS | SPML-KCM-CA-TR-0293 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43418
5 | TS | SPML-KCM-CA-TR-0294 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43418
5 | TS | SPML-KCM-CA-TR-0295 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43418
5 | TS | SPML-KCM-CA-TR-0301 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43424
5 | TS | SPML-KCM-CA-TR-0302 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43424
5 | TS | SPML-KCM-CA-TR-0303 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43440
5 | TS | SPML-KCM-CA-TR-0304 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43424
5 | TS | SPML-KCM-CA-TR-0313 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43431
5 | TS | SPML-KCM-CA-TR-0314 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43431
5 | TS | SPML-KCM-CA-TR-0315 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43431
5 | TS | SPML-KCM-CA-TR-0316 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43431
5 | TS | SPML-KCM-CA-TR-0317 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43431
5 | TS | SPML-KCM-CA-TR-0318 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43431
5 | TS | SPML-KCM-CA-TR-0319 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43431
5 | TS | SPML-KCM-CA-TR-0320 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43431
5 | TS | SPML-KCM-CA-TR-0321 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43431
5 | TS | SPML-KCM-CA-TR-0322 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43431
5 | TS | SPML-KCM-CA-TR-0323 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43431
5 | TS | SPML-KCM-CA-TR-0326 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43457
5 | TS | SPML-KCM-CA-TR-0328 | Concrete Works | Reinforcement | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43435
5 | TS | SPML-KCM-CA-TR-0329 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43437
5 | TS | SPML-KCM-CA-TR-0330 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43437
5 | TS | SPML-KCM-CA-TR-0331 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43437
5 | TS | SPML-KCM-CA-TR-0332 | Foundation | Excavation | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43437
5 | TS | SPML-KCM-CA-TR-0333 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43437
5 | TS | SPML-KCM-CA-TR-0334 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43437
5 | TS | SPML-KCM-CA-TR-0335 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43437
5 | TS | SPML-KCM-CA-TR-0346 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43447
5 | TS | SPML-KCM-CA-TR-0353 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43451
5 | TS | SPML-KCM-CA-TR-0355 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0356 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0358 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43453
5 | TS | SPML-KCM-CA-TR-0363 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43454
5 | TS | SPML-KCM-CA-TR-0368 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43458
5 | TS | SPML-KCM-CA-TR-0372 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43460
5 | TS | SPML-KCM-CA-TR-0373 | Foundation | Piling | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43460
5 | TS | SPML-KCM-CA-TR-0402 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43481
5 | TS | SPML-KCM-CA-TR-0453 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43498
5 | TS | SPML-KCM-CA-TR-0498 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0536 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43536
5 | TS | SPML-KCM-CA-TR-0563 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43545
5 | TS | SPML-KCM-CA-TR-0567 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43545
5 | TS | SPML-KCM-CA-TR-0570 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43548
5 | TS | SPML-KCM-CA-TR-0579 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43552
5 | TS | SPML-KCM-CA-TR-0580 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43552
5 | TS | SPML-KCM-CA-TR-0581 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43554
5 | TS | SPML-KCM-CA-TR-0627 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43575
5 | TS | SPML-KCM-CA-TR-0628 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43575
5 | TS | SPML-KCM-CA-TR-0629 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43575
5 | TS | SPML-KCM-CA-TR-0630 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43575
5 | TS | SPML-KCM-CA-TR-0679 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43605
5 | TS | SPML-KCM-CA-TR-0680 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43605
5 | TS | SPML-KCM-CA-TR-0681 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43605
5 | TS | SPML-KCM-CA-TR-0710 | GRP System | GRP Lining | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43638
5 | TS | SPML-KCM-CA-TR-0712 | Foundation | Excavation | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0721 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43635
5 | TS | SPML-KCM-CA-TR-0726 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43639
5 | TS | SPML-KCM-CA-TR-0770 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43662
5 | TS | SPML-KCM-CA-TR-0790 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43678
5 | TS | SPML-KCM-CA-TR-0791 | Finishes | Standing Seem | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43703
5 | TS | SPML-KCM-CA-TR-0792 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0794 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43680
5 | TS | SPML-KCM-CA-TR-0800 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43684
5 | TS | SPML-KCM-CA-TR-0801 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43684
5 | TS | SPML-KCM-CA-TR-0805 | Finishes | Standing Seem | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43689
5 | TS | SPML-KCM-CA-TR-0806 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43689
5 | TS | SPML-KCM-CA-TR-0837 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43719
5 | TS | SPML-KCM-CA-TR-0846 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43723
5 | TS | SPML-KCM-CA-TR-0851 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0852 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | B | 43727
5 | TS | SPML-KCM-CA-TR-0858 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43736
5 | TS | SPML-KCM-CA-TR-0859 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43736
5 | TS | SPML-KCM-CA-TR-0871 | GRP System | GRP Lining | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43747
5 | TS | SPML-KCM-CA-TR-0872 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43747
5 | TS | SPML-KCM-CA-TR-0887 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0888 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0889 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0935 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43799
5 | TS | SPML-KCM-CA-TR-0936 | Finishes | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0946 | Finishes | Aluminium profile | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-0955 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43822
5 | TS | SPML-KCM-CA-TR-0957 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43823
5 | TS | SPML-KCM-CA-TR-0984 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43907
5 | TS | SPML-KCM-CA-TR-1001 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43935
5 | TS | SPML-KCM-CA-TR-1002 | Finishes | Gypsum Ceiling | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43911
5 | TS | SPML-KCM-CA-TR-1003 | Finishes | Epoxy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43908
5 | TS | SPML-KCM-CA-TR-1005 | Rainwater Management System | Gutter System | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43939
5 | TS | SPML-KCM-CA-TR-1006 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43912
5 | TS | SPML-KCM-CA-TR-1007 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43912
5 | TS | SPML-KCM-CA-TR-1008 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43912
5 | TS | SPML-KCM-CA-TR-1011 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43918
5 | TS | SPML-KCM-CA-TR-1012 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43918
5 | TS | SPML-KCM-CA-TR-1013 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43918
5 | TS | SPML-KCM-CA-TR-1014 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43918
5 | TS | SPML-KCM-CA-TR-1022 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-1025 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43956
5 | TS | SPML-KCM-CA-TR-1026 | Structural System | Steel Structure | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-1033 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43960
5 | TS | SPML-KCM-CA-TR-1053 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44020
5 | TS | SPML-KCM-CA-TR-1054 | Finishes | Epoxy | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44020
5 | TS | SPML-KCM-CA-TR-1055 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44020
5 | TS | SPML-KCM-CA-TR-1056 | Concrete Works | Binding Concrete | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44020
5 | TS | SPML-KCM-CA-TR-1057 | Finishes | Painting | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44020
5 | TS | SPML-KCM-CA-TR-1070 | Space Protection System | Bollards | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-1073 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44058
5 | TS | SPML-KCM-CA-TR-1081 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-1086 | Finishes | Wall Tiles | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44199
5 | TS | SPML-KCM-CA-TR-1099 | Signages | Wayfinding Signages | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44089
5 | TS | SPML-KCM-CA-TR-1101 | Concrete Works | Water Proofing | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44090
5 | TS | SPML-KCM-CA-TR-1107 | Building Envelope | Water Proofing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44103
5 | TS | SPML-KCM-CA-TR-1115 | Finishes | Glazing | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44111
5 | TS | SPML-KCM-CA-TR-1120 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44123
5 | TS | SPML-KCM-CA-TR-1170 | Roofing and Glazing System | Skylight | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44210
5 | TS | SPML-KCM-CA-TR-1182 | Code Upgrade | Code Upgrade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44233
5 | TS | SPML-KCM-CA-TR-1183 | Code Upgrade | Code Upgrade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44233
5 | TS | SPML-KCM-CA-TR-1184 | Code Upgrade | Code Upgrade | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44233
5 | TS | SPML-KCM-ID-PQ-0596 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44233
5 | TS | SPML-KCM-ID-PQ-0598 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44126
5 | TS | SPML-KCM-ID-PQ-0602 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-ID-PQ-0626 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-ID-PQ-0632 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-ID-PQ-0634 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 44202
5 | TS | SPML-KCM-ID-PQ-0647 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43585
5 | TS | SPML-KCM-ID-PQ-0661 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | A | 43597
5 | TS | SPML-KCM-MEP-OM-EL-001 | ELV | Public Address System | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44173
5 | TS | SPML-KCM-MEP-OM-EL-003 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-EL-004 | ELV | Disabled Toilet Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-OM-EL-007 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-OM-EL-010 | HV System | Transformer | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-OM-EL-014 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-OM-EL-017 | Lighting | Light Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44154
5 | TS | SPML-KCM-MEP-OM-EL-020 | HV System | RMU | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44171
5 | TS | SPML-KCM-MEP-OM-EL-033 | Power Distribution | UPS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44132
5 | TS | SPML-KCM-MEP-OM-EL-036 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-EL-045 | Power Distribution | Containment | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44143
5 | TS | SPML-KCM-MEP-OM-EL-047 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-OM-EL-048 | ELV | Access Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44171
5 | TS | SPML-KCM-MEP-OM-EL-049 | ELV | Access Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-OM-EL-050 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44171
5 | TS | SPML-KCM-MEP-OM-EL-052 | Power Distribution | Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44143
5 | TS | SPML-KCM-MEP-OM-EL-053 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44149
5 | TS | SPML-KCM-MEP-OM-EL-054 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44186
5 | TS | SPML-KCM-MEP-OM-EL-055 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44179
5 | TS | SPML-KCM-MEP-OM-EL-058 | HV System | Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44185
5 | TS | SPML-KCM-MEP-OM-EL-059 | Earthing & Lightning Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44187
5 | TS | SPML-KCM-MEP-OM-FFG-002 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-FFG-005 | Fire Fighting System | Clean Agent | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-OM-FFG-006 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-OM-FFG-008 | Fire Fighting System | Water Deluge system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-OM-FFG-009 | Fire Fighting System | Foam Deluge system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-OM-HVAC-013 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-HVAC-016 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-HVAC-018 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-HVAC-019 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-HVAC-021 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-HVAC-022 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-OM-HVAC-023 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-HVAC-024 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44151
5 | TS | SPML-KCM-MEP-OM-HVAC-025 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-HVAC-026 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-HVAC-027 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-HVAC-028 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-HVAC-029 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44192
5 | TS | SPML-KCM-MEP-OM-HVAC-030 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-HVAC-032 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-HVAC-034 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44192
5 | TS | SPML-KCM-MEP-OM-HVAC-035 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44192
5 | TS | SPML-KCM-MEP-OM-HVAC-043 | HVAC | Leak Detection | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-HVAC-044 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44192
5 | TS | SPML-KCM-MEP-OM-HVAC-046 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44192
5 | TS | SPML-KCM-MEP-OM-HVAC-051 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-HVAC-056 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-HVAC-057 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-PL-011 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-PL-012 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44179
5 | TS | SPML-KCM-MEP-OM-PL-015 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-PL-031 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-OM-PL-037 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-PL-038 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44151
5 | TS | SPML-KCM-MEP-OM-PL-039 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44151
5 | TS | SPML-KCM-MEP-OM-PL-040 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-OM-PL-041 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44140
5 | TS | SPML-KCM-MEP-OM-PL-042 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44140
5 | TS | SPML-KCM-MEP-PQ-0001 | NULL | NULL | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43220
5 | TS | SPML-KCM-MEP-PQ-0002 | NULL | NULL | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | D | 43220
5 | TS | SPML-KCM-MEP-PQ-0003 | NULL | NULL | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44174
5 | TS | SPML-KCM-MEP-PQ-0153 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44114
5 | TS | SPML-KCM-MEP-PQ-0259 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44114
5 | TS | SPML-KCM-MEP-PQ-0260 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44114
5 | TS | SPML-KCM-MEP-PQ-0262 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44114
5 | TS | SPML-KCM-MEP-PQ-0286 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44114
5 | TS | SPML-KCM-MEP-PQ-EL-0026 | NULL | NULL | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-PQ-EL-0029 | NULL | NULL | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44174
5 | TS | SPML-KCM-MEP-PQ-EL-0046 | NULL | NULL | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-PQ-EL-0050 | NULL | NULL | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44147
5 | TS | SPML-KCM-MEP-PQ-EL-0106 | NULL | NULL | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44161
5 | TS | SPML-KCM-MEP-PQ-EL-0121 | NULL | NULL | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-PQ-EL-0182 | NULL | NULL | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44147
5 | TS | SPML-KCM-MEP-PQ-EL-0330 | NULL | NULL | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44131
5 | TS | SPML-KCM-MEP-PQ-HVAC-0220 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44114
5 | TS | SPML-KCM-MEP-PQ-HVAC-0251 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44114
5 | TS | SPML-KCM-MEP-PQ-HVAC-0388 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44189
5 | TS | SPML-KCM-MEP-PQ-ME-0059 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | D | 43338
5 | TS | SPML-KCM-MEP-PQ-ME-0095 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44114
5 | TS | SPML-KCM-MEP-PQ-ME-0099 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44114
5 | TS | SPML-KCM-MEP-PQ-PL-0125 | NULL | NULL | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44114
5 | TS | SPML-KCM-MEP-TR--0380 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | E | 44138
5 | TS | SPML-KCM-MEP-TR-0010 | Registers | Registers | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | B | 43355
5 | TS | SPML-KCM-MEP-TR-0011 | Registers | Registers | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | B | 43355
5 | TS | SPML-KCM-MEP-TR-0012 | Registers | Registers | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | B | 43335
5 | TS | SPML-KCM-MEP-TR-0013 | Registers | Registers | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | B | 43335
5 | TS | SPML-KCM-MEP-TR-0021 | Registers | Registers | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 43457
5 | TS | SPML-KCM-MEP-TR-0027 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43326
5 | TS | SPML-KCM-MEP-TR-0104 | General | General | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | B | 43380
5 | TS | SPML-KCM-MEP-TR-0139 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0140 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44181
5 | TS | SPML-KCM-MEP-TR-0143 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44181
5 | TS | SPML-KCM-MEP-TR-0148 | General | General | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | E | 43410
5 | TS | SPML-KCM-MEP-TR-0149 | General | General | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | E | 43410
5 | TS | SPML-KCM-MEP-TR-0156 | Power Distribution | Isolators | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0160 | Lighting | Light Fixtures | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0162 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44181
5 | TS | SPML-KCM-MEP-TR-0169 | Lighting | Lighting Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0170 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0179 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44179
5 | TS | SPML-KCM-MEP-TR-0180 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44179
5 | TS | SPML-KCM-MEP-TR-0183 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0195 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0197 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44179
5 | TS | SPML-KCM-MEP-TR-0207 | HVAC | Leak Detection | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | C | 44182
5 | TS | SPML-KCM-MEP-TR-0208 | Miscellaneous | Miscellaneous | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44174
5 | TS | SPML-KCM-MEP-TR-0209 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0215 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0219 | Power Distribution | GA Drawing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44164
5 | TS | SPML-KCM-MEP-TR-0221 | ELV | Access Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0225 | Emergency Lighting | CBS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0227 | Power Distribution | GA Drawing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44174
5 | TS | SPML-KCM-MEP-TR-0229 | ADM | ADM | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | E | 43494
5 | TS | SPML-KCM-MEP-TR-0231 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0237 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0240 | Procurement | Long Lead | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44174
5 | TS | SPML-KCM-MEP-TR-0242 | Miscellaneous | Miscellaneous | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44184
5 | TS | SPML-KCM-MEP-TR-0243 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44184
5 | TS | SPML-KCM-MEP-TR-0244 | Power Distribution | GA Drawing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0245 | HV System | Transformer | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0247 | Sealant | Fire Sealant | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0249 | Power Distribution | ADCD | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44181
5 | TS | SPML-KCM-MEP-TR-0250 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0252 | ADM | ADM | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44189
5 | TS | SPML-KCM-MEP-TR-0255 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0256 | Procurement | Long Lead | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44184
5 | TS | SPML-KCM-MEP-TR-0258 | Power Distribution | ADDC | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44179
5 | TS | SPML-KCM-MEP-TR-0261 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44186
5 | TS | SPML-KCM-MEP-TR-0263 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0265 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0267 | Power Distribution | GA Drawing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0268 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44179
5 | TS | SPML-KCM-MEP-TR-0273 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0275 | Lighting | Lighting Fixture | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0276 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44181
5 | TS | SPML-KCM-MEP-TR-0277 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0278 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-TR-0281 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-TR-0282 | Power Distribution | SLD | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0284 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0285 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44179
5 | TS | SPML-KCM-MEP-TR-0288 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0290 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44179
5 | TS | SPML-KCM-MEP-TR-0292 | Lighting | Light Fixtures | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44164
5 | TS | SPML-KCM-MEP-TR-0295 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44164
5 | TS | SPML-KCM-MEP-TR-0297 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44184
5 | TS | SPML-KCM-MEP-TR-0298 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0300 | Lighting | Light Fixtures | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0301 | Lighting | Light Fixtures | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44164
5 | TS | SPML-KCM-MEP-TR-0302 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44179
5 | TS | SPML-KCM-MEP-TR-0303 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0304 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44170
5 | TS | SPML-KCM-MEP-TR-0305 | Power Distribution | Capacitor Bank | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44174
5 | TS | SPML-KCM-MEP-TR-0306 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44164
5 | TS | SPML-KCM-MEP-TR-0307 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44203
5 | TS | SPML-KCM-MEP-TR-0308 | Plumbing | Irrigation System | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 43706
5 | TS | SPML-KCM-MEP-TR-0309 | Lighting | Light Fixtures | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | C | 43669
5 | TS | SPML-KCM-MEP-TR-0310 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-TR-0311 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44181
5 | TS | SPML-KCM-MEP-TR-0316 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44164
5 | TS | SPML-KCM-MEP-TR-0320 | HV System | Transformer | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44181
5 | TS | SPML-KCM-MEP-TR-0323 | Power Distribution | Capacitor Bank | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44185
5 | TS | SPML-KCM-MEP-TR-0324 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44184
5 | TS | SPML-KCM-MEP-TR-0328 | Lighting | Light Fixtures | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | B | 43730
5 | TS | SPML-KCM-MEP-TR-0329 | HV System | Transformer | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-TR-0332 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44181
5 | TS | SPML-KCM-MEP-TR-0333 | Lighting | Light Fixtures | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-TR-0334 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44164
5 | TS | SPML-KCM-MEP-TR-0335 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44181
5 | TS | SPML-KCM-MEP-TR-0336 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44164
5 | TS | SPML-KCM-MEP-TR-0339 | Power Distribution | Panels | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44164
5 | TS | SPML-KCM-MEP-TR-0340 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-TR-0341 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-TR-0342 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-TR-0343 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0344 | Miscellaneous | Miscellaneous | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-TR-0345 | Lighting | Light Fixtures | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-TR-0346 | Miscellaneous | Miscellaneous | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44174
5 | TS | SPML-KCM-MEP-TR-0347 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44179
5 | TS | SPML-KCM-MEP-TR-0348 | Warranty | Warranty | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-TR-0349 | General | As Built | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | E | 43827
5 | TS | SPML-KCM-MEP-TR-0350 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0353 | Power Distribution | ADCD | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 43851
5 | TS | SPML-KCM-MEP-TR-0355 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-TR-0356 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0357 | Power Distribution | ADDC | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44203
5 | TS | SPML-KCM-MEP-TR-0358 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-TR-0359 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44174
5 | TS | SPML-KCM-MEP-TR-0360 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44181
5 | TS | SPML-KCM-MEP-TR-0361 | Expansion | Expansion Joint | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 44202
5 | TS | SPML-KCM-MEP-TR-0362 | Registers | Registers | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44172
5 | TS | SPML-KCM-MEP-TR-0363 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-TR-0371 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44164
5 | TS | SPML-KCM-MEP-TR-0373 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-0374 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | B | 44179
5 | TS | SPML-KCM-MEP-TR-0375 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44189
5 | TS | SPML-KCM-MEP-TR-0395 | Signage | Wayfinding Signage | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | B | 44153
5 | TS | SPML-KCM-MEP-TR-0396 | EV | EV Charger | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44156
5 | TS | SPML-KCM-MEP-TR-0397 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44156
5 | TS | SPML-KCM-MEP-TR-0398 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44184
5 | TS | SPML-KCM-MEP-TR-0415 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44163
5 | TS | SPML-KCM-MEP-TR-0418 | Equipment | Equipment | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0419 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44165
5 | TS | SPML-KCM-MEP-TR-0420 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44173
5 | TS | SPML-KCM-MEP-TR-0421 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-TR-0422 | Lighting | Emergency Lighting | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44178
5 | TS | SPML-KCM-MEP-TR-0423 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44177
5 | TS | SPML-KCM-MEP-TR-0424 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44180
5 | TS | SPML-KCM-MEP-TR-0429 | ELV | BMS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44188
5 | TS | SPML-KCM-MEP-TR-0430 | Earthing & Lightning Protection | Earthing | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44189
5 | TS | SPML-KCM-MEP-TR-EL-0381 | ELV | CCTV | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44146
5 | TS | SPML-KCM-MEP-TR-EL-0382 | ELV | Access Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44146
5 | TS | SPML-KCM-MEP-TR-EL-0391 | ELV | Structured Cabling | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44153
5 | TS | SPML-KCM-MEP-TR-EL-0399 | Emergency System | CBS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44159
5 | TS | SPML-KCM-MEP-TR-EL-0400 | ELV | Public Address | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44159
5 | TS | SPML-KCM-MEP-TR-EL-0401 | ELV | Fire Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44159
5 | TS | SPML-KCM-MEP-TR-EL-0402 | Lighting | Lighting Control | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44159
5 | TS | SPML-KCM-MEP-TR-EL-0403 | EV | EV Charger | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44159
5 | TS | SPML-KCM-MEP-TR-EL-0404 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44160
5 | TS | SPML-KCM-MEP-TR-EL-0405 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44160
5 | TS | SPML-KCM-MEP-TR-EL-0406 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44160
5 | TS | SPML-KCM-MEP-TR-EL-0407 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44159
5 | TS | SPML-KCM-MEP-TR-EL-0408 | HVAC | Leak Detection | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44159
5 | TS | SPML-KCM-MEP-TR-EL-0409 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44160
5 | TS | SPML-KCM-MEP-TR-EL-0410 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44160
5 | TS | SPML-KCM-MEP-TR-EL-0411 | ELV | Disabled Toilet Alarm | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44159
5 | TS | SPML-KCM-MEP-TR-EL-0412 | Lighting | Skylight | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44159
5 | TS | SPML-KCM-MEP-TR-EL-0413 | Power Distribution | UPS | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44160
5 | TS | SPML-KCM-MEP-TR-EL-0414 | Plumbing | Water supply | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44163
5 | TS | SPML-KCM-MEP-TR-FFG-0372 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44182
5 | TS | SPML-KCM-MEP-TR-FFG-0384 | Fire Fighting System | Sprinkler system | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44146
5 | TS | SPML-KCM-MEP-TR-FFG-0385 | Power Distribution | Small Power | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44184
5 | TS | SPML-KCM-MEP-TR-FFG-0386 | Power Distribution | Generator | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44151
5 | TS | SPML-KCM-MEP-TR-HVAC-0389 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Electrical | NULL | Global Admin | A | 44153
5 | TS | SPML-KCM-MEP-TR-HVAC-0392 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44153
5 | TS | SPML-KCM-MEP-TR-HVAC-0393 | HVAC | Air Distribution | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44153
5 | TS | SPML-KCM-MEP-TR-HVAC-0394 | HVAC | Chilled Water | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44153
5 | TS | SPML-KCM-MEP-TR-HVAC-0416 | Seismic Support | Seismic Support | Al Forsan Central Mall | NULL | MEP | NULL | Global Admin | A | 44161
5 | TS | SPML-KCM-MEP-TR-PL-0383 | Plumbing | Drainage | Al Forsan Central Mall | NULL | Mechanical | NULL | Global Admin | A | 44146
5 | TS | SPML-KCM-PQ-0038 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43160
5 | TS | SPML-KCM-PQ-0039 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43160
5 | TS | SPML-KCM-PQ-0042 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43167
5 | TS | TS-0004 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43095
5 | TS | TS-0005 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43107
5 | TS | TS-0006 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43107
5 | TS | TS-0007 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43107
5 | TS | TS-0011 | NULL | NULL | Al Forsan Central Mall | NULL | Architectural | NULL | Global Admin | B | 43107
5 | TS | TS-0013 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43116
5 | TS | TS-0017 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43122
5 | TS | TS-0025 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43145
5 | TS | TS-0027 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43145
5 | TS | TS-0030 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43148
5 | TS | TS-0031 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43148
5 | TS | TS-0032 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43148
5 | TS | TS-0035 | NULL | NULL | Al Forsan Central Mall | NULL | Structural | NULL | Global Admin | A | 43151